### Section 3: Schedule of Requirements and Technical Specifications

Section 3a: Required Services

Rehabilitation of Saad Al-Udhaim Water Complex (1/4 m Gallon) and Desalination Treatment Plant (25M3/h) in Al-Udhaim Sub District, Diyala Governorate, Iraq

The proposed services focus on rehabilitating Saad Al-Udhaim water complex.  The current conditions for the most of compound units are experiencing frequent interruptions and disjunction to supply water service, resulted from major and secondary damages in the facility’s equipment and the structure due to the effects of attacks upon the liberation operations took place in the newly liberated areas.

The Contractor is required to perform the following required works and services:

- Civil works, including Removal of remaining portions of old existed Service Building and existed unit parts and debris to specified area out of the site; Pour Concrete for foundations and construct the steel structure required to lift the existed compounded Unit and construct the service building for water compound unit. Finishing works including installation of steel and PVC doors and windows.

- Mechanical works including installation and operate the Water Desalination Treatment Plant and the required pumps (Booster, Suction, Alum injector system and Chlorine unit) with connection pipes, valves and all required connections and accessories;

- Electrical works including supply, install and operate Electrical Transformer 250 KVA, Electrical Generator 150 KVA, also installation of new electrical Control panel board with cables and connections, Socket switches, lamps, ceiling and exhaust fans

- Other accessories and furniture: Water tank, Washbasin, Refrigerator, ½ set of Sofa and metal cupboard.

The Contractor is required to perform/execute above works with supply and installation of all other requirements according to the Bill of Quantities, and Technical Specifications. All supplied equipment and works must be performed under the laboratory test control of the End-user.

The Contractor shall visit the designated sites of the three water complex sites in Al-Muqdadiya District to become familiar with the condition of the work areas, the structures, the vicinity and the free space available for doing the work and storage of materials of construction.  It is the bidders’ responsibility to do research about the conditions of the site before they submit bids.

In general, the Contractor should become familiar with all prevailing conditions and circumstances which may affect the manner in which he will perform the work.

The Contractor shall implement the Project based on a detailed work plan which shall be approved by the Project Engineer.  The contractor is expected to produce/perform works which conforms in quality/quantity and accuracy of detailed specification.  The Contractor is to institute a quality control system to ensure adequate monitoring of the works progress at all times.

The prices proposed by the Contractor in the bill of quantities after the site visit shall be considered to include all that is required to carry out the work under the local conditions and the foreseeable and unforeseeable expenses which will be required to complete the work.

To perform the proposed services, the Contractor will work in close coordination and consultation with the technical team and UNDP Project Engineer.

### TERMS OF DELIVERY

The renovation works to be executed is to be completed within 120 Calendar Days from the date of site handover.

Section 3b: Related Services

| S. No. | Item/s to be Supplied4 | Qty. | Description/ Specifications of Goods | Related Services | Contract Duration |
| --- | --- | --- | --- | --- | --- |
| 1 | Supply and install water complex (1/4 m Gallon) and Desalination Treatment Plant (25M3/h) in Sadd Al-Udhaim Sub District, Diyala Governorate/Iraq | Lump Sum | As per BoQs | As per BoQs | 120 Calendar Days |

Further to the Schedule of Requirements in the preceding Table, Bidders are requested to take note of the following additional requirements, conditions, and related services pertaining to the fulfillment of the requirements:

| Delivery Terms of the Equipment | DAP |
| --- | --- |
| Exact Address | Saad Al-Udhaim, Al-Udhaim Sub district, Diyala Governorate, Iraq |
| Testing Requirements | All construction materials, mechanical and electrical equipment should be tested according to construction works specification. |
| Technical Support Requirements | As per the BoQ. |
| Duration of Contract | 120 calendar Days |
| Payment Terms | 100% of the total contract amount shall be paid within 30 days upon UNDP’s acceptance of the works as based on written acceptance certificate of completion of all works. |
| Conditions for Release of Payment | Certificate of payment from the UNDP Project Engineer duly certified by the Project Manager |