## Sheet1
BILL OF QUANTITIES, TECHNICAL SPECIFICATION & PRICE SCHEDULE FORM
ITB/KRT/DDR/18/009
Lot 3-part 2 – Rehabilitation irrigation canals of Elaalgaya Scheme-Eljabalian Locality –White Nile State
S/No | Specifications | Quantities | Unit | Unit Rate | Total (USD/SDG)
7 | Lot 3-part 2:Elaalgaia Project-Eljabalain Locality
7.1 | Earth Works (Rehabilitation of the main and secondary channels):
7.1.1 | Excavation of the main channel tail between the water intake and main pumping with total length of 200 meter and average width of 5 meter width and average depth of 1 meter. | 1000 | M3
7.1.2 | Excavation of the main channel between the main pumping house and boosting pump station with total length of 6,000 meter. Average width of the main channel is 5meter and the required depth is 1 meter. | 22500 | M3
7.1.3 | Excavation of the secondary channels of total length is 2500 meter. The average width of the secondary is 3 meter and the average depth required is 0.6m. | 4500 | M3
7.1.4 | Rehabilitation of the main and secondary channels earth embankments with dozer machine. | 70 | Dozer working hours
Subtotal for the Earth works
7.2 | Rehabilitation of the Hydraulic structures :
7.2.1 | Provision of materials and construction of 2 brick walls for the discharge chamfer. With good quality brick and cement sand mortar mix 1:6.price inclusive treating with water for at least 3 days. | 1 | item
7.2.2 | Provision of materials and constructing 101cm pipe diameter regulator with all accessories for channel (1). | 1 | item
- Price inclusive provision of steel pipes of 101 cm depth made of steel sheet of 6mm depth and steel flanges fabricated from 10 mm depth steel sheets.
- Provision of good materials and constructing regulator chamfer with good quality bricks and cement sand mortar mix 1:4 and treating with water. The walls shall be of 3 bricks up .067 of the walls height and the rest of 0.33 height shall be built with 2 brick walls.
- Provision of materials and plastering the walls of well internally and at the with cement sand mortar mix 1:6.
- Price inclusive provision and installation of steel gate with all standard accessories for regulator 101cm.
7.2.3 | Provision of materials and rehabilitation of regulators size 76 cm. | 3 | item
- Price inclusive removal of the existing damages regulator
- Provision of good materials and constructing regulator chamfer with good quality bricks and cement sand mortar mix 1:4 and treating with water. The walls shall be of 3 bricks up .067 of the walls height and the rest of 0.33 height shall be built with 2 brick walls.
- Provision of materials and plastering the walls of well internally and at the with cement sand mortar mix 1:6.
- Repaining the existing gate by provision of the missing parts and re-fixing it propely
7.2.4 | - Price inclusive provision of steel pipes of 50 cm depth made of steel sheet of 6mm depth and steel flanges fabricated from 10 mm depth steel sheets. | 1 | item
- Provision of good materials and constructing regulator chamfer with good quality bricks and cement sand mortar mix 1:4 and treating with water. The walls shall be of 3 bricks up .067 of the walls height and the rest of 0.33 height shall be built with 2 brick walls.
- Provision of materials and plastering the walls of well internally and at the with cement sand mortar mix 1:6.
- Price inclusive provision and installation of steel gate with all standard accessories for regulator 50cm.
7.2.5 | Provision of materials and construction of masonry pavement with granite stone and cement sand mortar mix 1:4 and curing with water | 70 | M2
7.2.6 | Abuashreen channels: | 12 | N0
Provision of 35cm diameter steel pipes for the abuashreen channels with following specifications:
- The steel pipe shall be fabricated for good quality 6 mm steel sheets and the flanges of 10 mm steel sheets.
- Each pipe shall have steel gate fabricated from good quality steel sheet of 10 mm with steel handle bolted to the steel pipe.
- Price inclusive fixing at the position.
7.2.7 | Excavation of Abuashreen channels with abuashreen opener .Each abuashreen shall be of total 700 meter length. | 12 | N0
Subtotal for the Rehabilitation of Hydronic Structures
7.3 | Mechanical Works:
7.3.1 | Supply spare parts and maintenance of existing diesel engine model CUMMINS 6BTA 75 KW. Bidders are encouraged to assess the machine before biding. | 1 | Item
7.3.2 | Supply spare parts and maintenance of existing diesel engine model CATTERPILLAR C7 of 150 KW. . Bidders are encouraged to assess the machine before biding. | 1 | Item
Subtotal for Mechanical works
Total of the offer of Alaalgya Project