## Cover Page
UNDP
UNITED NATIONS DEVELOPMENT PROGRAMME
ACCESS TO JUSTICE AND RULE OF LAW
BOOK 1: SCHEDULE OF QUANTITIES
CONSTRUCTION OF WALL FENCE FOR THE VOCATIONAL TRAINING CENTRE AT WAU PRISONS IN WAU STATE SOUTH SUDAN.
All prices in US Dollars
| Project No.: | ………
| Date: | 17 December, 2018
| Document No: | …..

## Preambles
PRICING PREAMBLES
1.0 General
1.1 The Bill of Quantities shall be read in conjunction with the Conditions of Contract, Specifications, Drawings and Employer’s requirements and the Tenderer shall provide against the bill rates or in the prices for the full scope of the work covered by the Contract, no claim or variations shall be considered on account of the Tender’s failure to comply with this provision.
1.2 The various documents collectively referred to herein as the Bill of Quantities shall jointly constitute the Bill of Quantities referred to in the Conditions of Contract and these preambles are to be read in conjunction with item descriptions in the Bill of Quantities.
1.3 Lump Sum values shall not be inserted where unit rates are applicable and the Tenderer shall ensure that identical items occurring in separate bills are not priced at different rates, unless this is the deliberate intention.
1.4 The Tenderer shall check against the summaries that each copy of the Bill of Quantities is complete in the number of pages and in the reproduction of each page. The Tenderer’s unit rates, prices and extensions shall be entered clearly by hand in black ink.
1.5 Unit rates, prices and extensions shall be given in the United state Dollar with cents taken to two decimal places or any other valid currency value taken to two decimal places.
1.6 The Bill of Quantities has generally been measured in accordance with the Principals of Measurement (International) for Works of Construction (June 1979), as published by the Royal Institution of Chartered Surveyors with amendments made to suit local practice and conditions. The Quantities inserted against items in the Bill of Quantities are estimated quantities for the Works for the purpose of Tender evaluation, and the Tenderer shall be deemed to have checked and verified such quantities in the compilation of his Tender Price prior to the submission of his Tender. Upon the award of the Contract, the priced Bill of Quantities shall be used solely for evaluating interim payments due to the Contractor, and as a schedule of rates for establishing the value of variations.
1.7 The Contractor shall not use the Bill of Quantities for the purpose of ordering materials or arranging Subcontractors. References to these activities shall be the Specifications and Drawings and instructions issued by the Engineer.
1.8 All items in the Bill of Quantities shall be deemed to have a monetary value, whether priced or unpriced. In the absence of a unit rate or price against any item, the cost shall be deemed to have been included elsewhere within the Contract Price and the work described to that item shall be executed by the Contractor without any additional payment.
1.9 The descriptions in the Bill of Quantities may be incomplete and the Tenderer is referred to the Drawings, Photographs and Specifications for complete information in respect of all the relevant descriptions, quality, dimensions, capacities, design parameters and the like.
2.0 Format of Descriptions
2.1 In addition to common abbreviations the following have been adopted; POM (I), Principal of Measurement (International) for Works of construction dated June 1979 as published by the royal Institution of Charted Surveyors, London
mm- Millimeter Pr-Pair
M-Linear Meter No-Number
m2- Square Meter Kg-Kilograms
m3- Cubic Meter
3.0 Rates
3.1 Rates and Prices shall be all inclusive, comprehensive and include the following:
a) All obligations imposed by the Contract.
b) Complying in every respect with the requirements and the considerations of the Specifications and Drawings.
c) All considerations arising from the definitions incorporated in each Preamble section.
d) Labour for fixing and all associated costs.
e) Materials and goods and all associated costs
f) Fitting and /or fixing materials and goods in any position, hoisting to any height.
g) Use of Scaffolding, plant, equipment and tools.
h) Any additional labours usually associated with measured items.
i) All necessary protection of the Works, removing all casings and temporary covering and making good and clearing away upon completion.
j) All applicable taxes, duties, charges, government levies, landing charges and transport.
k) Overheads & profit.
4.0 Measurements
4.1 All measurements are net and the rates shall include for all laps, waste, working space and trade or traditional allowances.
4.2 The pricing of materials shall take account of the following:
a) Pricing Preambles, Drawings and specifications shall apply reciprocally between the various sections of the Works, unless otherwise described.
b) Materials shall be of the specified quality unless otherwise described.
c) All materials shall be transported, handled, stored and fixed in accordance with the printed instruction or recommendations of their manufacturer or suppliers.
d) Protection of completed work, all casings and temporary coverings and making good and clearing away upon completion.
4.3 Contingency: In the event that the contractor meets unmeasured works, the contractor shall inform the engineer in writing. The engineer shall ascertain the unmeasured works to verify the contractors claim. The contractor shall submit its claim and wait for approval from the engineer/client. The contractor shall use the same rates as in the contract for similar items. No new rates shall be applied unless the unmeasured work in its nature does not exist in the already mentioned items in the priced bill of quantities.
5.0 Discrepancies
5.1 Any discrepancy arising in terms of these Preambles and the items contained within the Bill of Quantities must be brought to the attention of the Engineer for his clarification prior to the submission of tender.
EARTH WORKS
§ All quantities for excavation have been measured net with no allowance for increase in bulk or working space.
§ The Tenderer shall allow in this excavation rates for excavating in any material, including running sand and rock, commencing excavation at any depth, excavating below the normal water table, excavating around existing services and mains, supporting the vertical sides of excavations, working space and filling soft spots.
§ Rates and Prices to include,
a) Excavating by whatever means are necessary including hand excavation in any kind of ground, except rock and boulder rock.
b) Trimming or grading ground to produce level surfaces or surfaces to falls or slopes.
c) Ramming and compacting sides and bottoms of excavations and supports to sides.
d) Keeping free from water including any dewatering as necessary.
e) Any hand excavation required around existing services or the like.
CONCRETE WORK
§ The rates for all concrete work shall include for the following:
a) Concrete test cubes and testing costs wherever required.
b) Mixing, hoisting and placing and compacting on the surfaces of any material or on formwork.
b) The forming any construction joints, including any required preparation for adjacent pours, together with expansion joints or the like.
d) Curing and protecting concrete surfaces from harmful weather conditions
e) All necessary keys to concrete surfaces to receive in-situ finishes.
REINFORCEMENT
§ The rates for bar reinforcement shall include for the following;
a) Positioning and protecting starter bars, Straightening (If required) cutting to length and bending reinforcement to required shapes.
b) Cleaning and wire brushing.
c) Provision of supports (excluding links and stirrups) steel binding wire and
approved/proprietary distance pieces.
SHUTTERING
§ The rates for Shuttering or moulds as appropriate shall include for the followings;
a) All cutting and waste including raking curved or circular cutting and notching around pipes, ducting and fittings.
b) Setting up, strutting and supporting at any height above the structure subject to any limitations imposed by the engineer including all pops, stays struts, wedges and bolts etc.
c) Carefully coating with shutter oil ensuring that no shutter oil is applied to surfaces of reinforcement.
d) Rubbing down, filling and making good the surface of concrete after removal of shuttering.
MASONRY
§ The rates for brick walls shall include the following:
a) Straight raking curved and circular rough or fair cutting, plumbing at angles, cutting and bonding at angles, openings and intersections, building in to and/or against adjacent work, wedging and pinning up to soffits.
b) All necessary keys for in-situ finishing.
c) All necessary wall ties, dowels, straps, sleeves. Channels and other like fixings built-in
at junctions between brick work and insitu concrete including casting in, drilling,
bolting and the like.
d) All necessary brick work reinforcement at junctions between brick work and walls
construction joints or the like and openings.
WOODWORK
§ The rates for wood work shall include for the following;
a) All joints in the running length including structural joints.
b) Cutting and fitting to steelwork, trimming around opening, notching, boring and
sinking.
b) Wood work shall be fixed with non-corroding nails and screws and unless otherwise described all plugging and pellating shall be deemed to be included.
FINISHES
§ The rates for all work-in this section shall include for the followings:
a) Straight, racking, curved and circular cuttings or the like and all consequent wastages.
b) All setting out temporary rules, screeds, templates and supports.
c) Curing and cleaning off/down upon completion.
d) All labours and making good around pipes, ducting and fittings and the like

## Scope of works
PROJECT: CONSTRUCTION OF VOCATIONAL TRAINING CENTRE IN WAU PRISONS IN WAU SATE SOUTH SUDAN
SCOPE OF WORK
This document serves as a Scope of Work (SOW) to the Independent Contractor Agreement for the construction of Vocational Training Centre in WAU prisons
1. Description of Services.
Location: Contractor agrees to perform all required contracting Services relating to the construction of VTC owned by WAU prisons services
Method of Performing Services: Contractor will determine the method, details, and means of completing the Project. Contractor agrees to devote the required personnel for a minimum 120 calendar days to the Project.
Tools and Instrumentalities: Contractor, at its own expense, will supply all tools, instrumentalities and all building and installation materials for the Project, including without limitation paint, steel metal frames, ceiling mounted fan units, plumbing materials, iron poles, rain gutters and iron sheets etc.
Finishing Materials: Company shall be responsible for procuring the finishing materials as provided herein in the BoQ.
Work Items:
A) Wall Fence
Exterior and Interior Work
Block or/ Brick walls out of burnt clay bricks
Plaster works
Guard House
Exterior Work
Block or/ Brick walls out of burnt clay bricks
Metal doors and windows
Metal/timber roof structure plus roofing iron sheets
Painting works;
Fill exterior surfaces as necessary, prime all the plaster work
Paint siding, trim, doors, soffits, fascia, shutters, gutters, downspouts using 3-color paint scheme (weather guard – cream paint)
Interior Work
Block or/ Brick walls out of burnt clay bricks for all internal partitions.
Painting works;
Fill interior surfaces as necessary, prime all the plaster work
Paint siding, trim, doors, soffits, fascia, shutters, gutters, downspouts using 3-color paint scheme (vinyl silk – white paint)
Electrical wiring with all the required accessories
Fixing the roof mounted ceiling fans
2. Contractor’s payments.
In consideration for the Services to be performed by Contractor, UNDP agrees to pay Contractor the amount awarded based on the following payment schedule/milestones:
1. Milestone 1: 40% of contract amount upon approval of satisfactory completed activities as per stated in the bills of quantities;
2. Milestone 2: 50% of contract amount upon approval of satisfactory completed activities as per stated in the bills of quantities;
3. Milestone 3: 10% after defect liability period of 12-month;
3. Deadline.
Contractor shall complete the Project within 120 calendar days. For each additional duration, the conditions stated in the conditions of contract shall be applied.
17 December, 2018

## Preliminaries
UNDP
UNITED NATIONS DEVELOPMENT PROGRAMME
ACCESS TO JUSTICE AND RULE OF LAW
Book 1: SCHEDULE OF QUANTITIES
Project No.: | ……….
Project: |  | CONSTRUCTION OF VOCATIONAL TRAINING CENTRE AT WAU PRISONS IN WAU STATE SOUTH SUDA
Item: | BILLS OF QUANTITIES FOR PRELIMINARY WORKS
Date: | 17 December, 2018
All prices are in USD
ITEM | BRIEF DESCRIPTION OF WORK | UNIT | QTY | UNT COST | TOTAL COST
1. General
1.1 | Pre-construction work, mobilization activities. The bidders are strongly advised to visit the site before submitting their quotations to familiarize with the existing status of the undelaying strata | LS
The contractor shall provide and maintain temporary sheds for the storage of materials, tools, and tackle and the use of all persons employed on the Site. Those used for the storage of cement and other perishable materials and the like are to be weatherproofed at all times
Provide, maintain and keep in a clean condition adequate temporary sanitary accommodation and facilities in accordance with local regulations for all persons employed on the Works.
Allow for supplying temporary electricity for the Works and facilities of the contractor including 'connection, distribution system for the work, internal arrangements and all payment to the authorities for connections. It is the responsibility of the Contractor to ensure steady and uninterrupted power supply to Works. The Contractor shall not be entitled to claim and the Employer shall not pay cost incurred by the Contractor for using electric power generators or for using other alternative power supply method in case there happened to be disruptions to normal power supply due to any reason.
1.2 | Post construction works and clean up. | LS
1.3 | Allow for providing and maintenance of name board and advertising board to the specifications and as directed by the Engineer. | Item
TOTAL FOR PRELIMINARIES

## Fence 392m
Bill of Quantities for the Construction of Concrete Block Wall Perimeter Fencing to Wau VTC Wau State, RSS.
| Date: | 17 December, 2018
S.No. | Description | Qty | Unit | Rate (USD) | Amount (USD)
A | EXCAVATIONS AND EARTHWORKS
Total perimeter wall length 281m
A1 | Clearing and preparation of the site 392m long and 1.5m wide including removal of existing fence (chain link )and disposed off as directed | 591 | m2
a) back filling with selected excavated material & consolidating. Surface treatment; compaction before filling / foundation.
b) disposal of surplus soil as directed & keeping all excavations free from water unless other wise measured separately.
c) any additional excavation for working space.
Excavation & Earthwork Supports
A2 | Excavation of trenches for foundation walls, 60cm wide and an average depth of 60cm in any material except rock requiring blasting, and removal of surplus as directed. | 141 | m3
A3 | Backfill excavated trench with suitable excavated and borrowed materials. Compact backfill materials in 150mm layers using suitable compaction equipment. | 134 | m3
STONE PITCHING
| Rate shall include for form work depositing, handling, hoisting into position, vibrating, curing etc. and making good after removal of formwork etc. |  | Note
Stone pitching
A4 | Provide a strip foundation with stone pitching 330mm thick stone rubble masonry walls in strip/plinth foundations to maximum depth of 600mm. Use 1:2 cement : sand design mix concrete. | 78.4 | m3
CONCRETE WORKS
A5 | Supplying and placing reinforced concrete Grade M20to columns (230mm x 230mm) (No. 260) at each end of 3000mm cc wall . the columns should starting from the foundation base, the foundation base should be 600mm x 600 mm with concrete thickness of 230mm, the reinforcement spacing of 200mm c/c at base of foundation. The upright bars should be 04 in number size 10mm | 62.66 | m3
MASONRY WORKS
| Rate shall include for lifting, handling, weighting all rough and fair cutting, plumbing angles, normal straight cutting, forming rebated reveals and raking out joints for plastering. |  | Note
Brick work/ Hollow concrete block walls: bedded and jointed in cement and sand (1:4) mortar
A6 | Provide 2,000mm high wall, with 200mm thick hollow concrete blocks or/ (230mm thick brick wall) in cement sand (1:4) mortar: Provide expansion joints at interval of 3000mm. | 784 | m2
Plaster work
A7 | Provide and apply smoothly finished plaster using 1:3 cement -sand mix mortar on both sides of 230mm thick wall. Note that the plaster includes all the block work above the ground level. | 784 | m2
A8 | Supply and fix 300x75mm ex. Concrete coping on top of walls with weather throught as per the drawings. | 392 | m
A9 | Supplying and placing mass concrete Grade M20 ramp at base of entrance and exit gates size 3000 x 3000 x100mm. | 3.6 | m3
Reinforcement
Rate to include for supplying, cleaning, cutting, bending, fabricating, placing and the provision of all necessary temporary fixings and supports etc. including binding wires, bends, hooks, tying wires, chairs, distance blocks, steel separators/spacers
Tor steel reinforcement (to BS 4449 and characteristic strength fy = 460N/mm2) and Mild steel reinforcement ( to BS 4449 and characteristic strength fy = 250N/mm2)
A10 | R6 mild steel reinforcement bars/stirrups to columns, intermediate at 3000mm c.c | 872 | Kg
A11 | High yield reinforcement bars ( Y-12) | 3486 | Kg
F | Steel Gate
A12 | Provide and install a roll of standard razor wire -400mm diameter, 6m/roll on top of walls and columns. Fully clip and swage razor wire to angle iron and straightening wires as per manufacturer's specification | 65 | rolls
A13 | Provide and install 40mmx40mmx4mm angle iron as shown on drawing at each columns. | 133 | No.
A14 | Provide and install galvanized aligning link straightening wire (at least three rows)for razor wire installation -100m/roll | 10 | Rolls
A15 | Provide and install double leaf steel gate: 5,000.0mm wide, and 20000mm high, double leaf comprising 50*50*3mm SCS as vertical components and 60*50*3mm RHS as peripheral members as shown on the sketch. Note that a pedestrian access 800mm wide and 2100mm high for pedestrians shall be provided at this gate. provide all the necessary locking systems | 2 | LS
TOTAL FOR WALL FENCE

## Guard house
BoQ for guard house at Wau VTC
| Date: | 17 December, 2018
Item | Description | Qty | Unit | Rate US$ | Amount US$
B | EXCAVATIONS AND EARTHWORKS
External Size of 4000mm x 3000mm
Unless other wise stated, Rate shall include for
a) back filling with selected excavated material & consolidating. Surface treatment; compaction before filling / foundation.
b) disposal of surplus soil as directed & keeping all excavations free from water unless other wise measured separately.
c) any additional excavation for working space.
Excavation & Earthwork Supports
B.1 | Clearing and preparation of the site including cutting down and removal of top soil up to a depth of 150mm and disposed off as directed. | 20 | m²
B.2 | Excavation of trenches for wall foundations up to 0.9m deep and 0.6m wide in any material except hard rock requiring blasting, and removal of surplus as directed. | 7.6 | m³
B.3 | Filling & Back filling with selected soil( marram)
B.4 | Filling around foundation masonry with selected excavated materials: ram and compact well | 5.6 | m³
B.5 | Filling under floors with marram or other approved quality imported filling material. Spreading, watering and well ramming in | 12 | m³
B.6 | Anti - termite treatment to fillings and tops of foundations: as " Aldrex" or equal and approved insecticide treatment: applied in accordance with the manufacturer's printed instructions : include for 10 years warranty period. | 12 | m²
CONCRETE WORKS
a | Rate shall include for form work supply, fixing, depositing, handling, hoisting into position, vibrating, curing etc. and making good after removal of formwork etc. | Note
b | Reinforcements are paid separately unless otherwise specified in the item | Note
c | Rate shall include for supplying and laying of gauge 1000 polythene on ground, where concrete is in direct contact with ground, before pouring concrete unless other wise measured separately. | Note
In Situ Concrete
B7 | Supplying and placing of Gr.20 (1:2:4 ratio) 100mm thick concrete to floor beds. | 12 | m2
B8 | Ditto: 100mm thick splash apron beds 600mm wide laid to fall around the building. | 8.4 | m2
B9 | Ditto for strip foundation | 1.93 | m³
B10 | Ditto: for roof Tie beams | 0.64 | m³
Reinforcement
Rate to include for supplying, cleaning, cutting, bending, fabricating, placing and the provision of all necessary temporary fixings and supports etc. including binding wires, bends, hooks, tying wires, chairs, distance blocks, steel separators/spacers
Tor steel reinforcement (to BS 4449 and characteristic strength fy = 460N/mm2) and Mild steel reinforcement ( to BS 4449 and characteristic strength fy = 250N/mm2)
B11 | R6 mild steel reinforcement bars for stirrups | 16.5 | Kg
B12 | High yield reinforcement bars ( T12) | 65 | Kg
Formwork as specified : to
B13 | Ditto: for sides of ring beams | 3.22 | m²
B14 | Ditto: Sides of floor slab | 1.5 | m²
MASONRY WORKS
| Rate shall include for lifting, handling, weighting all rough and fair cutting, plumbing angles, normal straight cutting, forming rebated reveals and raking out joints for plastering. | Note
Masonry Work
Up to DPC level
B15 | Twenty centimetre thick solid concrete block walls in cement sand (1:4) mortar to splash apron and foundation masonry below the floor slab. | 14 | m²
B16 | 150mm thick walls in standard precast hollow cement blocks in 1:3 cement sand mortar for superstructure walls. | 42 | m²
THERMAL AND MOISTURE PROTECTION
Damp Proof Course
B17 | Horizontal damp proof course: bituminous: laid horizontally on screeded 20 mm thick (1:3) screeded beds to receive block walls. | 3.22 | m²
Damp proof membrane
B18 | Horizontal damp proof membrane :1000 gauge polythene membrane: laid on compacted fillings (measured separately) in ground floor beds. ( The rate shall include for laps & wastage). | 12 | m²
STRUCTURAL WOODEN WORKS
Definitions
Note :
| a] For the description of materials and workmanship refer "Specification of works", "preambles" and "Drawings". | Note
| b] Rate shall include for | Note
| b.1] All shop fabrication work, marking, delivery, unloading, hoisting, erecting and fixing as per detail drawings. | Note
| b.2] Members of any length. | Note
| b.3] Cutting to size and shape and joints in the running length. | Note
| b.4] Machine drilled bolt, holes, bolts, nuts and washers, cleats, shoe and gusset plates and all other connections. | Note
Fabricating and erecting framed structures
B19 | Supply and fix hard timber roof truss, RT1 spanning 4000mm long x 1200mm high, consisting of 4"*2" rafters, 6" * 2" chords and 3" * 2" ties & struts hard timber/mahogany members as per the drawings. | 2 | No
B20 | Supply and Fix hard timber 6" * 2" rafters. | 20 | m
Purlins
B21 | Supply & fix of 3"*2" hard timber/mahogany to purlins at a centre to centre spacing of 900mm centres. | 20 | m
ROOF COVERINGS, CEILING
| Rate shall include; | Note
a.01 | All, rivets, nails, clips, strips and delivering and fixing in position. | Note
a.02 | All timber shall apply Priming backs & applying two coats of an approved wood preservative before fixing. | Note
a.03 | All timber including plywood sheets shall have Final Finish; Two coat of wood preservative, two coats of primer, two coats of wood sheen spray paint. | Note
a.04 | Roof plumbing shall be measured & grouped separately; | Note
Roof Covering
B22 | Supplying & fixing of gauge 28 pre-painted Super VI profiled roofing sheets of approved colour: fixed with J-bolts to 150 x 50 x 2mm zed purlins ( measured separately) and rubber capping to tops of bolts. Note that the area is the projected one. | 24.1 | m²
Ridges
B23 | Supplying & fixing Gauge 26 prepainted ridge cap; 650mm girth (average) in position complete with all necessary roofing screws or hooks as required. | 13 | m
Valance / Barge Board
B24 | 25x225mm high timber valance board / barge board fixed to edges of rafters including necessary fittings screws and nails etc.: including wood preservative and painting all as per drawings | 19 | m
B25 | Supplying & fixing of PVC half round eave gutters of four inch dia. including all necessary accessories, as per drawings | 19 | m
B26 | Supplying & fixing of 75mm dia PVC rain water down pipes with metal straps to concrete block work as per detailed on Drawing at 1000mm centres vertically | 6 | pcs
0
DOORS AND WINDOWS
a | The work shall include supply, fabricate and installation of doors, windows, made out of approved quality timber Jak or equivalent to be finish as per the respective specification & drawings. | Note
b | Doors & Windows frame sections to be of,
b.01 | Outer frame & Inner frame - 75mm x 100mm minimum - Finish Size, unless otherwise stated. | Note
b.02 | The contractor shall submit shop drawings for the approval of the Architect & Engineer, prior to fabrication. | Note
b.03 | The contractor shall refer to all relevant specifications and drawings prior to pricing and it shall be his responsibility to complete the said works to the entire satisfaction of the Engineer at no additional cost. | Note
b.04 | All samples shall be provided for Engineer's approval prior to purchase of material. | Note
b.05 | Where swing doors has been specified prices shall include for provisions of floor hinges. | Note
c | Rates shall include;
c.01 | Hoisting and fixing in position, drilling and making good. | Note
c.02 | Brass Nails, Brass screws, glue, rawl plugs etc.,. | Note
c.03 | Framing together all work in accordance with the best practices. | Note
c.04 | Priming backs & applying two coats of an approved wood preservative before fixing. | Note
c.05 | Final Finish; Two coat of wood preservative, two coats of primer, two coats of wood sheen spray paint. | Note
c.06 | Rate to include for providing sundry items related to the door & windows like Glass blocks etc.. where necessary as a Architectural Feature to the door or window. | Note
c.07 | Rate shall include for 5mm thick clear float glass/ wired glass /tinted glass /translucent glass as appropriate to suit the respective doors and windows as shown in the drawings. | Note
c.08 | Rate shall include for ply wood sheets of approved colour with melamine coat on both sides where necessary. | Note
c.09 | Rates shall include for fixing timber frame, door sash / window casement brass fixing screws, lock sets with 3 keys manufactured in Europe to be used on all doors.
d | Only 16% of moisture content is recommended for all timber. | Note
e | All timber shall be pressured impregnated termite proofed, seasoned, planed timber and sand papered by hand to have smooth finish and to receive paint. | Note
f | Preservative Treatment
f.01 | Minimum of two application of C I C wood preservative or approved equivalent. | Note
f.02 | Preservative treatment for back of door & door frame in contact with masonry or concrete. | Note
g | Sizes
g.01 | The sizes given in the drawings and description of Bill of Quantities are finished sizes and subject to same permitted in the specifications. | Note
g.02 | The contractor shall check the measurement of openings physically at the site before fabricating the doors & windows. | Note
g.03 | Door / window frames are twice rebated and backed as appropriate. The sizes are as given in the detail drawing. | Note
g.04 | Mullions and transoms shall be rebated or non rebated as appropriate. The sizes are as given in the detail drawing. | Note
g.05 | Finished thickness of door & window sashes sash shall be 32mm and if there is any discrepancy in the sizes and detail given in the drawings and Bill of Quantities, the same given in the drawing shall prevail. | Note
h | Ironmongery
h.01 | All the locks shall be union / Yale or approved equivalent supplied by authorized dealer appointed by the manufacturer & approved by the Architect. | Note
h.02 | All ironmongery shall be heavy quality brass of approved European manufacture subject to approval of the Architect, ironmongery samples should be submitted for approval. | Note
j | Painting / Final Finish
j.01 | Unless otherwise stated all surface of timber Doors & Windows and casements and plywood door sashes shall be applied with two coat of wood preservative, two coats of primer, two coats of wood sheen spray paint. | Note
H | Doors and Windows
B27 | Metal door set, type D1, of size 900x2800mm high overall including 400mm high steel louvre PV, comprising of door profile steel sections frame fully welded and mitred at corners, bottle steel section shutter frames: the bottom half infilled with 2.5mm thick mild steel plate and the rest infilled with 5mm thick glass grilled with steel metal as shown in the drawing: include for all necessary door locks, iron mongery, final finish, & fixing to concrete or blockwork as per drawings. | 1 | Nos.
Windows
B28 | Window, type W1, steel, size 1000x1500mm high overall including 400mm high steel louvre PV, Comprising of 60x40x4mm RHS frame fully welded and mitred at corners, Zed & Tee section side hung 5mm thick glass infilled window sashes, :include for all necessary fasteners, burglar proof/grills and iron mongery, final finish, & fixing to concrete or blockwork as per drawings. | 1 | Nos.
FLOOR, WALL AND CEILING FINISHES
a | The contractor is advised to refer to the specification prior to pricing of this section of work | Note
b | The rate shall include for all temporary rules, screeds, grounds etc. for raking out joints of new brick work or hacking new concrete for key, internal & curved angles, joints between different surfaces arises quirks, inter sections between curved or irre | Note
c | All samples shall be provided for approval by the Engineer prior to purchase of materials. | Note
Wall Finishes
B29 | 20mm thick cement & sand (1:3) render finished semi rough with wood float on external faces, on block walls or concrete surfaces | 42 | m²
B30 | 12mm thick cement lime sand (1:1:3) plaster finished smooth with lime putty or approved equivalent on internal faces, on block walls or concrete surfaces. | 37.2 | m²
Floor finishes
B31 | 25mm. thick cement and sand 1:3 screed finished smooth with coloured cement floating including veranda. | 9.36 | m²
Plinth Plaster
B32 | 20mm. thick cement and sand 1:3 plinth plaster finished smooth steel floating. | 14 | m²
Ceiling Finishes
B33 | Provide and install hardboard ceiling false ceiling. The rate shall include wooden frames, all other activities required to complete the work. | 9.36 | m²
PAINTING
a | Rate shall include for preparation of surface cleaning down, smoothing, knotting, stepping etc. protection of floors and fitting, removing & replacing door and window, furniture, and cleaning windows etc. upon completion. | Note
b | Paint shall be from approved colour with approved manufacturer. | Note
Walls
B34 | Prepare and apply one coat of primer and two coats of weather shield paint of approved colour and quality to external faces of walls | 42 | m²
B35 | Prepare and apply one coat of primer and two coats of emulsion paint of approved colour and quality to internal faces of walls | 37.2 | m²
B36 | Prepare and apply one coat of primer and two coats of emulsion paint of approved colour and quality to the ceiling. | 9.36 | m²
B37 | Ditto: Plinths | 14 | m²
ELECTRICAL INSTALLATIONS
a | Unless otherwise stated, Rates in Bill of Quantities shall include all necessary materials Cables, conduits, PVC sunk box, bulbs, switches etc.) and labour required to complete the electrical installation to good working order. | Note
b | Except where specifically stated, all costs associated with provision of all holes, openings, chases, ducts and other builders' work required for installation and make them good, shall be included in the rates. | Note
c | Testing and commissioning of the electrical installation is to be carried out by the contractor and Cost of such testing and reports to be included in the rates unless otherwise mention separately. | Note
d | All types of fittings, materials, painting and finishes shall be approved by the Engineer prior to installation. | Note
Sub Distribution Board (SDB-1)
L.1 | MCCB, MCB shall be manufactured by Merlin Gerin , F&G, Moler or equivalent & approved by the Engineer.
01 Nos 40A , 2P RCCB
01 Nos 20A , 1P MCCB
02 Nos 6A , 1P MCCB
03 Nos 10 A , 2P MCB
01 Nos 30 A , 2P MCB
Set of Cu bus bars with neutral
Cu earth bar
Phase indicator lamps
B38 | Wiring & other installation cost to include supply of 4 core 16mm2 diameter armoured underground electric cable connection to the nearest power supply. | 1 | Nos.
Final Circuit Wiring
Rates for final circuit wiring shall include all necessary switches, sockets, materials Cables, conduits, PVC sunk box, & junction boxes, draw wires, etc. and labour required to complete the electrical installation to good working order.
Light Point Wiring
B39 | Wiring and installation (including supply of all materials) of the light points using approved type PVC insulated PVC sheathed 1 mm² copper cable and 2.5mm² Earth cable drawn through securely fixed concealed PVC conduit. (Switches shall be ABB / Clipsal / | 2 | Nos.
13ASocket Outlet
B40 | Supply & installation of 13A fused shuttered switched socket outlet to comply with relevant BS standard (Clipsal, Orange, Crabtree/ Tenby/ABB or equivalent). Wiring (including supply of earth wire & all other material required ) of above socket outlet | 1 | Nos.
Fan Point Wiring
B41 | Wiring & installation (including supply of all material, earth wire & switch) for ceiling / wall mounted fans using approved type 1.5 mm2 PVC insulated PVC sheathed copper cable & 2.5mm2 earth wire drawn through securely fixed PVC conduits. | 1 | Nos.
Fittings & Equipment's
Light Fittings
B42 | Supply and installation of Pendent lamp/Fluorescent fitting at least 4ft long complete with 36 W CFL (Philips or equivalent) Lamp suitable for indoor use including all other necessary accessories like terminal block etc. (accessories - thorn / Philips or equivalent & fitting | 2 | Nos.
B43 | Supply and installation of energy efficient lamps for out door use complete with all other necessary accessories like terminal block etc. (accessories - thorn / Philips or equivalent & fitting | 2 | Nos.
Ceiling Fans
B44 | Supply and installation of 56" sweep ceiling fan (KDK, National or equivalent) complete with regulator, fan hook, extension rod & attachment - Guarantee cards should be provided from accredited agent before installation including all wiring of 2.5mm2 | 1 | Nos.
TOTAL FOR GUARD HOUSE

## Summary
Summary for the construction of concrete block/Brick wall perimeter fence, gurad house at Wau VTC prisons
Date: | 17 December, 2018
S.No. | Item | Amount(USD)
1 | TOTAL FOR PRELIMINARIES | 0
2 | TOTAL FOR WALL FENCE | 0
3 | TOTAL FOR GUARD HOUSE | 0
| TOTAL OF PROJECT COST | 0