* United Nations Development Programme*

**BIH/**

**REQUEST FOR PROPOSAL**

**“Communication services for design and promotion of MZ Project results (2015-2019)”**

RFP No.: BIH/RFP-007-19

Project: Strengthening the Role of Local Communities/ Mjesne zajednice in Bosnia and Herzegovina

Country: Bosnia and Herzegovina

Issued on: 8 May 2019

 **Contents**

[Section 1. Letter of Invitation 4](#_Toc6313300)

[Section 2. Instruction to Bidders 5](#_Toc6313301)

[A. GENERAL PROVISIONS 5](#_Toc6313302)

[1. Introduction 5](#_Toc6313303)

[2. Fraud & Corruption, Gifts and Hospitality 5](#_Toc6313304)

[3. Eligibility 5](#_Toc6313305)

[4. Conflict of Interests 6](#_Toc6313306)

[B. PREPARATION OF PROPOSALS 6](#_Toc6313307)

[5. General Considerations 6](#_Toc6313308)

[6. Cost of Preparation of Proposal 6](#_Toc6313309)

[7. Language 6](#_Toc6313310)

[8. Documents Comprising the Proposal 6](#_Toc6313311)

[9. Documents Establishing the Eligibility and Qualifications of the Bidder 7](#_Toc6313312)

[10. Technical Proposal Format and Content 7](#_Toc6313313)

[11. Financial Proposals 7](#_Toc6313314)

[12. Proposal Security 7](#_Toc6313315)

[13. Currencies 8](#_Toc6313316)

[14. Joint Venture, Consortium or Association 8](#_Toc6313317)

[15. Only One Proposal 9](#_Toc6313318)

[16. Proposal Validity Period 9](#_Toc6313319)

[17. Extension of Proposal Validity Period 9](#_Toc6313320)

[18. Clarification of Proposal 9](#_Toc6313321)

[19. Amendment of Proposals 9](#_Toc6313322)

[20. Alternative Proposals 10](#_Toc6313323)

[21. Pre-Bid Conference 10](#_Toc6313324)

[C. SUBMISSION AND OPENING OF PROPOSALS 10](#_Toc6313325)

[22. Submission 10](#_Toc6313326)

[23. Deadline for Submission of Proposals and Late Proposals 11](#_Toc6313327)

[24. Withdrawal, Substitution, and Modification of Proposals 11](#_Toc6313328)

[25. Proposal Opening 12](#_Toc6313329)

[D. EVALUATION OF PROPOSALS 12](#_Toc6313330)

[26. Confidentiality 12](#_Toc6313331)

[27. Evaluation of Proposals 12](#_Toc6313332)

[28. Preliminary Examination 12](#_Toc6313333)

[29. Evaluation of Eligibility and Qualification 12](#_Toc6313334)

[30. Evaluation of Technical and Financial Proposals 13](#_Toc6313335)

[31. Due Diligence 13](#_Toc6313336)

[32. Clarification of Proposals 14](#_Toc6313337)

[33. Responsiveness of Proposal 14](#_Toc6313338)

[34. Nonconformities, Reparable Errors and Omissions 14](#_Toc6313339)

[E. AWARD OF CONTRACT 15](#_Toc6313340)

[35. Right to Accept, Reject, Any or All Proposals 15](#_Toc6313341)

[36. Award Criteria 15](#_Toc6313342)

[37. Debriefing 15](#_Toc6313343)

[38. Right to Vary Requirements at the Time of Award 15](#_Toc6313344)

[39. Contract Signature 15](#_Toc6313345)

[40. Contract Type and General Terms and Conditions 15](#_Toc6313346)

[41. Performance Security 15](#_Toc6313347)

[42. Bank Guarantee for Advanced Payment 15](#_Toc6313348)

[43. Liquidated Damages 16](#_Toc6313349)

[44. Payment Provisions 16](#_Toc6313350)

[45. Vendor Protest 16](#_Toc6313351)

[46. Other Provisions 16](#_Toc6313352)

[Section 3. Bid Data Sheet 17](#_Toc6313353)

[Section 4. Evaluation Criteria 20](#_Toc6313354)

[Section 5. Terms of Reference 24](#_Toc6313355)

[Section 6: Returnable Bidding Forms / Checklist 33](#_Toc6313367)

[**Form A:** Technical Proposal Submission Form 34](#_Toc6313368)

[**Form B:** BidderInformation Form 35](#_Toc6313369)

[**Form C:** Joint Venture/Consortium/Association Information Form 36](#_Toc6313370)

[**Form D:** QualificationForm 37](#_Toc6313371)

[**Form E:** Format ofTechnical Proposal 40](#_Toc6313372)

[**Form G:** Financial ProposalForm 43](#_Toc6313373)

# Section 1. Letter of Invitation

The United Nations Development Programme (UNDP) hereby invites you to submit a Proposal to this Request for Proposal (RFP) for the above-referenced subject.

This RFP includes the following documents and the General Terms and Conditions of Contract which is inserted in the Bid Data Sheet (BDS):

 Section 1: This Letter of Invitation

Section 2: Instruction to Bidders

Section 3: Bid Data Sheet (BDS)

Section 4: Evaluation Criteria

Section 5: Terms of Reference

Section 6: Returnable Bidding Forms

* Form A: Technical Proposal Submission Form
* Form B: Bidder Information Form
* Form C: Joint Venture/Consortium/Association Information Form
* Form D: Qualification Form
* Form E: Format of Technical Proposal
* Form F: Financial Proposal Submission Form
* Form G: Financial Proposal Form

If you are interested in submitting a Proposal in response to this RFP, please prepare your Proposal in accordance with the requirements and procedure as set out in this RFP and submit it by the Deadline for Submission of Proposals set out in Bid Data Sheet.

Please acknowledge receipt of this RFP by sending an email to registry.ba@undp.org, indicating whether you intend to submit a Proposal or otherwise. You may also utilize the “Accept Invitation” function in eTendering system, where applicable. This will enable you to receive amendments or updates to the RFP. Should you require further clarifications, kindly communicate with the contact person/s identified in the attached Bid Data Sheet as the focal point for queries on this RFP.

UNDP looks forward to receiving your Proposal and thank you in advance for your interest in UNDP procurement opportunities.

Issued by: Approved by:

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

|  |  |
| --- | --- |
| Name: [insert name of Procurement Officer]Title: [insert title]Date: Select date | Name: [insert name of Procurement Reviewer]Title: [insert title]Date: Select date |

# Section 2. Instruction to Bidders

|  |
| --- |
| GENERAL PROVISIONS |
| Introduction | * 1. Bidders shall adhere to all the requirements of this RFP, including any amendments in writing by UNDP. This RFP is conducted in accordance with the UNDP Programme and Operations Policies and Procedures (POPP) on Contracts and Procurement which can be accessed at <https://popp.undp.org/SitePages/POPPBSUnit.aspx?TermID=254a9f96-b883-476a-8ef8-e81f93a2b38d>
	2. Any Proposal submitted will be regarded as an offer by the Bidder and does not constitute or imply the acceptance of the Proposal by UNDP. UNDP is under no obligation to award a contract to any Bidder as a result of this RFP.
	3. As part of the bid, it is desired that the Bidder registers at the United Nations Global Marketplace (UNGM) website ([www.ungm.org](http://www.ungm.org)). The Bidder may still submit a bid even if not registered with the UNGM. However, if the Bidder is selected for contract award, the Bidder must register on the UNGM prior to contract signature.
 |
| Fraud & Corruption, Gifts and Hospitality | * 1. UNDP strictly enforces a policy of zero tolerance on proscribed practices, including fraud, corruption, collusion, unethical or unprofessional practices, and obstruction of UNDP vendors and requires all bidders/vendors observe the highest standard of ethics during the procurement process and contract implementation. UNDP’s Anti-Fraud Policy can be found at <http://www.undp.org/content/undp/en/home/operations/accountability/audit/office_of_audit_andinvestigation.html#anti>
	2. Bidders/vendors shall not offer gifts or hospitality of any kind to UNDP staff members including recreational trips to sporting or cultural events, theme parks or offers of holidays, transportation, or invitations to extravagant lunches or dinners.
	3. In pursuance of this policy, UNDP(a) Shall reject a proposal if it determines that the selected bidder has engaged in any corrupt or fraudulent practices in competing for the contract in question;(b) Shall declare a vendor ineligible, either indefinitely or for a stated period of time, to be awarded a contract if at any time it determines that the vendor has engaged in any corrupt or fraudulent practices in competing for, or in executing a UNDP contract.
	4. All Bidders must adhere to the UN Supplier Code of Conduct, which may be found at <http://www.un.org/depts/ptd/pdf/conduct_english.pdf>
 |
| Eligibility | * 1. A vendor should not be suspended, debarred, or otherwise identified as ineligible by any UN Organization or the World Bank Group or any other international Organization. Vendors are therefore required to disclose to UNDP whether they are subject to any sanction or temporary suspension imposed by these organizations.
	2. It is the Bidder’s responsibility to ensure that its employees, joint venture members, sub-contractors, service providers, suppliers and/or their employees meet the eligibility requirements as established by UNDP.
 |
| Conflict of Interests | * 1. Bidders must strictly avoid conflicts with other assignments or their own interests, and act without consideration for future work. Bidders found to have a conflict of interest shall be disqualified. Without limitation on the generality of the above, Bidders, and any of their affiliates, shall be considered to have a conflict of interest with one or more parties in this solicitation process, if they:
	2. Are or have been associated in the past, with a firm or any of its affiliates which have been engaged by UNDP to provide services for the preparation of the design, specifications, Terms of Reference, cost analysis/estimation, and other documents to be used for the procurement of the goods and services in this selection process;
	3. Were involved in the preparation and/or design of the programme/project related to the services requested under this RFP; or
	4. Are found to be in conflict for any other reason, as may be established by, or at the discretion of UNDP.
	5. In the event of any uncertainty in the interpretation of a potential conflict of interest, Bidders must disclose to UNDP, and seek UNDP’s confirmation on whether or not such a conflict exists.
	6. Similarly, the Bidders must disclose in their proposal their knowledge of the following:
	7. If the owners, part-owners, officers, directors, controlling shareholders, of the bidding entity or key personnel are family members of UNDP staff involved in the procurement functions and/or the Government of the country or any Implementing Partner receiving services under this RFP; and
	8. All other circumstances that could potentially lead to actual or perceived conflict of interest, collusion or unfair competition practices.

Failure to disclose such an information may result in the rejection of the proposal or proposals affected by the non-disclosure.* 1. The eligibility of Bidders that are wholly or partly owned by the Government shall be subject to UNDP’s further evaluation and review of various factors such as being registered, operated and managed as an independent business entity, the extent of Government ownership/share, receipt of subsidies, mandate and access to information in relation to this RFP, among others. Conditions that may lead to undue advantage against other Bidders may result in the eventual rejection of the Proposal.
 |
| PREPARATION OF PROPOSALS |
| General Considerations | * 1. In preparing the Proposal, the Bidder is expected to examine the RFP in detail. Material deficiencies in providing the information requested in the RFP may result in rejection of the Proposal.
	2. The Bidder will not be permitted to take advantage of any errors or omissions in the RFP. Should such errors or omissions be discovered, the Bidder must notify the UNDP.
 |
| Cost of Preparation of Proposal | * 1. The Bidder shall bear any and all costs related to the preparation and/or submission of the Proposal, regardless of whether its Proposal was selected or not. UNDP shall not be responsible or liable for those costs, regardless of the conduct or outcome of the procurement process.
 |
| Language  | * 1. The Proposal, as well as any and all related correspondence exchanged by the Bidder and UNDP, shall be written in the language (s) specified in the BDS.
 |
| Documents Comprising the Proposal | * 1. The Proposal shall comprise of the following documents:
	2. Documents Establishing the Eligibility and Qualifications of the Bidder;
	3. Technical Proposal;
	4. Financial Proposal;
	5. Proposal Security, if required by BDS;
	6. Any attachments and/or appendices to the Proposal.
 |
| Documents Establishing the Eligibility and Qualifications of the Bidder | * 1. The Bidder shall furnish documentary evidence of its status as an eligible and qualified vendor, using the Forms provided under Section 6 and providing documents required in those forms. In order to award a contract to a Bidder, its qualifications must be documented to UNDP’s satisfaction.
 |
| Technical Proposal Format and Content | * 1. The Bidder is required to submit a Technical Proposal using the Standard Forms and templates provided in Section 6 of the RFP.
	2. The Technical Proposal shall not include any price or financial information. A Technical Proposal containing material financial information may be declared non-responsive.
	3. Samples of items, when required as per Section 5, shall be provided within the time specified and unless otherwise specified by UNDP, and at no expense to UNDP
	4. When applicable and required as per Section 5, the Bidder shall describe the necessary training programme available for the maintenance and operation of the services and/or equipment offered as well as the cost to the UNDP. Unless otherwise specified, such training as well as training materials shall be provided in the language of the Bid as specified in the BDS.
 |
| Financial Proposals | * 1. The Financial Proposal shall be prepared using the Standard Form provided in Section 6 of the RFP. It shall list all major cost components associated with the services, and the detailed breakdown of such costs.
	2. Any output and activities described in the Technical Proposal but not priced in the Financial Proposal, shall be assumed to be included in the prices of other activities or items, as well as in the final total price.
	3. Prices and other financial information must not be disclosed in any other place except in the financial proposal.
 |
| Proposal Security | * 1. A Proposal Security, if required by BDS, shall be provided in the amount and form indicated in the BDS. The Proposal Security shall be valid up to thirty (30) days after the final date of validity of the Proposal.
	2. The Proposal Security shall be included along with the Technical Proposal. If Proposal Security is required by the RFP but is not found along with the Technical Proposal, the Proposal shall be rejected.
	3. If the Proposal Security amount or its validity period is found to be less than what is required by UNDP, UNDP shall reject the Proposal.
	4. In the event an electronic submission is allowed in the BDS, Bidders shall include a copy of the Bid Security in their proposal and the original of the Proposal Security must be sent via courier or hand delivery as per the instructions in BDS.
	5. The Proposal Security may be forfeited by UNDP, and the Proposal rejected, in the event of any one or combination, of the following conditions:
		1. If the Bidder withdraws itsoffer during the period of the Proposal Validity specified in the BDS, or;
		2. In the event that the successful Bidder fails:
		3. to sign the Contract after UNDP has issued an award; or
	6. to furnish the Performance Security, insurances, or other documents that UNDP may require as a condition precedent to the effectivity of the contract that may be awarded to the Bidder.
 |
|  Currencies | * 1. All prices shall be quoted in the currency or currencies indicated in the BDS. Where Proposals are quoted in different currencies, for the purposes of comparison of all Proposals:
1. UNDP will convert the currency quoted in the Proposal into the UNDP preferred currency, in accordance with the prevailing UN operational rate of exchange on the last day of submission of Proposals; and
2. In the event that UNDP selects a proposal for award that is quoted in a currency different from the preferred currency in the BDS, UNDP shall reserve the right to award the contract in the currency of UNDP’s preference, using the conversion method specified above.
 |
|  Joint Venture, Consortium or Association | * 1. If the Bidder is a group of legal entities that will form or have formed a Joint Venture (JV), Consortium or Association for the Proposal, they shall confirm in their Proposal that : (i) they have designated one party to act as a lead entity, duly vested with authority to legally bind the members of the JV, Consortium or Association jointly and severally, which shall be evidenced by a duly notarized Agreement among the legal entities, and submitted with the Proposal; and (ii) if they are awarded the contract, the contract shall be entered into, by and between UNDP and the designated lead entity, who shall be acting for and on behalf of all the member entities comprising the joint venture.
	2. After the Deadline for Submission of Proposal, the lead entity identified to represent the JV, Consortium or Association shall not be altered without the prior written consent of UNDP.
	3. The lead entity and the member entities of the JV, Consortium or Association shall abide by the provisions of Clause 9 herein in respect of submitting only one proposal.
	4. The description of the organization of the JV, Consortium or Association must clearly define the expected role of each of the entity in the joint venture in delivering the requirements of the RFP, both in the Proposal and the JV, Consortium or Association Agreement.  All entities that comprise the JV, Consortium or Association shall be subject to the eligibility and qualification assessment by UNDP.
	5. A JV, Consortium or Association in presenting its track record and experience should clearly differentiate between:
1. Those that were undertaken together by the JV, Consortium or Association; and
2. Those that were undertaken by the individual entities of the JV, Consortium or Association.
	1. Previous contracts completed by individual experts working privately but who are permanently or were temporarily associated with any of the member firms cannot be claimed as the experience of the JV, Consortium or Association or those of its members, but should only be claimed by the individual experts themselves in their presentation of their individual credentials.
	2. JV, Consortium or Associations are encouraged for high value, multi-sectoral requirements when the spectrum of expertise and resources required may not be available within one firm.
 |
| Only One Proposal | * 1. The Bidder (including the individual members of any Joint Venture) shall submit only one Proposal, either in its own name or as part of a Joint Venture.
	2. Proposals submitted by two (2) or more Bidders shall all be rejected if they are found to have any of the following:
	3. they have at least one controlling partner, director or shareholder in common; or
	4. any one of them receive or have received any direct or indirect subsidy from the other/s; or
	5. they have the same legal representative for purposes of this RFP; or
	6. they have a relationship with each other, directly or through common third parties, that puts them in a position to have access to information about, or influence on the Proposal of, another Bidder regarding this RFP process;
	7. they are subcontractors to each other’s Proposal, or a subcontractor to one Proposal also submits another Proposal under its name as lead Bidder; or
	8. some key personnel proposed to be in the team of one Bidder participates in more than one Proposal received for this RFP process. This condition relating to the personnel, does not apply to subcontractors being included in more than one Proposal.
 |
| Proposal Validity Period | * 1. Proposals shall remain valid for the period specified in the BDS, commencing on the Deadline for Submission of Proposals. A Proposal valid for a shorter period may be rejected by UNDP and rendered non-responsive.
	2. During the Proposal validity period, the Bidder shall maintain its original Proposal without any change, including the availability of the Key Personnel, the proposed rates and the total price.
 |
| Extension of Proposal Validity Period | * 1. In exceptional circumstances, prior to the expiration of the proposal validity period, UNDP may request Bidders to extend the period of validity of their Proposals. The request and the responses shall be made in writing, and shall be considered integral to the Proposal.
	2. If the Bidder agrees to extend the validity of its Proposal, it shall be done without any change in the original Proposal.
	3. The Bidder has the right to refuse to extend the validity of its Proposal, and in which case, such Proposal will not be further evaluated.
 |
| Clarification of Proposal | * 1. Bidders may request clarifications on any of the RFP documents no later than the date indicated in the BDS. Any request for clarification must be sent in writing in the manner indicated in the BDS. If inquiries are sent other than specified channel, even if they are sent to a UNDP staff member, UNDP shall have no obligation to respond or confirm that the query was officially received.
	2. UNDP will provide the responses to clarifications through the method specified in the BDS.
	3. UNDP shall endeavor to provide responses to clarifications in an expeditious manner, but any delay in such response shall not cause an obligation on the part of UNDP to extend the submission date of the Proposals, unless UNDP deems that such an extension is justified and necessary.
 |
| Amendment of Proposals | * 1. At any time prior to the deadline of Proposal submission, UNDP may for any reason, such as in response to a clarification requested by a Bidder, modify the RFP in the form of an amendment to the RFP. Amendments will be made available to all prospective bidders.
	2. If the amendment is substantial, UNDP may extend the Deadline for submission of proposal to give the Bidders reasonable time to incorporate the amendment into their Proposals.
 |
| Alternative Proposals | * 1. Unless otherwise specified in the BDS, alternative proposals shall not be considered. If submission of alternative proposal is allowed by BDS, a Bidder may submit an alternative proposal, but only if it also submits a proposal conforming to the RFP requirements. UNDP shall only consider the alternative proposal offered by the Bidder whose conforming proposal ranked the highest as per the specified evaluation method. Where the conditions for its acceptance are met, or justifications are clearly established, UNDP reserves the right to award a contract based on an alternative proposal.
	2. If multiple/alternative proposals are being submitted, they must be clearly marked as “Main Proposal” and “Alternative Proposal”
 |
| Pre-Bid Conference | * 1. When appropriate, a Bidder’s conference will be conducted at the date, time and location specified in the BDS. All Bidders are encouraged to attend. Non-attendance, however, shall not result in disqualification of an interested Bidder. Minutes of the Bidder’s conference will be disseminated on the procurement website and shared by email or on the e-Tendering platform as specified in the BDS. No verbal statement made during the conference shall modify the terms and conditions of the RFP, unless specifically incorporated in the Minutes of the Bidder’s Conference or issued/posted as an amendment to RFP.
 |
| SUBMISSION AND OPENING OF PROPOSALS |
| Submission  | * 1. The Bidder shall submit a duly signed and complete Proposal comprising the documents and forms in accordance with the requirements in the BDS. The submission shall be in the manner specified in the BDS.
	2. The Proposal shall be signed by the Bidder or person(s) duly authorized to commit the Bidder. The authorization shall be communicated through a document evidencing such authorization issued by the legal representative of the bidding entity, or a Power of Attorney, accompanying the Proposal.
	3. Bidders must be aware that the mere act of submission of a Proposal, in and of itself, implies that the Bidder fully accepts the UNDP General Contract Terms and Conditions.
 |
| **Hard copy (manual) submission** **Email Submission****eTendering submission** | * 1. Hard copy (manual) submission by courier or hand delivery allowed or specified in the BDS shall be governed as follows:
	2. The signed Proposal shall be marked “Original”, and its copies marked “Copy” as appropriate. The number of copies is indicated in the BDS. All copies shall be made from the signed original only. If there are discrepancies between the original and the copies, the original shall prevail.
	3. The Technical Proposal and the Financial Proposal envelopes MUST BE COMPLETELY SEPARATE and each of them must be submitted sealed individually and clearly marked on the outside as either “TECHNICAL PROPOSAL” or “FINANCIAL PROPOSAL”, as appropriate. Each envelope SHALL clearly indicate the name of the Bidder. The outer envelopes shall:

i. Bear the name and address of the bidder;ii. Be addressed to UNDP as specified in the BDS1. Bear a warning that states “*Not to be opened before the time and date for proposal opening*” as specified in the BDS.

If the envelopes and packages with the Proposal are not sealed and marked as required, UNDP shall assume no responsibility for the misplacement, loss, or premature opening of the Proposal.* 1. Email submission, if allowed or specified in the BDS, shall be governed as follows:
1. Electronic files that form part of the proposal must be in accordance with the format and requirements indicated in BDS;
2. The Technical Proposal and the Financial Proposal files MUST BE COMPLETELY SEPARATE. The financial proposal shall be encrypted with different passwords and clearly labelled. The files must be sent to the dedicated email address specified in the BDS.
3. The password for opening the Financial Proposal should be provided only upon request of UNDP. UNDP will request password only from bidders whose Technical Proposal has been found to be technically responsive. Failure to provide correct password may result in the proposal being rejected.
	1. Electronic submission through eTendering, if allowed or specified in the BDS, shall be governed as follows:
4. Electronic files that form part of the proposal must be in accordance with the format and requirements indicated in BDS;
5. The Technical Proposal and the Financial Proposal files MUST BE COMPLETELY SEPARATE and each of them must be uploaded individually and clearly labelled.
6. The Financial Proposal file must be encrypted with a password so that it cannot be opened nor viewed until the password is provided. The password for opening the Financial Proposal should be provided only upon request of UNDP. UNDP will request password only from bidders whose technical proposal has been found to be technically responsive. Failure to provide the correct password may result in the proposal being rejected.
7. Documents which are required to be in original form (e.g. Bid Security, etc.) must be sent via courier or hand delivery as per the instructions in BDS.
8. Detailed instructions on how to submit, modify or cancel a bid in the eTendering system are provided in the eTendering system Bidder User Guide and Instructional videos available on this link: <http://www.undp.org/content/undp/en/home/operations/procurement/business/procurement-notices/resources/>
 |
| Deadline for Submission of Proposals and Late Proposals | * 1. Complete Proposals must be received by UNDP in the manner, and no later than the date and time, specified in the BDS. UNDP shall only recognize the date and time that the bid was received by UNDP
	2. UNDP shall not consider any Proposal that is submitted after the deadline for the submission of Proposals.
 |
| Withdrawal, Substitution, and Modification of Proposals | * 1. A Bidder may withdraw, substitute or modify its Proposal after it has been submitted at any time prior to the deadline for submission.
	2. Manual and Email submissions: A bidder may withdraw, substitute or modify its Proposal by sending a written notice to UNDP, duly signed by an authorized representative, and shall include a copy of the authorization (or a Power of Attorney). The corresponding substitution or modification of the Proposal, if any, must accompany the respective written notice. All notices must be submitted in the same manner as specified for submission of proposals, by clearly marking them as “WITHDRAWAL” “SUBSTITUTION,” or “MODIFICATION”
	3. eTendering: A Bidder may withdraw, substitute or modify its Proposal by Canceling, Editing, and re-submitting the proposal directly in the system. It is the responsibility of the Bidder to properly follow the system instructions, duly edit and submit a substitution or modification of the Proposal as needed. Detailed instructions on how to cancel or modify a Proposal directly in the system are provided in Bidder User Guide and Instructional videos.
	4. Proposals requested to be withdrawn shall be returned unopened to the Bidders (only for manual submissions), except if the bid is withdrawn after the bid has been opened
 |
| Proposal Opening  | * 1. There is no public bid opening for RFPs. UNDP shall open the Proposals in the presence of an ad-hoc committee formed by UNDP, consisting of at least two (2) members. In the case of e-Tendering submission, bidders will receive an automatic notification once their proposal is opened.
 |
| EVALUATION OF PROPOSALS |
| Confidentiality | * 1. Information relating to the examination, evaluation, and comparison of Proposals, and the recommendation of contract award, shall not be disclosed to Bidders or any other persons not officially concerned with such process, even after publication of the contract award.
	2. Any effort by a Bidder or anyone on behalf of the Bidder to influence UNDP in the examination, evaluation and comparison of the Proposals or contract award decisions may, at UNDP’s decision, result in the rejection of its Proposal and may be subject to the application of prevailing UNDP’s vendor sanctions procedures.
 |
| Evaluation of Proposals | * 1. The Bidder is not permitted to alter or modify its Proposal in any way after the proposal submission deadline except as permitted under Clause 24 of this RFP. UNDP will conduct the evaluation solely on the basis of the submitted Technical and Financial Proposals.
	2. Evaluation of proposals is made of the following steps:
	3. Preliminary Examination
	4. Minimum Eligibility and Qualification (if pre-qualification is not done)
	5. Evaluation of Technical Proposals
	6. Evaluation of Financial Proposals
 |
| Preliminary Examination  | * 1. UNDP shall examine the Proposals to determine whether they are complete with respect to minimum documentary requirements, whether the documents have been properly signed, and whether the Proposals are generally in order, among other indicators that may be used at this stage. UNDP reserves the right to reject any Proposal at this stage.
 |
| Evaluation of Eligibility and Qualification | * 1. Eligibility and Qualification of the Bidder will be evaluated against the Minimum Eligibility/Qualification requirements specified in the Section 4 (Evaluation Criteria).
	2. In general terms, vendors that meet the following criteria may be considered qualified:
	3. They are not included in the UN Security Council 1267/1989 Committee's list of terrorists and terrorist financiers, and in UNDP’s ineligible vendors’ list;
	4. They have a good financial standing and have access to adequate financial resources to perform the contract and all existing commercial commitments,
	5. They have the necessary similar experience, technical expertise, production capacity where applicable, quality certifications, quality assurance procedures and other resources applicable to the provision of the services required;
	6. They are able to comply fully with UNDP General Terms and Conditions of Contract;
	7. They do not have a consistent history of court/arbitral award decisions against the Bidder; and
	8. They have a record of timely and satisfactory performance with their clients.
 |
| Evaluation of Technical and Financial Proposals | * 1. The evaluation team shall review and evaluate the Technical Proposals on the basis of their responsiveness to the Terms of Reference and other RFP documents, applying the evaluation criteria, sub-criteria, and point system specified in the Section 4 (Evaluation Criteria). A Proposal shall be rendered non-responsive at the technical evaluation stage if it fails to achieve the minimum technical score indicated in the BDS. When necessary and if stated in the BDS, UNDP may invite technically responsive bidders for a presentation related to their technical proposals. The conditions for the presentation shall be provided in the bid document where required.
	2. In the second stage, only the Financial Proposals of those Bidders who achieve the minimum technical score will be opened for evaluation. The Financial Proposals corresponding to Technical Proposals that were rendered non-responsive shall remain unopened, and, in the case of manual submission, be returned to the Bidder unopened. For emailed Proposals and e-tendering submissions, UNDP will not request for the password of the Financial Proposals of bidders whose Technical Proposal were found not responsive.
	3. The evaluation method that applies for this RFP shall be as indicated in the BDS, which may be either of two (2) possible methods, as follows: (a) the lowest priced method which selects the lowest evaluated financial proposal of the technically responsive Bidders; or (b) the combined scoring method which will be based on a combination of the technical and financial score.
	4. When the BDS specifies a combined scoring method, the formula for the rating of the Proposals will be as follows:

Rating the Technical Proposal (TP): **TP Rating** = (Total Score Obtained by the Offer / Max. Obtainable Score for TP) x 100 Rating the Financial Proposal (FP): **FP Rating** = (Lowest Priced Offer / Price of the Offer Being Reviewed) x 100Total Combined Score:**Combined Score =** (TP Rating) x (Weight of TP, e.g. 70%) + (FP Rating) x (Weight of FP, e.g., 30%) |
|  Due Diligence | * 1. UNDP reserves the right to undertake a due diligence exercise, also called post qualification, aimed at determining to its satisfaction, the validity of the information provided by the Bidder. Such exercise shall be fully documented and may include, but need not be limited to, all or any combination of the following:
		1. Verification of accuracy, correctness and authenticity of information provided by the Bidder;
		2. Validation of extent of compliance to the RFP requirements and evaluation criteria based on what has so far been found by the evaluation team;
		3. Inquiry and reference checking with Government entities with jurisdiction on the Bidder, or with previous clients, or any other entity that may have done business with the Bidder;
		4. Inquiry and reference checking with previous clients on the performance on on-going or contracts completed, including physical inspections of previous works, as necessary;
		5. Physical inspection of the Bidder’s offices, branches or other places where business transpires, with or without notice to the Bidder;
		6. Other means that UNDP may deem appropriate, at any stage within the selection process, prior to awarding the contract.
 |
| Clarification of Proposals | * 1. To assist in the examination, evaluation and comparison of Proposals, UNDP may, at its discretion, ask any Bidder for a clarification of its Proposal.
	2. UNDP’s request for clarification and the response shall be in writing and no change in the prices or substance of the Proposal shall be sought, offered, or permitted, except to provide clarification, and confirm the correction of any arithmetic errors discovered by UNDP in the evaluation of the Proposals, in accordance with RFP.
	3. Any unsolicited clarification submitted by a Bidder in respect to its Proposal, which is not a response to a request by UNDP, shall not be considered during the review and evaluation of the Proposals.
 |
| Responsiveness of Proposal | * 1. UNDP’s determination of a Proposal’s responsiveness will be based on the contents of the Proposal itself. A substantially responsive Proposal is one that conforms to all the terms, conditions, TOR and other requirements of the RFP without material deviation, reservation, or omission.
	2. If a Proposal is not substantially responsive, it shall be rejected by UNDP and may not subsequently be made responsive by the Bidder by correction of the material deviation, reservation, or omission.
 |
| Nonconformities, Reparable Errors and Omissions | * 1. Provided that a Proposal is substantially responsive, UNDP may waive any non-conformities or omissions in the Proposal that, in the opinion of UNDP, do not constitute a material deviation.
	2. UNDP may request the Bidder to submit the necessary information or documentation, within a reasonable period of time, to rectify nonmaterial nonconformities or omissions in the Proposal related to documentation requirements. Such omission shall not be related to any aspect of the price of the Proposal. Failure of the Bidder to comply with the request may result in the rejection of its Proposal.
	3. For Financial Proposal that has been opened, UNDP shall check and correct arithmetical errors as follows:
1. if there is a discrepancy between the unit price and the line item total that is obtained by multiplying the unit price by the quantity, the unit price shall prevail and the line item total shall be corrected, unless in the opinion of UNDP there is an obvious misplacement of the decimal point in the unit price; in which case the line item total as quoted shall govern and the unit price shall be corrected;
2. if there is an error in a total corresponding to the addition or subtraction of subtotals, the subtotals shall prevail and the total shall be corrected; and
3. if there is a discrepancy between words and figures, the amount in words shall prevail, unless the amount expressed in words is related to an arithmetic error, in which case the amount in figures shall prevail.
	1. If the Bidder does not accept the correction of errors made by UNDP, its Proposal shall be rejected.
 |
| AWARD OF CONTRACT |
| Right to Accept, Reject, Any or All Proposals | * 1. UNDP reserves the right to accept or reject any Proposal, to render any or all of the Proposals as non-responsive, and to reject all Proposals at any time prior to award of contract, without incurring any liability, or obligation to inform the affected Bidder(s) of the grounds for UNDP’s action. UNDP shall not be obliged to award the contract to the lowest priced offer.
 |
| Award Criteria | * 1. Prior to expiration of the proposal validity, UNDP shall award the contract to the qualified Bidder based on the award criteria indicated in the BDS.
 |
| Debriefing | * 1. In the event that a Bidder is unsuccessful, the Bidder may request a debriefing from UNDP. The purpose of the debriefing is to discuss the strengths and weaknesses of the Bidder’s submission, in order to assist the Bidder in improving its future proposals for UNDP procurement opportunities. The content of other proposals and how they compare to the Bidder’s submission shall not be discussed.
 |
| Right to Vary Requirements at the Time of Award | * 1. At the time of award of Contract, UNDP reserves the right to vary the quantity of services and/or goods, by up to a maximum twenty-five per cent (25%) of the total offer, without any change in the unit price or other terms and conditions.
 |
| Contract Signature | * 1. Within fifteen (15) days from the date of receipt of the Contract, the successful Bidder shall sign and date the Contract and return it to UNDP. Failure to do so may constitute sufficient grounds for the annulment of the award, and forfeiture of the Proposal Security, if any, and on which event, UNDP may award the Contract to the Second Ranked Bidder or call for new Proposals.
 |
| Contract Type and General Terms and Conditions  | * 1. The types of Contract to be signed and the applicable UNDP Contract General Terms and Conditions, as specified in BDS, can be accessed at <http://www.undp.org/content/undp/en/home/procurement/business/how-we-buy.html>
 |
| Performance Security | * 1. 40.1 A performance security, if required in BDS, shall be provided in the amount specified in BDS and form available at

<https://popp.undp.org/_layouts/15/WopiFrame.aspx?sourcedoc=/UNDP_POPP_DOCUMENT_LIBRARY/Public/PSU_Solicitation_Performance%20Guarantee%20Form.docx&action=default> within fifteen (15) days of the contract signature by both parties. Where a performance security is required, the receipt of the performance security by UNDP shall be a condition for rendering the contract effective. |
| Bank Guarantee for Advanced Payment | * 1. Except when the interests of UNDP so require, it is UNDP’s preference to make no advance payment(s) (i.e., payments without having received any outputs). If an advance payment is allowed as per BDS, and exceeds 20% of the total contract price, or USD 30,000, whichever is less, the Bidder shall submit a Bank Guarantee in the full amount of the advance payment in the form available at <https://popp.undp.org/_layouts/15/WopiFrame.aspx?sourcedoc=/UNDP_POPP_DOCUMENT_LIBRARY/Public/PSU_Contract%20Management%20Payment%20and%20Taxes_Advanced%20Payment%20Guarantee%20Form.docx&action=default>
 |
| Liquidated Damages | * 1. If specified in BDS, UNDP shall apply Liquidated Damages resulting from the Contractor’s delays or breach of its obligations as per the Contract.
 |
| Payment Provisions | * 1. Payment will be made only upon UNDP's acceptance of the work performed. The terms of payment shall be within thirty (30) days, after receipt of invoice and certification of acceptance of work issued by the proper authority in UNDP with direct supervision of the Contractor. Payment will be effected by bank transfer in the currency of contract.
 |
| Vendor Protest | * 1. UNDP’s vendor protest procedure provides an opportunity for appeal to those persons or firms not awarded a contract through a competitive procurement process. In the event that a Bidder believes that it was not treated fairly, the following link provides further details regarding UNDP vendor protest procedures: <http://www.undp.org/content/undp/en/home/operations/procurement/business/protest-and-sanctions.html>
 |
| Other Provisions | * 1. In the event that the Bidder offers a lower price to the host Government (e.g. General Services Administration (GSA) of the federal government of the United States of America) for similar services, UNDP shall be entitled to same lower price. The UNDP General Terms and Conditions shall have precedence.
	2. UNDP is entitled to receive the same pricing offered by the same Contractor in contracts with the United Nations and/or its Agencies. The UNDP General Terms and Conditions shall have precedence.
	3. The United Nations has established restrictions on employment of (former) UN staff who have been involved in the procurement process as per bulletin ST/SGB/2006/15 <http://www.un.org/en/ga/search/view_doc.asp?symbol=ST/SGB/2006/15&referer>
 |

# Section 3. Bid Data Sheet

The following data for the services to be procured shall complement, supplement, or amend the provisions in the Request for Proposals. In the case of a conflict between the Instructions to Bidders, the Data Sheet, and other annexes or references attached to the Data Sheet, the provisions in the Data Sheet shall prevail**.**

|  |  |  |  |
| --- | --- | --- | --- |
| **BDS No.** | **Ref. to Section.2** | **Data** | **Specific Instructions / Requirements** |
| 1 | 7 | Language of the Proposal  | English |
| 2 |  | Submitting Proposals for Parts or sub-parts of the TOR (partial bids) | Not Allowed |
| 3 | 20 | Alternative Proposals  | Shall not be considered |
| 4 | 21 | Pre-proposal conference  | Will not be conducted |
| 5 | 10 | Proposal Validity Period | 90 days |
| 6 | 14 | Bid Security  | Not Required |
| 7 | 41 | Advanced Payment upon signing of contract  | Not Allowed |
| 8 | 42 | Liquidated Damages | Will not be imposed |
| 9 | 40 | Performance Security | Not Required |
| 10 | 18 | Currency of Proposal  | Local currency BAM |
| 11 | 31 | Deadline for submitting requests for clarifications/ questions | 10 days before the submission deadline |
| 12 | 31 | Contact Details for submitting clarifications/questions  | Focal Person in UNDP: UNDP BiH, General ServicesAddress: Zmaja od Bosne bb, 71000 Sarajevo, Bosnia and Herzegovina E-mail address: registry.ba@undp.org  |
| 13 | 18, 19 and 21 | Manner of Disseminating Supplemental Information to the RFP and responses/clarifications to queries | Direct communication to prospective Proposers by email |
| 14 | 23 | Deadline for Submission  | 30 May 2019, 17:00 hrs, CET |
| 15 | 22 | Allowable Manner of Submitting Proposals | 🗵 Courier/Hand Delivery |
| 16 | 22 | Proposal Submission Address  | Zmaja od Bosne bb71 000 SarajevoBosnia and Herzegovina |
| 17 | 22 | Electronic submission (email or eTendering) requirements | N/A |
| 18 | 2736 | Evaluation Method for the Award of Contract | Combined Scoring Method, using the 70%-30% distribution for technical and financial proposals respectively The minimum technical score required to pass is 70%. |
| 19 |  | Expected date for commencement of Contract | *July 1, 2019* |
| 20 |  | Maximum expected duration of contract  | 4 months |
| 21 | 35 | UNDP will award the contract to: | One Proposer Only |
| 22 | 39 | Type of Contract  | Contract for Goods and Services on behalf of UN Entities<http://www.undp.org/content/undp/en/home/procurement/business/how-we-buy.html> |
| 23 | 39 | UNDP Contract Terms and Conditions that will apply | UNDP General Terms and Conditions for Professional Services<http://www.undp.org/content/undp/en/home/procurement/business/how-we-buy.html> |
| 24 |  | Other Information Related to the RFP | *All pages should be numbered* |

# Section 4. Evaluation Criteria

**Preliminary Examination Criteria**

Proposals will be examined to determine whether they are complete and submitted in accordance with RFP requirements as per below criteria on a Yes/No basis:

* Appropriate signatures
* Power of Attorney
* Minimum documents provided
* Technical and Financial Proposals submitted separately
* Bid Validity
* Bid Security submitted as per RFP requirements with compliant validity period

**Minimum Eligibility and Qualification Criteria**

Eligibility and Qualification will be evaluated on Pass/Fail basis.

If the Proposal is submitted as a Joint Venture/Consortium/Association, each member should meet minimum criteria, unless otherwise specified in the criterion.

|  |  |  |
| --- | --- | --- |
| **Subject** | **Criteria** | **Document Submission requirement** |
| **ELIGIBILITY**  |  |  |
| **Legal Status** | Vendor is a legally registered entity. | Form B: Bidder Information Form  |
| **Eligibility** | Vendor is not suspended, nor debarred, nor otherwise identified as ineligible by any UN Organization or the World Bank Group or any other international Organization in accordance with RFP clause 3.  | Form A: Technical Proposal Submission Form |
| **Conflict of Interest** | No conflicts of interest in accordance with RFP clause 4.  | Form A: Technical Proposal Submission Form |
| **Bankruptcy** | Not declared bankruptcy, not involved in bankruptcy or receivership proceedings, and there is no judgment or pending legal action against the vendor that could impair its operations in the foreseeable future. | Form A: Technical Proposal Submission Form |
|  |  |  |
| **QUALIFICATION** |  |  |
| **History of Non-Performing Contracts[[1]](#footnote-2)**  | Non-performance of a contract did not occur as a result of contractor default for the last 3 years. | Form D: Qualification Form |
| **Litigation History** | No consistent history of court/arbitral award decisions against the Bidder for the last 3 years.  | Form D: Qualification Form |
| **Previous Experience** | Minimum 5 years of relevant experience. | Form D: Qualification Form |
| Minimum 5 contracts of similar value, nature and complexity implemented over the last 5 years. *(For JV/Consortium/Association, all Parties cumulatively should meet requirement).* | Form D: Qualification Form |
| At least 2 contracts/assignments related to communication services and/or promotion in the last 3 years.*(For JV/Consortium/Association, all Parties cumulatively should meet requirement).* | Form D: Qualification Form |
| **Financial Standing** | Minimum average annual turnover of BAM 100,000.00 for the last 3 years.*(For JV/Consortium/Association, all Parties cumulatively should meet requirement).* | Form D: Qualification Form |
| Bidder must demonstrate the current soundness of its financial standing and indicate its prospective long-term profitability. *(For JV/Consortium/Association, all Parties cumulatively should meet requirement).* | Form D: Qualification Form |

**Technical Evaluation Criteria**

|  |  |
| --- | --- |
| **Summary of Technical Proposal Evaluation Forms** | **Points Obtainable** |
| 1. | Bidder’s qualification, capacity and experience  | 200 |
| 2. | Proposed Methodology, Approach and Implementation Plan | 400 |
| 3. | Management Structure and Key Personnel | 400 |
|  | **Total** | **1000** |

|  |  |
| --- | --- |
| **Section 1. Bidder’s qualification, capacity and experience** | **Points obtainable** |
| 1.1 | Reputation of Organization and Staff Credibility / Reliability / Industry Standing  | 30 |
| 1.2 | General Organizational Capability which is likely to affect implementation: management structure, financial stability and project financing capacity, project management controls, extent to which any work would be subcontracted | 70 |
| 1.3 | Relevance of specialized knowledge and experience on similar engagements done in the region/country | 60 |
| 1.4 | Quality assurance procedures and risk mitigation measures | 40 |
| **Total Section 1** | **200** |

|  |  |
| --- | --- |
| **Section 2. Proposed Methodology, Approach and Implementation Plan** | **Points obtainable** |
| 2.1 | Understanding of the requirement: Have the important aspects of the task been addressed in sufficient detail? Are the different components of the project adequately weighted relative to one another? | 60 |
| 2.2 | Description of the Offeror’s approach and methodology for meeting or exceeding the requirements of the Terms of Reference | 130 |
| 2.3 | Details on how the different service elements shall be organized, controlled and delivered  | 80 |
| 2.4 | Identification and analysis of risks and mitigation measures | 50 |
| 2.5 | Assessment of the implementation plan proposed including whether the activities are properly sequenced and if these are logical and realistic | 50 |
| 2.6 | Demonstration of ability to plan, integrate and effectively implement sustainability measures in the execution of the contract  | 30 |
|  |  |  |
| **Total Section** **2** | **400** |

|  |  |
| --- | --- |
| **Section 3. Management Structure and Key Personnel** | **Points obtainable** |
| 3.1 | Composition and structure of the team proposed. Are the proposed roles of the management and the team of key personnel suitable for the provision of the necessary services? |  | 70 |
| 3.2 | Qualifications of key personnel proposed (at least 7 experts) |  |  |
| 3.2a | Account Manager  |  | 70 |
|  | General Experience | 30 |  |
| Specific Experience relevant to the assignment  | 40 |
| 3.2b | Senior Communications Expert |  | 50 |
|  | General Experience | 20 |  |
|  | Specific Experience relevant to the assignment | 30 |  |
| 3.2c | Copywriter |  | 60 |
|  | General Experience | 30 |  |
|  | Specific Experience relevant to the assignment | 30 |  |
| 3.2d | Journalist |  | 30 |
|  | General Experience | 10 |  |
|  | Specific Experience relevant to the assignment | 20 |  |
| 3.2e | Videographer |  | 50 |
|  | General Experience | 25 |  |
|  | Specific Experience relevant to the assignment | 25 |  |
| 3.2f | Event Manager |  | 30 |
|  | General Experience | 10 |  |
|  | Specific Experience relevant to the assignment | 20 |  |
| 3.2g | Photojournalist |  | 40 |
|  | General Experience | 20 |  |
| Specific Experience relevant to the assignment | 20 |
| **Total Section 3**  | **400** |

# Section 5. Terms of Reference

**Title:** Communication services for design and promotion of MZ Project results (2015-2019)

**Reporting to:** UNDP MZ Project Manager

**Contract Type:** Contract for Goods and Services on behalf of UN Entities

**Duration:** 4 Months (tentative start early July 2019)

**I. Background information**

In 2015, UNDP launched the implementation of the Strengthening the Role of Local Communities/*Mjesne zajednice* in Bosnia and Herzegovina Project, which is financed jointly by the Government of Switzerland and the Government of Sweden. The project goal is to improve quality of life of the citizens of Bosnia and Herzegovina (B&H) through improving local infrastructure and services, increasing democratic accountability and social inclusion. The chosen means to achieve this goal is through encouraging community-led local development and revitalising of *mjesne zajednice* (MZs) as the places where government comes closest to the people and as grass-roots organisations that serve communities, with the possibility for real participation and joint action.

The Project's implementing strategy is to support and drive forward change from bottom-up by engaging citizens and communities and giving them a voice in local governance processes, and by revitalising MZs as spaces where citizens come together to interact and involve, to identify and solve problems, to transmit their concerns to the local government and participate in the ways it makes its plans, spends their money and takes decisions that affect people’s lives. In doing so, the Project places MZs and their communities at the centre of its work, while also relying on a broad range of relevant stakeholders to sustain and expand Project results and increase democratic accountability. The Project works with 24 LGs and 136 MZs country-wide. The key Project stakeholders are the following LGs: Banja Luka, Bijeljina, Brčko distrikt, Gračanica, Gradačac, Gradiška, Ilijaš, Jablanica, Ključ, Kotor Varoš, Laktaši, Ljubinje, Ljubuški, Nevesinje, Olovo, Pale FBiH, Petrovo, Rudo, Sanski Most, Stari Grad Sarajevo, Tešanj, Visoko, Zenica, Žepče, as well as their respective local communities that are part of the project.

**II. Project specific outline**

The purpose of this Request for Proposal is to engage the Service Provider to support the MZ Project to review and capture, in a user friendly, non-technical manner, human-interest stories and initiatives implemented by the MZ Project within the period 2015-2019.

With this Request for Proposal the MZ Project aim to portray stories of everyday activists supported by the project, those campaigning for improvement of their communities, more egalitarian, gender sensitive approaches – with the aim to challenge the *status quo* and catalyse various kinds of social change.

The purpose of this assigment is to demonstrate and promote to citizens the spirit and main idea behind strengthening local communities (MZs) in BiH for civic participation, engagement and collaboration to convey the highlights of the stories and snapshots of up-to-date Project achievements. Therefore, the focus will be on people-centred stories in the field in 24 Local Self-Governments in BiH.

**III. Assignment objective**

The objective of this assignment is to provide communications support in line with defined Scope of Work. The envisioned support has a strong human-interest aspects – captured throughout all planned communications materials and videos.

**IV. Scope of Work**

The following section will define expected communications products and results. Prior to the start of activities, the Service Provider will prepare and submit for approval a detailed description and workplan for the implementation of the assignment.

**Task 1. VIDEO PRODUCTION**

The selected Service Provider will produce up to **10 short videos** (covering locations: 24 partner LGs), up to one (1) minute in length each for external communications through social media and online portals. Short stories will be filmed within BiH (the project team will define exact locations together with the selected service provider depending on the final themes selected). Additionally, the Service Provider will produce one longer video up to three (3) minutes long, capturing overall project results.

• Develop a pre-production, production and post-production phase plan, including story scenarios,

• Subtitles in English,

• Field visit with filming crew,

• Video to be produced in HD format (MP4 for YouTube and website faster and easier upload),

• Video should have some graphic and animation elements,

• Video should use new video footage,

• Statements from key personnel, etc.,

• Content should be short and punchy.

**Task 2. COMMUNICATIONS/COPYWRITING/DESIGN SERVICES - 50 MZ STORIES DIGITAL/ONLINE CATALOGUE**

In the scope of this task, the Service Provider will engage a wide array of stakeholders identified by the Project into collaborative process for development of **Catalogue of stories**: photo, text and/or video in the digital format with the option for printing the catalogue, including high resulation photographs captured by a Photojournalist. The Catalogue online and print should be in BHS and ENG language.

While selecting stories, care will be taken to ensure adequate geographic and urban/rural coverage, full parity in terms of gender representation, adequate angle on empowerment of women, as well as adequate reflection on social inclusion matters.

Create and design **Short booklet or sketchbook**, showing through illustrations project processes, defined by the team – illustrating three working processes with local communities, civil society organizations and community hubs.

Prepare up to five **photo stories** using existing or new online platform, such as Exposure, for photo story or suggested by the Service Provider.

**Task 3. PR AND EVENT MANAGEMENT**

The selected Service Provider will provide technical support and PR management for the organization and implementation of maximum 30 promo mini-events through BiH (including partner LGs, community hubs, and other locations countrywide mutually agreed with MZ team) with the aim to present MZ project results.

PR management and support will entail:

##### Defining the format of the events and topics, identification of participants and preparation of relevant materials;

##### Event management;

##### Contacting local media in BiH, partner local communities, partnership with local radio stations and ensuring media presence;

##### Coordinating media appearances, as appropriate;

##### Providing media clipping after each event.

Service Provider is expected to consider all aspects related to organization, logistics and management of proposed events. We strongly encourage you to engage relevant stakeholders in the matter, liaise with national and entity level media outlets, but also use existing facilities such as community hubs.

All material prepared for the organization of the events will have to be submitted for approval to UNDP.

**Task 4. ONLINE AND SOCIAL MEDIA PROMOTION**

* Plan and conduct advertising for .30 or .60 sec YouTube videos on social media, with a minimum of 30000 views for the duration of this assignment, duration 15 days.
* Online portals: Arrange and conduct PR visibility online banners (leader board and/or wallpaper) and rotating banner on the four most visited and most influential online portals in BiH such as klix.ba, avaz.ba, nezavisne.com, bljesak.info. Banners with a minimum dimension 960 x 250 with additional proposition of innovative format, such as in text video. The Service Provider will create and produce visuals for the banners and interactive banners and suggest optimal number of impressions for the duration of the assignment, according to the approved timeline.

The Service Provider is due to carry out this assignments from the date of signing the contract up to the October 2019.

**V. Deliverables and Schedules/Expected Outputs**

The following outputs and deliverables are expected upon completion of the service:

|  **Deliverables** | **Indicative level of efforts** **(in consultancy days)** | **Deadline** |
| --- | --- | --- |
| VIDEO PRODUCTION: * Production of 11 HD videos (up to 10 short+1 long) with English subtitles.
 | 40 | July 2019 |
| COMMUNICATIONS/COPYWRITING/DESIGN SERVICES:* Preparation of 50 MZ stories digital/online Catalogue.
* Design of short booklet/sketchbook.
* Produce up to 5 photo stories.
 | 100 | July – August 2019 |
| PR AND EVENT MANAGEMENT:* Management and implementation of maximum 30 promo mini-events through BiH.
 | 100 | August – September 2019  |
| ONLINE AND SOCIAL MEDIA PROMOTION:* Planning and conducting advertising of YouTube videos on social media.
* Arrangement and conduction of PR visibility online banners.
 | 40 | October 2019 |

All key activities and deliverables will be subject to review by the UNDP MZ Project Manager and MZ Project Team. In order to proceed on the next phase, previous activity must be approved by above-mentioned subjects. After receiving written approval, the Service Provider will continue with following activities.

**VI. Governance and Accountability**

The UNDP will closely oversee the service provision and work in close cooperation and coordination with the service provider. Day to day management of the service will be devolved to the Service Provider. A strong performance regime will operate – with payments made to the service provider on an outputs basis.

Reporting is considered as the formal presentation of monitoring information and is related to service delivery under these ToRs. The service provider is expected to provide report for approval by UNDP MZ Project management. Within this assignment, the Service Provider will be obliged to submit the following reports:

• Stage reports

Upon completion of each assignment’s output, the Service Provider will prepare and submit a corresponding report to the MZ Project team. The stage reports should contain all relevant information on the progress made; results and deliverables in place (including all concrete products and deliverables attached to the document); critical reflection on issues and challenges faced, or these that may need attention in the following stage. The reports will be based on a template provided by the UNDP.

• Final report

The final report will be submitted within 10 days of completion of the services. The final report should also contain information on the achievement of objectives, measurable results and outputs, as well as on the lessons learnt.

All reports and supporting products and deliverables should be submitted to the UNDP in electronic form upon completion of each task.

UNDP withholds the right to request periodical updates/reports on particular issues. All reports will be submitted in writing to the above listed persons. UNDP might request of Service Provider to liaise with respective UNDP partners during the implementation of the activities.

**VII. Expected duration of the contract/assignment**

The expected duration od the assignment is 4 months, in the period July – October 2019.

**IX. Professional Qualifications of the Successful Contractor and its key personnel**

• Professional agencies registered for services in subject are eligible to apply.

• Applying companies must have at least 5 years of relevant experience.

• The service provider must be a registered organization and company that has institutional and managerial capacities and experienced human and adequate physical resources capable to respond to given assignments.

• Reference list of the most recently implemented relevant projects needs to be submitted alongside the offer, including the contact details and statement/confirmation of organizations/clients on the success of similar projects/contracts of no less than 5 references in the past 5 years.

• Curriculum Vitae of the all required experts need to be submitted alongside the offer.

The Service Provider is required to ensure a team of minimum 7 experts: **Account Manager, Senior Communications Expert, Copywriter, Journalist, Videographer, Event Manager and Photojournalist.** The Service Provider may also propose an additional expert or team of experts if deemed necessary for the implementation of the assignment. However, only the key experts shall be included in the evaluation process.

They should meet the requirements as set in the data sheet.

|  |  |  |
| --- | --- | --- |
| **Staff`s profile** | **General responsibilities in relation to carrying out the assignment**  | **Required Competencies and Conditions** |
| **Account Manager** | Lead the team;Coordinate the day-to-day implementation of the assignment with UNDP team;Provides expert input during the assignment’s tasks;Proposes key actions and suggestions.*Duration: July-October (up to 50 expert days)* | Bachelor’s degree in business administration, marketing, communications or other related field;Extensive experience in management and coordination of consultancy contracts;Extensive knowledge and practical experience in communication/production/promotion services;Proven experience of at least 10 years in providing consultancy services in Sector of Communications. |
| **Senior Communications Expert** | Support the Account Manager in identifying and developing effective approaches to defined tasks;Ensure that communications activities promote the project amongst media and other targeted audience;Oversee development of required materials;Develop communications and marketing plans and/or messages.*Duration: July-October (up to 40 expert days)* | Bachelor’s degree in business administration, marketing, communications, or other relate fields;At least 7 years of professional work experience in communications and marketing or public relations;More than 4 years of experience in designing, editing and producing publications, especially reports;Experience in brand management;Excellent oral communication skills, including presentation. |
| **Copywriter** | Design and develop content of MZ stories and Catalogue;Write/edit short success stories produced by the project;Select visuals/photos that will be used in materials. *Duration: July-October (up to 40 expert days)* | A university degree in communications (journalism) or related social science field; At least 5 years of relevant and proven professional experience in journalism, copywriting and editing;Strong knowledge of production of content for print media (newsletters and brochures) required.  |
| **Journalist** | Responsible for research, writing, editing, proofreading and filing news stories, features and articles for use on television and radio or within social media and newspapers, in print and online.*Duration: July-October (up to 40 expert days)* | A university degree in journalism (communications); At least 5 years of relevant and proven professional experience in journalism, copywriting and editing;Strong knowledge of production of content for print media (newsletters and brochures) required.  |
| **Videographer** | Responsible for recording events, video stories, dialogues, and other small-scale video productions. Also responsible for editing of recorded videos and formatting for public viewing.Responsible for video equipment.*Duration: July-October (up to 40 expert days)* | Formal background in communications, cinematography, broadcasting, video editing or related field;At least 5 years of relevant and proven professional experience in video recording and video editing;Equipped with technical knowledge and creativity when it comes to creating videos and using them to tell a story. |
| **Event Manager** | End to end management of all planned events; Responsible for the design and implementation of the plan for all media events;Ensuring all events are according to budget;Communicating to key internal and external stakeholders.*Duration: July-October (up to 40 expert days)* | Bachelor’s degree in business administration, marketing, communications, or other related fields;Minimum of 2 years’ event experience;Budget management experience;Excellent planning and time management skills. |
| **Photojournalist** | Capture and provide high quality and high-resolution images of events, including visual stories of implementing MZ Project activities;The photos will be used in a variety of advocacy events, publications and campaigns to capture public attention and highlight the importance of strengthening of MZ’s;The photojournalist will be required to have her/his own equipment (a semi-professional or professional DSLR camera, lenses, flashes and all other necessary accessories). *Duration: July-October (up to 30 expert days)* | At least 3 years of experience in the field of photography in social/development area;Specific experience as photojournalist is required; Advanced knowledge and skills of MS Office, including Corel Draw, Adobe Photoshop and other editing tools is required;Relevant experience in working with local actors is an asset. |

**XII. Price and Schedule of Payments**

|  |  |  |  |
| --- | --- | --- | --- |
| Outputs | Percentage | Timing | Condition for Payment Release |
| VIDEO PRODUCTION:* Up to 11 HD videos (up to 10 short+1 long) with English subtitles produced.
 | 20% | July 2019 | Within thirty (30) days from the date of meeting the following conditions:1. UNDP’s written acceptance (i.e., not mere receipt) of the quality of the outputs; and
2. Receipt of invoice from the Service Provider.
 |
| COMMUNICATIONS/COPYWRITING/DESIGN SERVICES:* 50 MZ stories digital/online Catalogue prepared.
* Short booklet/sketchbook designed.
* Up to 5 photo stories produced.
 | 30% | July – August 2019 |
| PR AND EVENT MANAGEMENT:* Maximum 30 promo mini-events through BiH managed and implemented.
 | 30% | August – September 2019  |
| ONLINE AND SOCIAL MEDIA PROMOTION:* YouTube videos advertised on social media.
* PR visibility online banners arranged and promoted.
 | 20% | October 2019 |

**Remark:** UNDP holds the right to reject development or implementation of some of assignment tasks. In that case, the price of the rejected tasks would be subtracted from the total price.

# Section 6: Returnable Bidding Forms / Checklist

This form serves as a checklist for preparation of your Proposal. Please complete the Returnable Bidding Forms in accordance with the instructions in the forms and return them as part of your Proposal submission. No alteration to format of forms shall be permitted and no substitution shall be accepted.

Before submitting your Proposal, please ensure compliance with the Proposal Submission instructions of the BDS 22.

**Technical Proposal Envelope:**

|  |  |
| --- | --- |
| **Have you duly completed all the Returnable Bidding Forms?**  |  |
| * Form A: Technical Proposal Submission Form
 | [ ]  |
| * Form B: Bidder Information Form
 | [ ]  |
| * Form C: Joint Venture/Consortium/ Association Information Form
 | [ ]  |
| * Form D: Qualification Form
 | [ ]  |
| * Form E: Format of Technical Proposal
 | [ ]  |
| **Have you provided the required documents to establish compliance with the evaluation criteria in Section 4?**  | [ ]  |

**Financial Proposal Envelope**

**(Must be submitted in a separate sealed envelope/password protected email)**

|  |  |
| --- | --- |
| * Form F: Financial Proposal Submission Form
 | [ ]  |
| * Form G: Financial Proposal Form
 | [ ]  |

## **Form A:** Technical Proposal Submission Form

|  |  |  |  |
| --- | --- | --- | --- |
| Name of Bidder: | [Insert Name of Bidder] | Date: | Select date |
| RFP reference: | [Insert RFP Reference Number] |

We, the undersigned, offer to provide the services for [Insert Title of services] in accordance with your Request for Proposal No. [Insert RFP Reference Number] and our Proposal. We are hereby submitting our Proposal, which includes this Technical Proposal and our Financial Proposal sealed under a separate envelope.

We hereby declare that our firm, its affiliates or subsidiaries or employees, including any JV/Consortium /Association members or subcontractors or suppliers for any part of the contract:

1. is not under procurement prohibition by the United Nations, including but not limited to prohibitions derived from the Compendium of United Nations Security Council Sanctions Lists;
2. have not been suspended, debarred, sanctioned or otherwise identified as ineligible by any UN Organization or the World Bank Group or any other international Organization;
3. have no conflict of interest in accordance with Instruction to Bidders Clause 4;
4. do not employ, or anticipate employing, any person(s) who is, or has been a UN staff member within the last year, if said UN staff member has or had prior professional dealings with our firm in his/her capacity as UN staff member within the last three years of service with the UN (in accordance with UN post-employment restrictions published in ST/SGB/2006/15);
5. have not declared bankruptcy, are not involved in bankruptcy or receivership proceedings, and there is no judgment or pending legal action against them that could impair their operations in the foreseeable future;
6. undertake not to engage in proscribed practices, including but not limited to corruption, fraud, coercion, collusion, obstruction, or any other unethical practice, with the UN or any other party, and to conduct business in a manner that averts any financial, operational, reputational or other undue risk to the UN and we embrace the principles of the United Nations Supplier Code of Conduct and adhere to the principles of the United Nations Global Compact.

We declare that all the information and statements made in this Proposal are true and we accept that any misinterpretation or misrepresentation contained in this Proposal may lead to our disqualification and/or sanctioning by the UNDP.

We offer to provide services in conformity with the Bidding documents, including the UNDP General Conditions of Contract and in accordance with the Terms of Reference

Our Proposal shall be valid and remain binding upon us for the period of time specified in the Bid Data Sheet.

We understand and recognize that you are not bound to accept any Proposal you receive.

I, the undersigned, certify that I am duly authorized by [Insert Name of Bidder] to sign this Proposal and bind it should UNDP accept this Proposal.

Name: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Title: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Date: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Signature: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

[*Stamp with official stamp of the Bidder*]

## **Form B:** BidderInformation Form

|  |  |
| --- | --- |
| **Legal name of Bidder** | [Complete] |
| **Legal address** | [Complete] |
| **Year of registration** | [Complete] |
| **Bidder’s Authorized Representative Information** | Name and Title: [Complete] Telephone numbers: [Complete]Email: [Complete] |
| **Are you a UNGM registered vendor?** | [ ]  Yes [ ]  No If yes, [insert UGNM vendor number]  |
| **Are you a UNDP vendor?** | [ ]  Yes [ ]  No If yes, [insert UNDP vendor number]  |
| **Countries of operation** | [Complete] |
| **No. of full-time employees** | [Complete] |
| **Quality Assurance Certification (e.g. ISO 9000 or Equivalent) (***If yes, provide a Copy of the valid Certificate):* | [Complete] |
| **Does your Company hold any accreditation such as ISO 14001 related to the environment?** *(If yes, provide a Copy of the valid Certificate):* | [Complete] |
| **Does your Company have a written Statement of its Environmental Policy?** *(If yes, provide a Copy)* | [Complete] |
| **Contact person UNDP may contact for requests for clarification during Proposal evaluation**  | Name and Title: [Complete]Telephone numbers: [Complete]Email: [Complete] |
| **Please attach the following documents:**  | * Company Profile, which should not exceed fifteen (15) pages, including printed brochures and product catalogues relevant to the goods/services being procured.
* Certificate of Incorporation/ Business Registration
* Tax Registration/Payment Certificate issued by the Internal Revenue Authority evidencing that the Bidder is updated with its tax payment obligations, or Certificate of Tax exemption, if any such privilege is enjoyed by the Bidder
* Trade name registration papers, if applicable
* Local Government permit to locate and operate in assignment location, if applicable
* Official Letter of Appointment as local representative, if Bidder is submitting a Bid in behalf of an entity located outside the country
* Power of Attorney
 |

## **Form C:** Joint Venture/Consortium/Association Information Form

|  |  |  |  |
| --- | --- | --- | --- |
| Name of Bidder: | [Insert Name of Bidder] | Date: | Select date |
| RFP reference: | [Insert RFP Reference Number] |

To be completed and returned with your Proposal if the Proposal is submitted as a Joint Venture/Consortium/Association.

|  |  |  |
| --- | --- | --- |
| **No** | **Name of Partner and contact information** *(address, telephone numbers, fax numbers, e-mail address)* | **Proposed proportion of responsibilities (in %) and type of services to be performed**  |
| 1 | [Complete] | [Complete] |
| 2 | [Complete] | [Complete] |
| 3 | [Complete] | [Complete] |

|  |  |
| --- | --- |
| **Name of leading partner** (with authority to bind the JV, Consortium, Association during the RFP process and, in the event a Contract is awarded, during contract execution) | [Complete] |

We have attached a copy of the below document signed by every partner, which details the likely legal structure of and the confirmation of joint and severable liability of the members of the said joint venture:

[ ]  Letter of intent to form a joint venture ***OR*** [ ]  JV/Consortium/Association agreement

We hereby confirm that if the contract is awarded, all parties of the Joint Venture/Consortium/Association shall be jointly and severally liable to UNDP for the fulfillment of the provisions of the Contract.

|  |  |
| --- | --- |
| Name of partner: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  | Name of partner: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ |
| Signature: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ | Signature: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ |
| Date: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ | Date: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ |
|  |  |
| Name of partner: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ | Name of partner: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ |
| Signature: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ | Signature: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ |
| Date: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ | Date: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ |

## **Form D:** QualificationForm

|  |  |  |  |
| --- | --- | --- | --- |
| Name of Bidder: | [Insert Name of Bidder] | Date: | Select date |
| RFP reference: | [Insert RFP Reference Number] |

If JV/Consortium/Association, to be completed by each partner.

**Historical Contract Non-Performance**

|  |
| --- |
| [ ]  Contract non-performance did not occur for the last 3 years  |
| [ ]  Contract(s) not performed for the last 3 years |
| **Year** | **Non- performed portion of contract** | **Contract Identification** | **Total Contract Amount** (current value in US$) |
|   |  | Name of Client: Address of Client: Reason(s) for non-performance: |  |

**Litigation History** (including pending litigation)

|  |
| --- |
| [ ]  No litigation history for the last 3 years |
| [ ]  Litigation History as indicated below |
| **Year of dispute**  | **Amount in dispute** (in US$) | **Contract Identification** | **Total Contract Amount** (current value in US$) |
|   |  | Name of Client: Address of Client: Matter in dispute: Party who initiated the dispute: Status of dispute:Party awarded if resolved: |  |

**Previous Relevant Experience**

Please list only previous similar assignments successfully completed in the last 5 years.

List only those assignments for which the Bidder was legally contracted or sub-contracted by the Client as a company or was one of the Consortium/JV partners. Assignments completed by the Bidder’s individual experts working privately or through other firms cannot be claimed as the relevant experience of the Bidder, or that of the Bidder’s partners or sub-consultants, but can be claimed by the Experts themselves in their CVs. The Bidder should be prepared to substantiate the claimed experience by presenting copies of relevant documents and references if so requested by UNDP.

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Project name & Country of Assignment** | **Client & Reference Contact Details** | **Contract Value** | **Period of activity and status** | **Types of activities undertaken** |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |

*Bidders may also attach their own Project Data Sheets with more details for assignments above.*

[ ]   Attached are the Statements of Satisfactory Performance from the Top 3 (three) Clients or more.

**Financial Standing**

|  |  |
| --- | --- |
| **Annual Turnover for the last 3 years** | Year       USD      Year       USD      Year       USD       |
| **Latest Credit Rating (if any), indicate the source** |  |

|  |  |
| --- | --- |
| **Financial information**(in US$ equivalent) | **Historic information for the last 3 years** |
|  | Year 1 | Year 2 | Year 3 |
|  | *Information from Balance Sheet* |
| Total Assets (TA) |  |  |  |
| Total Liabilities (TL) |  |  |  |
| Current Assets (CA) |  |  |  |
| Current Liabilities (CL) |  |  |  |
|  | *Information from Income Statement* |
| Total / Gross Revenue (TR) |  |  |  |
| Profits Before Taxes (PBT) |  |  |  |
| Net Profit  |  |  |  |
| Current Ratio |  |  |  |

[ ]  Attached are copies of the audited financial statements (balance sheets, including all related notes, and income statements) for the years required above complying with the following condition:

* 1. Must reflect the financial situation of the Bidder or party to a JV, and not sister or parent companies;
	2. Historic financial statements must be audited by a certified public accountant;
	3. Historic financial statements must correspond to accounting periods already completed and audited. No statements for partial periods shall be accepted.

## **Form E:** Format ofTechnical Proposal

|  |  |  |  |
| --- | --- | --- | --- |
| Name of Bidder: | [Insert Name of Bidder] | Date: | Select date |
| RFP reference: | [Insert RFP Reference Number] |

The Bidder’s proposal should be organized to follow this format of Technical Proposal. Where the bidder is presented with a requirement or asked to use a specific approach, the bidder must not only state its acceptance, but also describe how it intends to comply with the requirements. Where a descriptive response is requested, failure to provide the same will be viewed as non-responsive.

**SECTION 1: Bidder’s qualification, capacity and expertise**

* 1. Brief description of the organization, including the year and country of incorporation, and types of activities undertaken.
	2. General organizational capability which is likely to affect implementation: management structure, financial stability and project financing capacity, project management controls, extent to which any work would be subcontracted (if so, provide details).
	3. Relevance of specialized knowledge and experience on similar engagements done in the region/country.
	4. Quality assurance procedures and risk mitigation measures.
	5. Organization’s commitment to sustainability.

**SECTION 2: Proposed Methodology, Approach and Implementation Plan**

This section should demonstrate the bidder’s responsiveness to the TOR by identifying the specific components proposed, addressing the requirements, providing a detailed description of the essential performance characteristics proposed and demonstrating how the proposed approach and methodology meets or exceeds the requirements. All important aspects should be addressed in sufficient detail and different components of the project should be adequately weighted relative to one another.

* 1. Explain how you understand the requirement(s), its important aspects and components.
	2. A detailed description of the approach and methodology for how the Bidder will achieve the Terms of Reference of the project, keeping in mind the appropriateness to local conditions and project environment.
	3. Explain how the different service elements shall be organized, controlled and delivered. The methodology shall also include details of the Bidder’s internal technical and quality assurance review mechanisms. Also, explain whether any work would be subcontracted, to whom, how much percentage of the work, the rationale for such, and the roles of the proposed sub-contractors and how everyone will function as a team.
	4. Identification and analysis of risks and mitigation measures (e.g. Risk Assessment Matrix).
	5. Implementation plan including a Gantt Chart or Project Schedule indicating the detailed sequence of activities that will be undertaken and their corresponding timing.
	6. Demonstrate how you plan to integrate sustainability measures in the execution of the contract.
	7. Any other comments or information regarding the project approach and methodology that will be adopted.

**SECTION 2A: Bidder’s Comments and Suggestions on the Terms of Reference**

Provide comments and suggestions on the Terms of Reference, or additional services that will be rendered beyond the requirements of the TOR, if any.

**SECTION 3: Management Structure and Key Personnel**

* 1. Describe the overall management approach toward planning and implementing the project. Include an organization chart for the management of the project describing the relationship of key positions and designations. Provide a spreadsheet to show the activities of each personnel and the time allocated for his/her involvement.
	2. Provide CVs for key personnel that will be provided to support the implementation of this project using the format below. CVs should demonstrate qualifications in areas relevant to the Scope of Services.

**Format for CV of Proposed Key Personnel**

|  |  |
| --- | --- |
| Name of Personnel | [Insert] |
| Position for this assignment | [Insert] |
| Nationality | [Insert] |
| Language proficiency  | [Insert] |
| Education/ Qualifications | *[Summarize college/university and other specialized education of personnel member, giving names of schools, dates attended, and degrees/qualifications obtained.]* |
| [Insert] |
| Professional certifications | *[Provide details of professional certifications relevant to the scope of services]* |
| * Name of institution: [Insert]
* Date of certification: [Insert]
 |
| Employment Record/ Experience | *[List all positions held by personnel (starting with present position, list in reverse order), giving dates, names of employing organization, title of position held and location of employment. For experience in last five years, detail the type of activities performed, degree of responsibilities, location of assignments and any other information or professional experience considered pertinent for this assignment.]* |
| [Insert] |
| References | *[Provide names, addresses, phone and email contact information for two (2) references]* |
| Reference 1: [Insert]Reference 2:[Insert] |

I, the undersigned, certify that to the best of my knowledge and belief, these data correctly describe my qualifications, my experiences, and other relevant information about myself.

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Signature of Personnel Date (Day/Month/Year)

**Form F:** Financial Proposal Submission Form

|  |  |  |  |
| --- | --- | --- | --- |
| Name of Bidder: | [Insert Name of Bidder] | Date: | Select date |
| RFP reference: | [Insert RFP Reference Number] |

We, the undersigned, offer to provide the services for [Insert Title of services] in accordance with your Request for Proposal No. [Insert RFP Reference Number] and our Proposal. We are hereby submitting our Proposal, which includes this Technical Proposal and our Financial Proposal sealed under a separate envelope.

Our attached Financial Proposal is for the sum of [Insert amount in words and figures].

*Our Proposal shall be valid and remain binding upon us for the period of time specified in the Bid Data Sheet.*

We understand you are not bound to accept any Proposal you receive.

Name: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Title: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Date: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Signature: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

[*Stamp with official stamp of the Bidder*]

## **Form G:** Financial ProposalForm

|  |  |  |  |
| --- | --- | --- | --- |
| Name of Bidder: | [Insert Name of Bidder] | Date: | Select date |
| RFP reference: | [Insert RFP Reference Number] |

The Bidder is required to prepare the Financial Proposal following the below format and submit it in an envelope separate from the Technical Proposal as indicated in the Instruction to Bidders. Any Financial information provided in the Technical Proposal shall lead to Bidder’s disqualification.

The Financial Proposal should align with the requirements in the Terms of Reference and the Bidder’s Technical Proposal.

**Currency of the proposal:** [Insert Currency]

**Table 1: Summary of Overall Prices**

|  |  |
| --- | --- |
|  | **Amount(s)** |
| **Professional Fees** (from Table 2) |  |
| **Other Costs** (from Table 3) |  |
| **Total Amount of Financial Proposal** |  |

**Table 2: Breakdown of Professional Fees**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Name** | **Position** | **Fee Rate** | **No. of Days/months/ hours** | **Total Amount** |
| *A* | *B* | *C=A+B* |
| In-Country  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
| Home Based  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
| **Subtotal Professional Fees:** |  |

**Table 3: Breakdown of Other Costs**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  **Description** | **UOM** | **Quantity** | **Unit Price** | **Total Amount** |
| International flights | Trip |  |  |  |
| Subsistence allowance | Day |  |  |  |
| Miscellaneous travel expenses | Trip |  |  |  |
| Local transportation costs | Lump Sum |  |  |  |
| Out-of-Pocket Expenses |  |  |  |  |
| Other Costs: (please specify) |  |  |  |  |
| **Subtotal Other Costs:** |  |

**Table 4: Breakdown of Price per Deliverable/Activity**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Deliverable/****Activity description**  | **Time**(person days) | **Professional Fees** | **Other Costs** | **Total** |
| Deliverable 1 |  |  |  |  |
| Deliverable 2 |  |  |  |  |
| Deliverable 3 |  |  |  |  |
| ….. |  |  |  |  |

1. Non-performance, as decided by UNDP, shall include all contracts where (a) non-performance was not challenged by the contractor, including through referral to the dispute resolution mechanism under the respective contract, and (b) contracts that were so challenged but fully settled against the contractor. Non-performance shall not include contracts where Employers decision was overruled by the dispute resolution mechanism. Non-performance must be based on all information on fully settled disputes or litigation, i.e. dispute or litigation that has been resolved in accordance with the dispute resolution mechanism under the respective contract and where all appeal instances available to the Bidder have been exhausted. [↑](#footnote-ref-2)