**TERMS OF REFERENCE**

for Provision of Interior Design, Renovation Services and Furniture for ARISE Plus Myanmar Trade-Related Assistance project office renovation in Yangon, Myanmar

1. **Background**

The International Trade Centre (ITC) is implementing the ARISE Plus Myanmar Trade-Related Assistance project which aims to contribute to inclusive and sustainable growth. It supports greater connectivity and economic integration between Myanmar and the Association of Southeast Asian Nations (ASEAN) in line with the ASEAN Economic Community (AEC) Blueprint 2025.

As part of the project implementation modalities ITC is organizing the opening an Arise Plus project office in Yangon, within the premises of the Department of Consumer Affairs (DoCA) of the Ministry of Commerce (MOC), which aims to provide a good working environment to project staff where optimum office space is utilized with adequate equipment/furniture for best staff performance. In view of these factors, it is required to complete the necessary renovation works in the office space allocated for the project.

In order to complete the above arrangement in time, the office is looking for an individual contractor who will be responsible to fulfill the objectives of the office renovation work and to carry out all the tasks mentioned under Section III.

1. **Objective.**

Professional renovation service (Interior Design and Construction services) and provision of adequate Furniture are required for refurbishment and renovation of the Myanmar Arise Plus Project office in Yangon, Myanmar. The objective of this assignment is the interior design, renovation, renovation works and furnishing, including, supervision of works. The approximate area under renovation is approximately 102 sqm (incl. 34 sqm for office, 64 sqm for conference room).

Major services and activities include but not limited to the following:

* Task A. Perform all required site surveys and measurements, liaise with DoCA facility management unit, and execute the project office design.
* Task B. Construction and Renovation services and supervision. Supply the Equipment and Furniture provision. Office ready.

**III. Scope of work, activities, tasks, deliverables and timelines, plus budget per deliverable.**

In close coordination with UNDP procurement Unit in Yangon and the Department of Consumer Affairs (DoCA) in Yangon, and under overall supervision of the ITC Project team, the Design, Renovation Services and Supply of furniture will be required to complete the office interior renovation project.

Task A. Perform all required site surveys and measurements, liaise with the facility management unit of DoCA, and execute the project office interior design, renovation services:

1. Arrange site surveys and data collection.
2. Draw execution plans, including: all necessary floor plans, sections, elevations, schemes, Furniture layouts and specifications, fire/hazard escape drawings, etc.
3. Develop detailed time schedule for the design phase execution
4. Develop works execution time schedule.
5. BOQ for renovation works with price estimate.
6. BOQ for furniture supply and installation with price estimate.
7. No. of Fire Extinguishers required for the project office and security plans
8. Revise the design documentation and BOQ as needed until the price estimates fit in ITC construction budget expectation.
9. Assist in obtaining necessary authorizations and approvals from DoCA facility management unit and respective local authorities.

Task B. Construction and Renovation services and supervision. Office ready.

1. Submit construction and Renovations works execution schedules.
2. Complete the construction and renovation work as per agreed plan.
3. Provide comprehensive construction site supervision.
4. Organize all necessary meetings with ITC and UNDP.
5. Provide quality assurance and control.
6. Validate works done as per approved milestones to when payments to contractor and suppliers can be released by UNDP.
7. Issuing all necessary certificates.

Task C. Supply Equipment and Furniture provision. Office equipment ready.

1. Design lay-out and furniture to maximize the usable working space. Possible arrangement could include 4 desks + chairs with power, cables & telephone for one working station, 1 display stand for printed material, 1 conference room table + 8 chairs with power and cables, 1 high table for coffee machine and microwave and 1 filling cabinet
2. Bidder shall consider the work station available for the connection of the electrical switches for power, cable and telephone networks
3. Provide price quotations for required office furniture including technical specifications, designs, catalogues and drawings
4. Other UN agencies, funds or programs should have the right to purchase the same or similar services from selected Contractor(s) at their sole discretion under this terms and conditions

**Proposed duration.**

* Task A 10 working days
* Task B and C Interior renovation and furniture provision works duration 1 month
* Defect liability period 6 months
1. **REPORTING OBLIGATIONS**
	1. **Contractor’s outputs for Phase 1:**

|  |  |  |
| --- | --- | --- |
|  | **Name of the report**  | **Deadline for submission**  |
| 1  | Final technical design and accompanying documents and assessments for office rooms: * Technical description;
* Bill of quantities with estimated cost
* Technical specification for furniture and other equipment
* All drawings necessary for structures of such kind, as prescribed by the local law
 | 10 days after contract signature  |

The contractor will deliver an electronic copy of technical designs and accompanying documents to UNDP/ITC and MOC/DoCA in both Myanmar and English languages.

* 1. **Contractor’s outputs for Phase 2:**

|  |  |  |
| --- | --- | --- |
|  | **Name of the report**  | **Period/deadline for submission**  |
| 1  | Weekly reports on the process and progress of renovation of the project office in accordance to the TOR.  | Every week, following commencement of civil works for renovation of project office until completion of works  |
| 2 | Renovation and Construction Project service and supply the equipment and furniture for Project Office | Estimated commencement of works: as soon as the technical design is agreed on with MOC/DoCA and ITC. Estimated completion of works: at the latest on 30 November 2019 |
| 3 | Final delivery of the renovation made  | At maximum, 5 days after completion of renovation works and supply the furniture and equipment.   |

The contractor will deliver an electronic copy of technical designs and accompanying documents to UNDP/ITC and MOC/DoCA in both Myanmar and English languages.

**Qualifications, Specialized Experience and additional competencies.**

* Proven track record in successful implementation of similar projects in the past 2 years.
* Professional expertise and excellent background in interior design, construction works and supervision.
* The constructor must have the necessary experience and expertise in the supply and installation of office furniture and equipment

**Payments schedule.**

Upon completion of the Task A

Upon completion of the Task B and C Renovation Work and suppling office Furniture.

Upon completion of the defect liability period, rectifying all defects and issuing of Final completion certificate. 5%

**Evaluation criteria.**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **TECHNICAL EVALUATION CRITERIA**  | **REQUIRED SUPPORTING DOCUMENTS**  | **RATING**  | **SCALING**  | **MAXIMUM SCORE**  |
| **TECHNICAL CAPABILITY**  |  |  |  |  |
| 1. Years of experience in carrying out Architectural and Engineering activities and a proven record in delivering professional results
 | Company profile; including description of company, years of experience, number of employees and business license  |  |  | 10 |
| 1. Experience in conducting similar projects.
 | List of at least 3 similar works, certificates of works completion, clients names and contact details, reference letters |  |  | 20  |
| **METHODOLOGY**  |
| 1. A detailed description of the proposed methodology, describing the approach that will be taken to deliver the project
 | A description of the proposed methodology  | The proposed methodology thoroughly describes the envisaged approach taken to deliver the project | 30  | 30  |
| The proposed methodology mostly provides a satisfactory description of the envisaged approach taken to deliver the project  | 20  |
| The proposed methodology provides a partial description of the envisaged approach taken to deliver the project  | 10  |
| No methodology or description of activities provided  | 0  |
| **TOTAL TECHNICAL SCORE**  | **60**  |

Minimum technical required score: 60 points (Technical Proposals scoring less than 60 points will be considered non-responsive, therefore will be rejected). Obtaining a minimum of 60 points from the technical evaluation would be considered for the financial evaluation and having received the highest combined weight technical proposal 60% + financial 40%= 100%.

|  |  |
| --- | --- |
| Sylvie Bétemps CochinSenior Trade Promotion Officer, Office for Asia and the PacificInternational Tarde Centre | Xuejun JiangChief, Office for Asia and the PacificInternational Trade Centre |

**Annexes:**

Annex 1. Floor plan of office building. Drawing and measurements are estimates.