TERMS OF REFERENCE

Situation analysis: Conflict Affected Children in Eastern Ukraine

- Background

Since 2014, Eastern Ukraine has experienced a serious deterioration in the overall socio-economic situation, triggered by the start of an armed conflict, which has changed the situation for many households and worsened living standards.

In 2019, an estimated 5.2 million  people bear the brunt of the armed conflict in eastern Ukraine. Even after six years of active hostilities, there is no immediate resolution in sight to end the suffering of the affected population, 3.5 million of whom require humanitarian assistance and protection due to widespread mine contamination, escalating psychological trauma and the degrading impact of the lack of access to basic services. Most people in need live in the conflict-affected oblasts of Donetska and Luhanska, divided by the 427-kilometre-long ‘contact line’, which is equivalent to the length of the French-German border.

There are around 700,000 of children living in the Luhanska and Donetska oblasts (both in Government-controlled area (GCA) and non-Government controlled area (NGCA)), and the on-going conflict continues to endanger daily their physical and psychological wellbeing, especially those living along the ‘contact line’ where active armed hostilities are most intense. The education cluster reports that there are more than 242,000 children and teachers in schools located along the ‘contact line’ regularly experiencing  shelling and facing extreme levels of mine contamination. More than 150 schools are singled out of their proximity to military activities, while 62 schools reported unexploded ordnance near them. In most communities, to reach their education facility, children commute along unsafe routes. In a single incident in May 2018, a child was killed and three more injured from an explosion in their school bus. Attacks on schools are frequent. Since the start of the conflict over 750 educational facilities were damaged due to hostilities, and on several occasions, education facilities were damaged more than once. Alarmingly is also the fact that not all the education facilities regularly exposed to shelling are adequately equipped or accessible bomb shelters or safe spaces.

As a part of its Country Programme Document for 2018-2022, UNICEF is committed to achieve its goals through evidence-based advocacy in the fields of social protection, child protection, education, health and environment, with social inclusion as an overarching focus area concern. As such, UNICEF regularly invests in efforts to generates disaggregated data to identify the most vulnerable population, in particular children (girls and boys) and their key barriers for these population groups in accessing social and other services.

Since the beginning of the conflict in the Eastern Ukraine, only two relevant assessments were conducted by UNICEF in 2017, “Children of the contact Line” and it’s updated version in 2018, which focused on identifying the impact of the conflict on children and their needs. These assessments provided limited qualitative information related to a limited geographically scope (0-5km area of the contact line). These two studies do not provide extensive quantitative information at the household level and do not cover the whole conflict-affected areas (GCA and NGCA).

- Rationale and objectives

The primary aim of the study is to generate data to be basis for analytical information and knowledge with specific focus on humanitarian needs of the most vulnerable children living in the conflict-affected regions of Ukraine, in conformity with the requirements of the Child Rights Convention, and more especially those standards set out in the International Humanitarian Law and SPHERE Standards, as well as in Ukrainian national standards. The purpose of the study is to assess the needs of children and households with children in the conflict-affected areas.

Objectives:

- Identify the impact of the conflict on children and household living with children;

- Identify the needs and gaps of conflict-affected children and households with children in the following 5 key areas: Child Protection, Health, Education, WASH, Social Policy;

Key research questions:

- Did the conflict have impact on wellbeing of children, boys and girls of different ages? What was the impact?

- What is the situation with children and household with children in the concrete area (as per 5 key areas)?

- What are the identified needs in each area?

Key research questions should cover following areas:

- Child Protection:

- Attitudes Toward Domestic Violence;

- Birth registration;

- Child Discipline;

- Child Labour;

- Child Functioning;

- Children living arrangements and Orphanhood.

- Child Functioning (disabilities) as crosscutting issue;

- Health:

- Child mortality;

- Child nutrition;

- Child Health;

- Maternal and newborn health;

- HIV/AIDS and Sexual Behavior;

- Education:

- Early Childhood Education

- Primary and secondary school participation

- Parental involvement

- WASH:

- Use of safely managed drinking water services;

- Use of safely managed sanitation services, including hand-washing with soap and water;

- Social Policy:

- Poverty;

- Access to basic social services and benefits;

Geographical coverage: 4 geographical area: Non-Government Controlled Area (NGCA) (Luhanska and Donetska oblast), Government Controlled Area (GCA) (Luhanska and Donetska oblast) with splitting up by urban/rural, GCA 0-5km, GCA 5-20-km of Line of Contact disaggregation.

The study (assessment) will provide qualitative and representative quantitative estimates of the impact of the conflict on wellbeing, gaps and needs of the children in eastern Ukraine.

The research approach and data collection and analysis methods should also focus on equity, gender and human rights aspects, be responsive and appropriate for analysing the gender equality, human rights issues including child rights issues identified in the scope. Gender equality, equity and human rights considerations will be elaborated by the Research Team during the inception phase and addressed across the final report.

The study will equip UNICEF programming with evidence-based analysis on situation of children and provide baseline information for future measure of progress. The study will foster a better understanding of the relevance of humanitarian needs and gaps in 5 key areas (Child Protection, Health, Education, WASH and Social Policy) and support coordination within and across agencies, organizations and communities on how to address those needs. Data analysis and interpretation will enable to better understand the Child Rights Situation regarding humanitarian, recovery and development activities. In addition, the study will provide evidence for further advocacy with the Government and local authorities on the current risks for conflict-affected children and their families. Therefore, the findings of the study would help UNICEF and other agencies to promote and support the development of effective Child Protection, Health, Education, WASH, Social Policy programming that ensure qualitative humanitarian and recovery activities.

Table 1: Overview of study Users and Uses

| Users | Uses |
| --- | --- |
| All sections of UNICEF Country Office, Monitoring & Evaluation unit | Develop the programme strategy and planning (Humanitarian Action for Children, Annual Work Plan), tailor strategic approaches to the slowly changing context. Incorporate data (i) to improve the performance of future interventions; (ii) to improve future interventions; (ii) to strengthen the M&E component and ensure strong evidence-based approach in planning and strategizing |
| National level authorities | Support decision making, as well as the development of strategic orientations on the future programming, including the allocation of human, material and financial resources based on the evidence generated by the study. |
| Territorial (hromadas) authorities | Adjust monitoring approaches to enhance quality program delivery and development. Improve budget allocation and effective budget usage procedures, harmonization of actions with the international humanitarian response community to minimize expenses and avoid leaving gaps or overlapping in covering critical needs of the affected population. |
| Donors and other Development partners | Influence the future design and scale-up of UNICEF Programmes |
| Partner NGOs and other Civil Society Organisations | Build on the evidence generated by the study to improve performance of IPs Strengthen capacity where it is lacking. |

Theory of change:

| Activity | The survey process |
| --- | --- |
| Output | Report with systematized data about the respective situation at household level |
| Outcome: | Survey will provide possibility to draw a base-line, which will allow then to identify trends by regular monitoring. Government, local authorities, humanitarian community and UNICEF evidenced based interventions with focus on most vulnerable children living in the conflict-affected regions of Ukraine |
| Impact: | Needs of the most vulnerable children and their families living in the conflict-affected regions are addressed Improved Child Rights Situation conflict-affected regions |

- Methodology

This study shall use a mixed-methods approach to investigate the major trends in situation of children in the conflict-affected regions:

The following methodology is recommended for carrying out the Study:

- Desk review of documents, studies and reports produced by UNICEF and other national and international organizations on humanitarian situation of affected people and children in eastern conflict area of Ukraine. Familiarization with similar studies in other countries.

- Secondary data analysis: official statistical and administrative data review, collection and analysis (SSSU, Government, local authorities) covering the period from 2013 (pre-conflict) to up to date available data. Official humanitarian data review, collection and analysis (reports, past study/research/evaluation reports related to the subject, etc.). Considering no reliable sources of information in NGCA it is expected to have gaps in secondary data and information for the period from 2014 to up to date.

- Quantitative research (survey at household [HH] level): interviews with conflict-affected households with children (age 0-17) in different locations on both sides of the Line of Contact and check points between GCA and NGCA;

The study shall involve the collection and analysis of primary data to fill in the gaps identified during the secondary data review. The questioner should be built on the Multiple Cluster Indicator Survey questionnaire adapted to the context and available resources.

Primary data collection should be limited to a survey of not more than 2500 households, chosen randomly from Donetska and Luhanska oblasts.  The survey design should provide a statistically representative depiction of households with children from main geographical areas.

Considering difficult access to the household in NGCA and limited information on total number and structure of population in NGCA, the survey design in NGCA might not follow the same rigorous methodology as in GCA. The data should be stratified by urban/rural settlement type to better understand the geographical differences in needs.

- Qualitative research (focus groups, in-depth interview, key informant): focus group discussions should be conducted among representatives of the household with children, in-depth interviews should be conducted with representative of household with children, key informant interviews should be conducted with local authorities, institutions national and international experts on the concrete area (as per 5 key areas).

- Expert discussion. To review the findings of the study by discussing with UNICEF experts from Child Protection, Education, Health, WASH and Social Policy.

The following limitations to the research are anticipated:

- limited access for primary data collection in some settlements close to contact line;

- limited data collection quality control in NGCA;

- alternative modalities for primary data collection in NGCA;

- unavailability and poor quality of secondary data due to emergency challenges;

To address some of these limitations, the Research Team will use information provided through the assessment on access, availability, scope and quality of data and validate key determinants of inequity and trends. The Research Team will inform UNICEF of identified limitations and will discuss alternative and acceptable solutions.

Ethical considerations

- Potential contractors will need to agree to meet the standards set in the UNICEF Procedure for Ethical Standards in Research, Evaluation, Data Collection and Analysis and Ukrainian Ethical consideration

- Potential contractors need to supply evidence of having undertaken ethics training or commit to undertake ethics training if capacity development is a priority and researchers with ethics training are unavailable.

- Researchers can identify relevant potential ethical issues and mitigation strategies relating to potential harms and benefits, informed consent, privacy and confidentiality and payment and compensation. If applicable, include specific considerations for research related to children and/or sensitive issues (such as violence against women and girls) and reference appropriate additional sources of guidelines and standards (e.g. UNICEF's guidance on children in research, WHO's guidance on violence research).

- Ethical review of the questionnaire should be undertaken

- Activities

| # | Activities | Estimated working days |
| --- | --- | --- |
| 1 | Desk review; Drafting the inception report: Mapping and identifying of sources for secondary data collection and analysis; Develop a methodology approach for the quantitative and qualitative data collection; Meet with the relevant stakeholders for agreeing the inception report. | 15 days |
| 2 | Methodology: Develop questionnaires for the primary data collection thought HH interviews, FGD, in-depth interviews, key informant interviews; Develop sampling methodology and draw a sample; Develop data collection instructions for the interviewers; Conduct training for the interviews (training could be conducted in Luhansk and/or Donetsk oblast GCA); Secondary data collection: Develop set of indicators to be collected; Data gathering; Data analysis; Primary data collection Conduct HH interviews; Conduct Focus Group Discussions; Conduct In-Depth interviews; Conduct Key Informants Interviews; Undertake Data cleaning and processing; | 75 days |
| 3 | Draft Report developing: Review of findings and analysis Submit the first draft of the report based on quantitative and qualitative data Present findings and review of the initial report by UNCIEF: identifying gaps and areas needing clarification. Submit draft Report | 30 days |
| 4 | Expert discussions (within UNCEF expert group) | 10 days |
| 5 | Final Report drafting: Finalize analysis, incorporating received feedback Review Final Report by UNICEF | 20 days |
| 6 | Presentation the findings (together with UNICEF): Publish and disseminate the report Meet with main stakeholders. | 2 days |
|  | Total | 152 days |

- Deliverables

The Contractor is responsible to submit the following Deliverables:

- Detailed Inception Report (IR) in English. Electronic version to be submitted within 15 working days after signing a contract and initial briefing with the Research Manager. This report should be 10 to 20 pages in length and should be in line with UN standards for IRs. The IR should outline detailed scope, study framework, methodology, secondary data sources, sampling methodology, data collection methods, data collection plan (field work), timeline for activities and submission of deliverables. The IR should also include initial data and findings based on the documentary review and final study design/plan. The Inception Phase will be used as a study phase and to collect and review all available evidence. This report will be used as an initial point of agreement and understanding between the Contractor and Research Manager. A draft will be shared in advance for comments and approved by UNICEF.

- Draft of Study Report in English and Ukrainian and dataset in Excel. Electronic version of the first draft should be submitted after completion data collection and analysis. The draft report should be in line with UNICEF standards and contain the same sections as the final report and will be at least 50 pages in length (excluding annexes). It will also contain an executive summary of no more than 5 pages.  The drafts will be shared with the UNICEF to seek their comments. The draft report will be quality assured by RSE Steering Committee. Draft should include Annexes (Electronic file with secondary data stored in a structured way and file with anonymize clean primary data set with final sampling weights). These files should contain all data and source of information that were used. Information from the data file should be used for the report and all indicators will be attached as indicators).

- Study Report (Final draft) in English and Ukrainian. Electronic versions of the report to be submitted after receiving consolidated comments and feedback from UNICEF. The final report will be at least 50 pages in length. It will also contain an executive summary of no more than 5 pages that includes a brief description of the situation, its context, the purpose of the study, its methodology and its major findings, conclusions and recommendations. The final report should include all received comments and suggestions provided by QA review providers. The Study Report should systematically answer the key study questions posed. It should clearly give the conclusions and recommends in a way that is substantiated by evidence. Report should include Annexes, and Power point presentation in English and Ukrainian (electronic version) based on the finalized study report summarizing the entire process, purpose, objectives, methodology, findings and recommendations and conclusions.

The Contractor should propose a timeline to submit the deliverables in their implementation plan (in proposals).

The oriented structure of the study report:

The Study Report is proposed to have the following structure, to be reviewed once the Contractor is selected:

Opening pages

Executive Summary

Introduction

Chapter 1:  Background, Objectives and Methodology

1.1. Background, Purpose, Objectives and Scope of the Study

1.2. Study Methodology

1.3. Major Limitations, Ethical considerations, Human Rights and Gender

Chapter 2: Situation Analysis

2.1. Overall context, baseline and end-survey results

2.2. Demographic situation

2.3. Socio-Economic situation

Chapter 3: Needs Assessment in 5 key areas: Child Protection, Health, Education, WASH, Social Policy

3.1. Child Protection

Analysis and Findings in

- Government-Controlled Area;

- 0-5 and 5-20-km areas along the Line of Contact;

- Non-Government-Controlled Area.

3.2. Health

Analysis and Findings in

- Government-Controlled Area;

- 0-5 and 5-20-km areas along the Line of Contact;

- Non-Government-Controlled Area.

3.3. Education, WASH, Social Policy

Analysis and Findings in

- Government-Controlled Area;

- 0-5 and 5-20-km areas along the Line of Contact;

- Non-Government-Controlled Area.

3.4. WASH

Analysis and Findings in

- Government-Controlled Area;

- 0-5 and 5-20-km areas along the Line of Contact;

- Non-Government-Controlled Area.

3.5. Social Policy

Analysis and Findings in

- Government-Controlled Area;

- 0-5 and 5-20-km areas along the Line of Contact;

- Non-Government-Controlled Area.

3.6. Cross-cutting topics

Conclusions and Recommendations

ANNEXES

- Terms of Reference

- Desk Review and Background Documents

- Detailed Methodology

- The questionnaire

- Interview Guides and Survey Instrument

- Information on the Contractor

- Results framework

- Output data tables

The study report will not be used for academic publishing by the Contractor.

The final structure will be discussed with potential contractor.

- Communication and dissemination

The study result will be disseminated to the Country Office (CO) senior management. The findings will be discussed at the management team meetings, programmatic reviews to inform the CO’s programming. The plan for dissemination and advocacy of the study result will be cleared by the CO’s RSE Steering Committee. Dissemination plan will be developed respectively in the office and then discussed/agreed with the CO.

- Roles

UNICEF as commissioner takes the accountability of the study and Head of CO RSE Steering Committee designated as supervisor for this study. Managerial function for this study will be done by M&E Officer (Research Manager).

The UNICEF CO RSE Steering Committee will have the following responsibilities:

•	to review TOR and make recommendations;

•	to ensure that study process meets the standards of quality and apply the procedures outlined in the SOPs for Quality Assurance and Ethical Standards in UNICEF-supported RSEs towards results for children in the CEE/CIS Region, like Procedure for Quality Assurance in UNICEF Research, UNICEF Evaluation and Research policies and other relevant guiding documents;

•	to review inception report, draft and final reports to ensure they meet UNICEF’s quality assurance and ethical standards;

•	to provide technical advice and support to the study process.

The Research Manager will have the following responsibilities:

•	Lead the management of the study process throughout the study (design, implementation and dissemination and coordination of its follow up);

•	Facilitate the participation of those involved in the study design;

•	Coordinate the selection of the Contractors;

•	Provide the Contractor with overall guidance as well as with administrative support; Oversee progress and conduct of the study, the quality of the process and the products;

•	Approve the deliverables and evaluate the Contractor’s work in consultation with RSE Steering Committee.

The Contractor will report to Research Manager and conduct the study by fulfilling the contractual arrangements in line with the TOR, RSE norms and standards and Ethical Guidelines; this includes developing of a study (implementation) plan as part of the inception report, drafting and finalizing the final report and other deliverables, and briefing the commissioner on the progress and key findings and recommendations, as needed.

The Contractor should also adhere to UNICEF’s RSE Policy, to UNEG’s ethical guidelines for UN evaluations and to UNICEF Reporting Standards. Contractor members will sign a no conflict of interest attestation.

The Contractor must demonstrate personal and professional integrity during the whole process of the study. Contractor must respect the right of institutions and individuals to provide information in confidence and ensure that sensitive data cannot be traced to its source. Furthermore, the Contractor and its members must take care that those involved in the study have an opportunity to examine the statements attributed to them. The study process must be sensitive to beliefs, manners, and customs of the social and cultural environment in which they will work. Especially, the Contractor must be sensitive to and address issues of protection, discrimination and gender inequality. Furthermore, the Contractor members are not expected to assess the personal performance of individuals and must balance an assessment of management functions with due consideration of this principle. Finally, if the Contractor uncover evidence of wrongdoing, such cases must be reported discreetly to the appropriate investigative body.

The study should follow UN Research and Study Norms and Standards – including ensuring that the planned study fully addresses any ethical issues.

- ESTIMATED COST

Payment schedule

| Amount | Deliverable |
| --- | --- |
| 30% | Detailed Inception Report (IR) in English and Ukrainian |
| 40% | First Draft of Study Report in English and Ukrainian |
| 30% | Study Report (Final draft) in English and Ukrainian and Power point presentation in English and Ukrainian |

Price proposal budget

All interested institutions are requested to include in their submission detailed costs including:

- Lumpsum for consultancy services based on this TOR and the consultant’s methodology and plan of actions according to the ToR with detailed breakdown to demonstrate:

  - Daily rate of each team member including hours per day

  - Expenses (external and internal travel, data collection (field works), accommodation, interpretation and translation etc. Please include all relevant costs that are required for this exercise) to be agreed prior to commencing project. The consultant should note that in case data collection (field work) will be revised jointly with UNICEF in course of project implementation, the quoted rates will be applicable during the revision process.

  - Any additional requirements needed to complete project or that might have an impact on cost or delivery of products

- The consultants would be required to use their own computers, printers, photocopier etc.

It is suggested to submit budget proposal in the following structure that should include more detailed cost disaggregation, as described above:

| Component | Estimated Cost |
| --- | --- |
| Survey design and methodology and overall survey management 1.1 1.2 …etc |  |
| Data collection and processing 2.1. 2.2. …etc |  |
| Data analysis and reporting 3.1 3.2 …etc |  |

All travel costs should be planned properly in the technical proposal and included in the financial proposal. Please note that if selected, the Contractor will arrange (if necessary) all visa formalities. UNICEF will be unable to secure travel visas.

It is essential that:

i) travel cost shall be calculated based on economy class travel, regardless of the length of travel; ii) costs for accommodation, meals and incidentals shall not exceed applicable daily subsistence allowance (DSA) rates, as promulgated by the International Civil Service Commission (ICSC); and iii) Travels and other incidental expenses that were not known ex ante or any additional costs with regards to the travel expenses submitted in the proposal should be justified by the Consultant and accepted by UNICEF before they are incurred. Such expenses may be paid as reimbursable against actual cost incurred , in these cases, necessary documentation shall be submitted with the invoice for reimbursement (e.g. proof of airline ticket purchased).

- TECHNICAL QUALIFICATION CRITERIA

A.	UNICEF is seeking to hire the Contractor, fulfilling the following requirements:

- Duly registered in Ukraine (national or international with representing office in Ukraine).

- Proven experience in conducting survey (not less than three years).  Assessing and/or consultancy on humanitarian response will be considered as an advantage;

- Ability to provide a data collection team in Luhansk and Donetsk oblast (GCA). Data collection team to be present in NGCA will be considered as advantage.

Potential contractors shall provide evidences of their capacity in terms of the above.

B	The Contractor shall provide a minimum leadership team: Survey manager, Sample Specialist, Data Analyst, Data collection manager.

The leadership team should have the following qualifications:

- Advanced university degree (Master or higher), preferably in economics, social studies, statistics or a related field. A combination of relevant academic background and relevant work experience may be accepted in lieu of the advanced university degree;

Ability to produce content to a high standard for deliverables;

- At least three years’ experience in managing studies, surveys, assessments, including experience in an emergency setting (Survey manager).

- Strong analytical skills and qualitative and/or quantitative statistical data processing applications (for Data Analyst);

- Strong survey sample design skills (for Sample Specialist);

- At least three years of experience of managing data collection teams (Data Collection manager);

- Sensitivity towards ethics with regards to humanitarian issues, different cultures, local customs, religious beliefs and practices, personal interaction and gender roles, disability, age and ethnicity.

The proposed team must correspond to the minimum criteria – team composition and minimum experience of the proposed staff. In case of deviation, the offers may be considered technically not compliant.

C. Potential contractors must provide the next information:

  - Basic details

| The full name of organization |  |
| --- | --- |
| Date of foundation |  |
| Address |  |
| Area of interest. |  |
| The total number of staff |  |
| The number of involved personnel (positions), including interviewers |  |
| Description and composition of the field team |  |

- CVs of team members, who will be leading the project: Survey manager, Sample Specialist, Data Analyst, Data collection manager etc.

- The list of company’s implemented projects (surveys, studies) relevant to the topic. The list should include the name of clients; the names of projects; the duration of projects; links to reports if they are publicly available.

- A list of three contacts for references from different projects for the last three years.

- Brief technical approach and methodology according to ToR, including quality assurance (2 pages maximum).

- Workplan (using the template below).

|  | Month | 1 | 2 |
| --- | --- | --- | --- |
| Item | Week | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 |
| 1. | Inception report |  |  |  |  |  |  |  |  |
|  | 1.1 Desk review |  |  |  |  |  |  |  |  |
|  | 1.2 Secondary data mapping |  |  |  |  |  |  |  |  |
|  | 1.3.Draft methodology |  |  |  |  |  |  |  |  |
|  | etc. |  |  |  |  |  |  |  |  |
| 2. | Data collection |  |  |  |  |  |  |  |  |
|  | 2.1 | Secondary data |  |  |  |  |  |  |  |  |
|  | 2.2 | Interviewers |  |  |  |  |  |  |  |  |
|  | 2.3 | FGD |  |  |  |  |  |  |  |  |
|  |  | In-depth interviews |  |  |  |  |  |  |  |  |
|  | etc. |  |  |  |  |  |  |  |  |  |
| 3. | Draft Report |  |  |  |  |  |  |  |  |
|  | 3.1 |  |  |  |  |  |  |  |  |  |
|  | 3.2 |  |  |  |  |  |  |  |  |  |
|  | etc. |  |  |  |  |  |  |  |  |  |
| 4. | Final report |  |  |  |  |  |  |  |  |

D. Technical evaluation of proposals

The Contractor’s team must correspond to the minimum criteria otherwise offers will be considered technically non-compliant.

Proposals will be evaluated technically using the criteria as indicated below.

| Mandatory Requirements (Pre-qualification Criteria) | Yes/No |
| --- | --- |
| Company or organization has valid registration in Ukraine |  |
| Company or organization has a minimum of three years of experience in implementing statistically relevant studies. |  |

|  | MAIN CRITERIA | Points |
| --- | --- | --- |
|  | Organization’s experience in relevant studies, surveys, assessments. The number of studies, surveys, assessments: 5 points. Relevance of studies, surveys or assessments to the ToR: 15 points. Humanitarian experience or working in the Eastern Ukraine – 5 points Experience with UN – 5 points | 30 |
|  | Appropriate methodology and plan of actions according to the ToR: Brief technical approach and methodology, including quality assurance (2 pages) – 30 points Workplan – 10 points | 40 |
|  | Experience of staff that will work on the project Relevance of education – 10 Experience in the relevant studies, assessments - 10 Experience in an emergency setting - 10 | 30 |
|  | Total | 100 |

The Offer is considered technically acceptable (and therefore eligible for opening of financial offers), when it obtains 70 Points out of 100 in course of technical evaluation. The final selection of the Contractor will be based on technical and financial issues with weighing of 70% to the technical proposal and 30% to the financial aspects.

E. Price proposals

Payment is contingent on approval by the Study managers and will be made in three instalments:

- 30% upon submission of Detailed Inception Report (IR) in English;

- 40% upon submission and UNICEF acceptance of the draft of the Study Report in English and Ukrainian;

- 30% upon submission and approval of finalized study report, power point presentation.

The institutions may propose different payment schedules that will be considered during the assessment of the proposal.

Annex 1. Criteria for Ethical Review Checklist

Criteria for Ethical Review Checklist

Does this evidence generation project/programme need to go through an ethical review process?

| Does the project/programme Involve: | Yes | No |
| --- | --- | --- |
| Children as participants, researchers and data collectors? |  | No |
| Specifically targeting persons with an illness, disability, mental health issue or persons in institutions? |  | No |
| Targeting and involving a group that may be perceived as vulnerable within the local context (e.g. women, minority groups, persons with HIV/AIDS, the economically and educationally disadvantaged, persons in institutions, trafficked persons, persons who have or are experiencing violence? |  | No |
| Primary research within humanitarian contexts (that is not routine monitoring/administrative data)? | Yes |  |
| Specifically exploring issues related to violence, abuse or trauma? |  | No |
| Health-based assessments, diagnoses and treatments as part of the evidence generation programme? |  | No |
| Data analysis of restricted access or non-anonymised data of individuals? |  | No |
| Secondary data analysis where the findings may be sensitive? |  | No |
| Merging of databases that will result in personal information becoming identifiable? |  | No |
| The measurement and collection of health-related data, including assessments, diagnoses and the collection of biological samples? |  | No |
| Primary data collection that involves questions on Violence, Abuse, Prostitution, Female Genital Mutilation, Political views, HIV/AIDS, Reproductive, sexual, reproductive and mental health? |  | No |
| Primary data collection that involves questions that may be considered private or sensitive in the local context? |  | No |
| Eliciting opinions for which fear may exist of public disclosure resulting in limitations to future freedoms and access to services? |  | No |
| Randomised Control Trials involving the provision of cash transfers, or other goods and services, to one group and not to another group? |  | No |
| The implementation of MICS within your country? |  | No |

ANNEX 2. List of secondary data:

Reference documents UNCIEF standards:

- UNICEF Office of Research “Taxonomy for Defining and Classifying UNICEF Research, Evaluation & Studies”, September 2014

- Standard Operations Procedures (SOP) for Quality Assurance and Ethical Standards in UNICEF-supported Research, Studies and Evaluations (RSEs) towards Measurable Results for Children in the CEE/CIS Region;

UNICEF Ukraine’s Country Programme Document (2012-2017):

https://www.unicef.org/about/execboard/files/Ukraine_final_approved_2012-2016_20_Oct_2011.pdf

Multiple Indictor Cluster Survey Ukraine 2012

https://datacatalog.worldbank.org/dataset/ukraine-multiple-indicator-cluster-survey-2012

Humanitarian Needs Overview (HNO):

2015: https://www.humanitarianresponse.info/en/operations/ukraine/document/ukraine-humanitarian-needs-overview-hno-2015 ;

2016: https://www.humanitarianresponse.info/en/operations/ukraine/document/ukraine-humanitarian-needs-overview-hno-2016;

2017: https://www.humanitarianresponse.info/en/operations/ukraine/document/ukraine-2017-humanitarian-needs-overview-hno;

2018: https://www.humanitarianresponse.info/en/node/156653

2019:  https://www.humanitarianresponse.info/en/operations/ukraine/document/ukraine-2019-humanitarian-needs-overview-hno

The children of the contact line in Eastern Ukraine

2016: https://reliefweb.int/sites/reliefweb.int/files/resources/children_of_the_contact_line_unicef_2017.pdf

2017: https://www.unicef.org/ukraine/media/451/file/report_1.pdf

Humanitarian Needs Overview 2019 https://www.humanitarianresponse.info/en/operations/ukraine/document/ukraine-2019-humanitarian-needs-overview-hno

MICS 2012 https://datacatalog.worldbank.org/dataset/ukraine-multiple-indicator-cluster-survey-2012