INDIVIDUAL CONSULTANT PROCUREMENT NOTICE

Date:     16/12/2015

Country: Papua New Guinea

Description of the assignment: The UNDAF End of Programme Evaluation will inform the next UNDAF programming cycle by generating evidence and lessons learnt based on the assessment of the current UNDAF outcome and process performance. The evaluation will provide recommendations for the next programme cycle and support greater accountability of the United Nations Country Team in Papua New Guinea to UNDAF stakeholders.

Post: UNDAF Evaluation Team Leader

Project name: UNDAF 2012 – 2017 End of Programme Evaluation

Period of assignment/services (if applicable): The consultancy will be carried out for a maximum of 35 working days from February to April 2016.

Proposal should be submitted by email to registry.pg@undp.org no later than January 15th 2016. Subject line for the email should read: Submission of proposal for UNDAF Evaluation Team Leader.

Any request for clarification must be sent by standard electronic communication to the e-mail indicated above. UNDP will respond by standard electronic mail and will send copies of the response, including an explanation of the query without identifying the source of inquiry, to all consultants.

1. BACKGROUND

The United Nations Development Assistance Framework (UNDAF) is a strategic programme framework that describes the collective response of the UN system to national development priorities. It reflects the comparative advantage of the UN by emphasising the thematic competence of the UN organizations involved, without necessarily highlighting their specific mandates. The current UNDAF PNG, 2012-2017, was signed by the Government of Papua New Guinea (GoPNG) and the UN in 2012. Under the overarching theme of ‘‘Supporting PNG to accelerate MDG Achievement’’, the United Nations Country Team (UNCT) has agreed to focus support in four key outcome areas in the current UNDAF cycle: Governance for Equitable Development Social Justice, Protection and Gender Equality Access to Basic Services Environment, Climate Change and Disaster Risk Management The UNCT in PNG, in collaboration with its GoPNG partners, is currently in the process of preparing an End of Programme UNDAF Evaluation. The evaluation will serve as a major input for the planning process of the next UNDAF and an accountability tool for the delivery of results during the current UNDAF cycle. The evaluation will also help the UNCT position itself in the changing development context of the country, especially with regard to the end of the MDGs and the Post-2015 Development Agenda, as well as national development priorities. This is a joint evaluation being co-managed by the UN and the Department of National Planning and Monitoring. The UNDAF Evaluation will seek to be independent, credible and useful, and will adhere to the highest possible professional standards in evaluation including the United Nations Evaluation Group (UNEG) Evaluation Norms and Standards of Evaluation. The evaluation will be responsive to the needs and priorities of the UN system and GoPNG and engage the participation of a broad range of stakeholders. For further details please see Annex II (UNDAF 2012-2017 End of Programme Evaluation Terms of Reference)

2. SCOPE OF WORK, RESPONSIBILITIES AND DESCRIPTION OF THE PROPOSED ANALYTICAL WORK

Given the country context and strategic position of the UN in PNG, as well as the UN’s Delivering as One approach the UNDAF End of Programme Evaluation will focus on programme relevance, effectiveness and efficiency while also looking at the sustainability of interventions moving into the next UNDAF cycle and the process of mainstreaming the 2030 Agenda for Sustainable Development. While the evaluation will be conducted mainly in Port Moresby, capital of PNG, the Evaluation Team Leader is encouraged to consider including 1-2 field visits in their methodology. The Evaluation Team Leader will work under the supervision of the Evaluation Manager (M&E Specialist, Resident Coordinator’s Office) and the Evaluation Management Group (consisting of a United Nations Country Representative, results based management specialists from the UN and representatives from the Department of National Planning and Monitoring). The Individual Consultant will have overall responsibility for producing a quality assured and timely UNDAF End of Programme Evaluation Report. For further details please see Annex II (UNDAF 2012-2017 End of Programme Evaluation Terms of Reference)

3. REQUIREMENTS FOR EXPERIENCE AND QUALIFICATIONS

The required qualifications and/or experience are presented below: General Qualifications (Team Leader UNDAF Evaluation Expert): Advanced Post-graduate degree (Masters and equivalent) in international relations, political science, international development, gender, governance and public policy, social sciences, evaluation or a related subject. Professional Experience (Team Leader UNDAF Evaluation Expert): A minimum of 10 years’ relevant professional experience in evaluation in developing countries is required. Documented previous experience in managing and leading complex UNDAF evaluations, and a solid understanding on the use of evaluation methodologies. Competencies (Team Leader UNDAF Evaluation Expert): Substantive knowledge of development issues, especially related to the four outcome pillars of the 2012-2017 UNDAF as well as strong understanding of and experience with gender equality, women’s empowerment and human rights as cross-cutting development themes. Specialized experience and/or methodological/technical knowledge, including some specific data collection and analytical skills, particularly in the following areas: understanding of human rights-based approaches to programming; gender considerations; Results Based Management principles; logic modelling/logical framework analysis; quantitative and qualitative data collection and analysis; participatory approaches. Excellent knowledge of the UN system and UN common country programming processes. Demonstrated knowledge of Delivering as One. Knowledge and sensitivity in terms of the political context of Papua New Guinea. Demonstrated capacity in strategic thinking, problem solving and policy advice. Previous experience working in Papua New Guinea or similar settings in the region is an advantage. Strong inter-personal, teamwork and organizational skills. Excellent presentation and drafting, report writing skills, and familiarity with information technology, including proficiency in word processing, spreadsheets, and presentation software. Fluency in written and spoken English is essential. Knowledge of Tok Pisin, or other local languages, is considered an advantage.

4. DOCUMENTS TO BE INCLUDED WHEN SUBMITTING THE PROPOSALS.

Interested individual consultants must submit the following documents/information to demonstrate their qualifications: 1. Proposal: (i) Explaining why they are the most suitable for the work (ii) Provide a detailed methodology and action plan on how they will approach and conduct the work 2. Financial proposal (please see section five) 3. Personal CV including past experience in similar projects and at least 3 references

5. FINANCIAL PROPOSAL

Lump sum contracts: The financial proposal shall specify a total lump sum amount, and payment terms around specific and measurable (qualitative and quantitative) deliverables (i.e. whether payments fall in installments or upon completion of the entire contract). Payments are based upon output, i.e. upon satisfactory delivery of the services specified in the ToR- the payment schedule is described in Annex II (UNDAF Evaluation ToR). In order to assist the requesting unit in the comparison of financial proposals, the financial proposal will include a breakdown of this lump sum amount (including travel, per diems, and number of anticipated working days). Duration and Travel: The consultancy will be carried out for a maximum of 35 working days between February 1st and May 31st 2016. All team members will start and complete the assignment on the same date. In close consultation with the Evaluation Management Group, the International Consultant will organize a maximum of 35 working days into home-based tasks, mission to Port Moresby and field trips outside of Port Moresby. In country working days for the International Consultant are not expected to exceed a maximum of 20 days. All envisaged travel costs must be included in the financial proposal. This includes all travel to join duty station/repatriation travel. In general, UNDP should not accept travel costs exceeding those of an economy class ticket. Should the IC wish to travel on a higher class he/she should do so using their own resources. In the case of unforeseeable travel, payment of travel costs including tickets, lodging and terminal expenses should be agreed upon, between the respective business unit and Individual Consultant, prior to travel and will be reimbursed.

6. EVALUATION

The evaluation of submitted proposals will be based on cumulative analysis (i.e. technical qualifications and price proposal). The weight of the technical criteria is 70%; the weight of the financial proposal is 30%. Candidates that obtain a minimum of 49 pts out of a maximum 70 pts will be considered for the financial evaluation. Candidates that do not meet the minimum requirements will be disqualified. Criteria Maximum Points Technical Criteria Technical Sub-criteria Overall Response Completeness of response. Overall concord between TOR requirements and proposal. 5 5 Maximum Points 10 Company and Key Personnel Experience with the UN and knowledge of the UN reform agenda. Relevant technical work experience. Adequate qualification (advanced graduate degree in relevant discipline). 10 10 10 Maximum Points 30 Proposed Methodology and Approach Soundness of proposed methodology Sequence of activities and timeline well defined and logical. Delivery schedule promises efficient implementation. 10 10 10 Maximum Points 30 Technical Criteria Maximum Points 70 Financial 30 Total Maximum 100

ANNEXES

ANNEX 1- EVALUATION TEAM LEADER TERMS OF REFERENCE (TOR)

ANNEX II- UNDAF END OF PROGRAMME EVALUATION TOR

ANNEX III- INDIVIDUAL CONSULTANT GENERAL TERMS AND CONDITIONS

ANNEX I                                 Terms of Reference

Consultancy: UNDAF Evaluation Team Leader

| Location: | Port Moresby, capital of Papua New Guinea with travel to the districts if/when required. |
| --- | --- |
| Application Deadline: | January 15 |
| Additional Category: | UNDAF Evaluation |
| Type of Contract: | Individual Consultant |
| Project: | UNDAF 2012-2017 End of Programme Evaluation |
| Languages Required: | English |
| Starting Date: | February 1st |
| Duration of Initial Contract: | Maximum of 35 Working Days |

Background

The UN Country Programme (UNCP) in Papua New Guinea is a ‘self-starter’ for the Delivering as One (DaO) approach, since 2006. This approach has been built on the key elements of results-based management (RBM) such as a focus on performance management, alignment of the UNCP Results and Monitoring and Evaluation Frameworks with national policy, strategic documents and planning frameworks, and building on the comparative advantage of the UNCT’s strategic position in Papua New Guinea (PNG). In line with this approach the current United Nations Development Assistance Framework (UNDAF) cycle outlines the strategic programme framework for the UN in PNG and is accompanied by an UNDAF Action Plan that operationalising the UNDAF strengthening partnership between the UN system and the Government of Papua New Guinea (GoPNG).

The Millennium Development Goals (MDGs) provided the basis for the UN’s strategic positioning and support to national development plans while the UNDAF Action Plan introduced new ways of providing assistance in line with ongoing UN Reform as well as the Paris Declaration on Aid Effectiveness and the Accra Agenda for Action. Both the UNDAF and Action Plan aim to simplify and harmonize the UN’s contribution to national development, ensure alignment with GoPNG priorities and to utilize national systems and procedures for programme delivery to reduce transaction costs.

The current UNDAF and Action Plan were originally planned to be for a four year period (2012-2015). However, following a GoPNG request, the UN extended the UNDAF for a further two years (from 2015 to 2017). The agreement to extend the UNDAF was in order to align with GoPNG’s Medium Term Development Plan (MTDP) 2 2016-2017. Upon agreeing to extend the current UNDAF cycle in 2014 the UN team, together with a representative from PNG’s Department of National Planning and Monitoring (DNPM), reviewed progress against the existing UNDAF and made some changes to the plans and expected outputs, which remain closely aligned to GoPNG priorities for the period up to 2017.

The UNDAF was themed as ‘Supporting PNG to accelerate MDG Achievement’ and the following development pillars were identified and agreed upon by the UN and GoPNG as priority outcome areas in support of the GoPNG’s MTDP Plan 2011-2015:

1. Governance for Equitable Development

2. Social Justice, Protection and Gender Equality

3. Access to Basic Services

4. Environment, Climate Change and Disaster Risk Management

The key strategies underpinning the UNDAF are capacity development, the promotion of human rights and the application of a human rights-based approach to programming, the empowerment and strengthening of civil society, promotion of evidence-based monitoring systems, mainstreaming of gender equality and opportunities for women, and fighting HIV and AIDS and other communicable diseases.

The United Nations Country Team in PNG, in collaboration with its GoPNG partners, is currently in the process of preparing an End of Programme UNDAF Evaluation, which will serve as a major input for the planning process of the next UNDAF cycle and an accountability tool for the delivery of results during the current UNDAF cycle. This is a joint evaluation being co-managed by the UN and DNPM.

The UNDAF evaluation will seek to be independent, credible and useful, and will adhere to the highest possible professional standards in evaluation including the United Nations Evaluation Group (UNEG) Evaluation Norms and Standards of Evaluation. The evaluation will be responsive to the needs and priorities of the UN system and GoPNG and engage the participation of a broad range of stakeholders.

A short-term Evaluation Team composed of an Evaluation Team Leader, Evaluation Specialist and National Evaluation Consultant is therefore to be deployed to conduct an independent, evidence based evaluation of the 2012-2017 UNDAF as per the UNDAF End of Programme Evaluation Terms of Reference.

Duties and Responsibilities

Under the general supervision of the UN Resident Coordinator, delegated, on a daily basis, to the Evaluation Manager (M&E Specialist- Resident Coordinator’s Office) and in close cooperation with the Evaluation Management Group (consisting of UN and Department of National Planning and Monitoring representatives), the consultant- taking due consideration of the relevant United Nations Evaluation Group (UNEG) Norms and Standards of Evaluation- shall have overall responsibility for conducting and managing the evaluation and producing the deliverables outlined in the ToR:

- Overall coordination and management of the Evaluation Team to deliver on the expected outputs;

- Lead the evaluation process in a timely manner;

- Lead the development of a prioritized and sequenced the inception report including harmonized evaluation plan outlining methodology and timeline;

- Identify additional support needs that may be required for conducting the evaluation;

- Lead the Evaluation Team in conducting a thorough desk review;

- Lead the Evaluation Team in conducting field visits to the project sites identified and collect data;

- Lead the Evaluation Team in conducting key informant interviews, focus group discussion, surveys, questionnaires etc. for data collection as needed;

- Produce the UNDAF evaluation draft and final reports, responsible for quality assurance and timely submission of the report to the EMG, UN RC office and the UNCT;

- Lead the Evaluation Team in conducting stakeholder consultations including, a validation workshop followed by presenting the UNDAF evaluation results and ways forward upon submission and approval of the final report; and

- Ensure a gender-sensitive, as well as human-rights based approach.

Management and coordination of the Evaluation Team will be delivered in line with the parameters set out in the UNDAF evaluation ToR and the Evaluation Team’s inception report, including harmonized evaluation plan. The Evaluation Team Leader is responsible for quality assurance of the work of Evaluation Team members and ensuring strict adherence to the UNEG Norms and Standards of Evaluation. Payment of the Team Leader is based on the delivery of outputs quality assured and accepted outputs as described in the evaluation ToR.

The Evaluation Team leader will work in close collaboration with the Evaluation Manager and Evaluation Management Group in focusing the evaluation on lessons learned for the next UNDAF cycle, potential approaches and entry points for mainstreaming the Sustainable Development Goals into the next UNDAF and assessing the relevance and contribution of the UNDAF 2012-2017 to national development results.

Deliverables:

- Inception report- The Evaluation Team will collect data using the proposed methodologies: desk review, observation, interviews and focus group discussions including participation of relevant stakeholders within DaO. The Evaluation Team will develop a full methodology and survey instruments and an Evaluation Plan as part of the Inception Report which will include a stakeholder stake map, the final list of evaluation questions, the evaluation matrix, the overall evaluation design and methodology, a detailed description of the data collection plan for the field phase, and a description of the roles and responsibilities of the individual team members.

- A PowerPoint presentation highlighting the main components of the final inception report, reflecting the comments provided by the EMG and key stakeholders, to be presented to the EMG and the UNCT.

- A PowerPoint presentation and stakeholder meeting to share and explain findings to stakeholders after data collection phase has ended.

- Draft UNDAF End of Programme Evaluation Report. The Evaluation Team will write a draft UNDAF report and a proposed action plan for implementation of evaluation recommendations (ANNEX 5), keeping in mind the proposed structure of the final UNDAF report (ANNEX 2) distributing to members of the EMG for review and comments. The revised draft report shall thereafter be submitted to the UNCT and Steering Committee with a validation workshop being held to validate the preliminary findings and recommendations.

- Final UNDAF End of Programme Evaluation Report. The final report should be based on two rounds of commenting on draft evaluation reports, taking into account potential comments from the Steering Committee, EMG and the UNCT. The final version will be submitted in English to the UN Country Team and Steering Committee through the Resident Coordinator for review by the Steering Committee. It will include a set of clear, forward-looking and actionable recommendations logically linked to the findings and conclusions, and identify lessons learnt to improve the strategies, implementation mechanism, and management of the next UNDAF as well as a proposed Action Plan for the next programme cycle. There will be clear guidance provided on mainstreaming the SDGs into the next UNDAF cycle.

Competencies

- Substantive knowledge of development issues, especially related to the four outcome pillars of the 2012-2017 UNDAF as well as strong understanding of and experience with gender equality, women’s empowerment and human rights as cross-cutting development themes.

- Specialized experience and/or methodological/technical knowledge, including some specific data collection and analytical skills, particularly in the following areas: understanding of human rights-based approaches to programming; gender considerations; Results Based Management (RBM) principles; logic modelling/logical framework analysis; quantitative and qualitative data collection and analysis; participatory approaches.

- Excellent knowledge of the UN system and UN common country programming processes

- Demonstrated knowledge of Delivering as One

- Challenges and sensitivity in terms of the political context of Papua New Guinea.

- Demonstrated capacity in strategic thinking, problem solving and policy advice.

- Previous experience working in Papua New Guinea or similar settings in the region is an advantage.

- Strong inter-personal, teamwork and organizational skills.

- Excellent presentation and drafting, report writing skills, and familiarity with information technology, including proficiency in word processing, spreadsheets, and presentation software.

- Fluency in written and spoken English is essential.

- Knowledge of Tok Pisin, or other local languages, is considered an advantage.

Required Skills and Expertise

- The successful candidate will have an Advanced Post-graduate degree (Masters and equivalent) in one of the following disciplines: international relations, political science, international development, governance and public policy, social sciences, evaluation or a related subject.

- A minimum of ten years of functionally-related professional evaluation experience including documented previous experience in managing and leading complex UNDAF evaluations.

- Strong knowledge, understanding and experience in integrating gender sensitive and human rights based approaches into evaluations.

ANNEX II

United Nations Development Assistance Framework (UNDAF) 2012-2017 End of programme Evaluation

December 2015

United Nations in Papua New Guinea

Terms of Reference

UNDAF End of Programme Evaluation

United Nations Papua New Guinea - Delivering as One

I. BACKGROUND

1.1 Development Context

Papua New Guinea (PNG) achieved independence from Australia in 1975 and is home to 7,275,324 million people according to the 2011 National Population and Housing Census. This figure was a 40% increase from the population count captured in the 2000 Census. PNG has experienced strong GDP growth since 2010 however the 2014 National Human Development Report (NHDR) notes that ‘there is a widespread perception within the country that the extractive-based form of development has not been inclusive or reached as many Papua New Guineans as it could and should have’. In 2014 PNG was ranked 157th out of 187 countries in the Human Development Index placing in the low human development category- this represents a fall of four places from the 153 rank achieved in 2011.

The country faces a range of complex challenges including service delivery to a diverse, dispersed and mostly rural population spread over 600 islands, poor accessibility to parts of the country, high logistical costs and supply management difficulty. In 2012 only 7 per cent of the population had access to the electric grid and reticulated water, and two-fifths of health/sub-health centres and rural health posts had no electricity or essential medical equipment.

Another challenge faced by the Government of Papua New Guinea (GoPNG) and development partners is the relatively high level of crime and violence in PNG contributing to a high cost of security overheads. In addition to these costs the high rate of crime, including domestic violence, has a long-term social impact constraining mobility and negatively impacting development interventions. The country has also faced periods of political instability including the 2011-2012 constitutional crisis.

PNG has a high level of decentralisation with 22 provinces, 89 districts, 313 Local Level Governments (LLGs) and 6,131 Wards. In May 2012 two new provinces officially came into existence, the Hela Province and the Jiwaka Province continuing the general trend in PNG towards increased financial devolution to provinces, districts and LLGs. The NHDR notes that with the recent trend towards decentralisation ‘central government policy making and fiscal control remains strong while implementation and service delivery is limited by weak capacity among both line government agencies and the sub-national service providers. This has led to inefficiencies in the public service, including corruption’.

There are 15 resident UN Agencies, Funds and Programmes (AFPs) operating in PNG of varying sizes each with a specific mandate, capacity and role to play in the development process. During the preparation stage of the UNDAF (2012-2017) the UN Country Team (UNCT) in PNG identified dramatic increases in operational costs as a threat to programme delivery. To mitigate this potential impediment the UNCT developed an operational strategy that focuses on a dual approach of resource mobilisation and reducing operational overheads.

1.2. The Papua New Guinea UNDAF 2012- 2017

The UN Country Programme (UNCP) in Papua New Guinea is a ‘self-starter’ for the Delivering as One (DaO) approach, since 2006. This approach has been built on the key elements of results-based management (RBM) such as a focus on performance management, alignment of the UNCP Results and Monitoring and Evaluation Frameworks with national policy, strategic documents and planning frameworks, and building on the comparative advantage of the UNCT’s strategic position in PNG. In line with this approach the current UNDAF cycle outlines the strategic programme framework for the UN in PNG and is accompanied by an UNDAF Action Plan that operationalising the UNDAF strengthening partnership between the UN system and GoPNG.

The Millennium Development Goals (MDGs) provided the basis for the UN’s strategic positioning and support to national development plans while the UNDAF Action Plan introduced new ways of providing assistance in line with ongoing UN Reform as well as the Paris Declaration on Aid Effectiveness and the Accra Agenda for Action. Both the UNDAF and Action Plan aim to simplify and harmonize the UN’s contribution to national development, ensure alignment with GoPNG priorities and to utilize national systems and procedures for programme delivery to reduce transaction costs.

The current UNDAF and Action Plan were originally planned to be for a four year period (2012-2015). However, following a GoPNG request, the UN extended the UNDAF for a further two years (from 2015 to 2017). The agreement to extend the UNDAF was in order to align with GoPNG’s Medium Term Development Plan (MTDP) 2 2016-2017. Upon agreeing to extend the current UNDAF cycle in 2014 the UN team, together with a representative from PNG’s Department of National Planning and Monitoring (DNPM), reviewed progress against the existing UNDAF and made some changes to the plans and expected outputs, which remain closely aligned to GoPNG priorities for the period up to 2017.

The UNDAF was themed as ‘Supporting PNG to accelerate MDG Achievement’ and the following development pillars were identified and agreed upon by the UN and GoPNG as priority outcome areas in support of the GoPNG’s MTDP Plan 2011-2015:

1. Governance for Equitable Development

2. Social Justice, Protection and Gender Equality

3. Access to Basic Services

4. Environment, Climate Change and Disaster Risk Management

The key strategies underpinning the UNDAF are capacity development, the promotion of human rights and the application of a human rights-based approach to programming, the empowerment and strengthening of civil society, promotion of evidence-based monitoring systems, mainstreaming of gender equality and opportunities for women, and fighting HIV and AIDS and other communicable diseases.

1.3 UNDAF End of Programme Evaluation in the context of Papua New Guinea

The UNCT PNG, in collaboration with its GoPNG partners is currently in the process of preparing an End of Programme UNDAF Evaluation, which will serve as a major input for the planning process of the next UNDAF and an accountability tool for the delivery of results during the current UNDAF cycle. This is a joint evaluation being co-managed by the UN and DNPM.

The UNDAF Evaluation will seek to be independent, credible and useful, and will adhere to the highest possible professional standards in evaluation including the United Nations Evaluation Group (UNEG) Evaluation Norms and Standards of Evaluation. The evaluation will be responsive to the needs and priorities of the UN system and GoPNG and engage the participation of a broad range of stakeholders.

II. EVALUATION PURPOSE, OBJECTIVES AND SCOPE

2.1 Purpose

The UNDAF End of Programme Evaluation will be completed by May 2016 so as to inform the next programme cycle by generating evidence and lessons learnt based on the assessment of the current performance of the UNDAF outcomes and process. The evaluation will determine how the UNDAF helped UN agencies to contribute more effectively and efficiently to national development efforts, including aligning with GoPNG priorities and strategies and shaping the development agenda. The purpose of the evaluation is twofold, it is a learning tool informing future programming and will also support greater accountability of the UNCT to UNDAF stakeholders.

The primary users of the evaluation will be the UNDAF partners, i.e. the UNCT, GoPNG, donors and partners who support the programmes. The timing of this evaluation is crucial in feeding into the preparation and planning phase for the next UNDAF cycle which is scheduled to commence in the final quarter of 2016.

2.2 Objectives

The objectives of the UNDAF Evaluation are:

- To assess the relevance and contribution of the UNDAF to national development results and MDG achievement given the PNG context.

- To identify the factors that have affected the UNCT's contribution and assess how the UNDAF has been implemented, answering the question of why the performance is as it is and explaining the enabling factors and bottlenecks supporting greater accountability to UNDAF stakeholders.

- To generate a set of clear, forward-looking and actionable recommendations logically linked to the findings and conclusions. These recommendations will include specific guidance on how to implement, monitor and evaluate the Sustainable Development Goals (SDGs) in the next UNDAF cycle.

2.3 Scope and Key Questions

Given the context described above, the UNDAF End of Programme Evaluation will focus on programme relevance, effectiveness and efficiency while also looking at the sustainability of interventions moving into the next UNDAF cycle and the process of mainstreaming the 2030 Agenda for Sustainable Development.

While the evaluation will be conducted mainly in Port Moresby, capital of PNG, the Evaluation Team is encouraged to consider including 1-2 field visits in their methodology. When choosing sites to visit, the Evaluation Team should consider the availability of baseline data for these sites, and make the choice of the locations to visit based on the implementation of relevant UN programmes in these areas. The proposed field visits should be presented in the inception report, and should be discussed with the Evaluation Management Group (EMG).

The evaluation will examine the following areas:

- Relevance of the UNDAF in relation to the issues it was designed to address as well as their underlying causes in the context of national policies and strategies:

- Do the UNDAF outcomes address key issues, their underlying causes, and challenges identified by GoPNG strategic plans and priorities?

- To what extent has the UNDAF results matrix been sufficiently flexible to adjust to evolving national policies and strategies (e.g. National Development Plans and Goals, legislative reforms) and changing development circumstances during the current programme cycle?

- To what extent have the UNDAF outcomes been relevant to internationally agreed goals and commitments guiding the work of UN AFPs?

- To what extent have human rights principles and standards been reflected or promoted in the UNDAF?

- How can the next the planning phase for the next UNDAF cycle best incorporate the SDGs to ensure that the post 2015 development agenda is fully reflected?

- To what extent and in what ways are the concepts of gender equity and equality and other cross-cutting issues reflected in programming? Were specific goals and targets set and if so have they been met?

- Assess the effectiveness of UNDAF implementation and performance in terms of progress towards agreed UNDAF outcomes. Identify lessons learnt for future programming, particularly how the UN can best contribute to mainstreaming and localising the 2030 Sustainable Development Agenda:

- What progress has been made towards the realization of UNDAF outcomes as a contribution to the achievement of National Priorities and the MDGs? What lessons learnt can be identified and used to guide planning for mainstreaming and localising the SDGs in the next UNDAF programme cycle?

- What are the main factors that contributed to the realization or non-realization of the outcomes?

- Were expected outcomes realistic given the UNDAF timeframe, AFPs’ capacities and resources?

- To what extent and in what ways have the comparative advantages of the UN organizations been utilized in the national context and contributed to streamlining the work of the UN in PNG?

- Assess the efficiency of the UNDAF as a coordination and partnership framework:

- To what extent and in what ways has the UNDAF contributed to achieving better synergies among the programmes of UN AFPs?

- To what extent the effectiveness of programme support by individual AFPs been enhanced as a result of joint programming?

- Is the distribution of roles and responsibilities among the different UNDAF partners well defined, facilitated in the achievement of results and have the arrangements been respected in the course of implementation?

- Have the external and internal structures for programme delivery facilitated the efficient and effective delivery of UNDAF results and reduced duplication?

- Are the funding allocations, task team budgets and overall expenditures aligned with the stated UNDAF priorities and sufficiently targeted to maximise efficiency?

- To the extent possible, assess the medium term impact of UNDAF on the lives of the poor, vulnerable and marginalized in PNG, notably in the realization of MDGs and MTDP:

- Determine whether there is any major change in UNDAF and national development indicators that can reasonably be attributed to or be associated with UNDAF implementation.

- Identify the contribution the UNDAF has made to working with key strategic partners in reaching the poor, vulnerable and marginalized through UNDAF implementation.

- Based on the human rights and gender equality principles applied during UNDAF implementation what observable or measurable impact has the UNDAF had on human rights and gender equality in PNG to date?

- Analyse to what extent results achieved and strategies used by the UNDAF are sustainable (i) as a contribution to national development and (ii) in terms of the added value of UNDAF for cooperation among individual AFPs:

- To what extent and in what way have national capacities been enhanced in government, civil society and NGOs in order to enable these actors to continue achieving positive results without the UN/development partners’ support?

- To what extent has institution-building and institution-strengthening taken place in human rights and gender equality terms?

- Have complementarities, collaboration and /or synergies fostered by UNDAF contributed to greater sustainability of results of Donors intervention in the country?

- Does the UNDAF respond to the challenges of national capacity development and promote ownership of programmes?

III. PROPOSED EVALUATION METHODOLOGY AND PROCESS

The UNDAF End of Programme Evaluation will utilise a mixed method approach and be carried out in accordance with UNEG Evaluation Norms and Standards of Evaluation and Ethical Standards as well as OECD/DAC evaluation principles and guidelines and fully compliant with the UNEG Quality Checklist for Evaluation Reports. The evaluation will be conducted in close collaboration with the UN Resident Coordinator’s Office (RCO), UNCT, EMG, the UN’s RBM Committee, the United Nations Evaluation Development Group for Asia and the Pacific (UNEDAP) and national counterparts.

3.1. Methodology

Once the Evaluation Team members for the UNDAF Evaluation have been selected, during the inception phase, a thorough preparatory work should be conducted by the team members, including a comprehensive desk review, to define their specific evaluation approach, data collection methods and required evaluation tools. A Harmonized Evaluation Plan will be developed accordingly including qualitative and quantitative methods to evaluate the UNDAF implementation and performance and to make recommendations informing the next programming cycle.

3.2 Data Collection

The UNDAF End of Programme Evaluation will be carried out through a wide participation of all relevant stakeholders including the UN and its thematic task teams, GoPNG institutions, CSOs as well as development partners and beneficiaries. Field visits to selected project sites and briefing and debriefing sessions with UN and GoPNG officials, development partners, and civil society are envisaged.

In order to use existing information and avoid duplication, secondary data will be mainly collected from various data sources including a comprehensive desk review and analysis of relevant documents as well as triangulation of different studies. Data is to be presented/disaggregated (by sex, age and location), where possible. Primary data will also be collected from stakeholder key informant interviews, discussions, field visits and consultative processes. At the beginning of the field mission, the Evaluation Team will present the inception report and seek agreement on the evaluation methodology.

3.3 Processes

The evaluation will be conducted in three phases:

Phase 1- Preparation:

- Collection of reference material: The UN RCO, in close consultations with the RBM Committee, will compile a list of background materials, documents, and reports relevant to the UNDAF Evaluation.

- Identification and selection of consultants: The UNCT will jointly identify and select the appropriate consultants for the UNDAF Evaluation Team. The UN RCO will take the lead, jointly with the EMG, in soliciting CVs of available consultants.

- Development of evaluation strategy and design: Prior to the main data collection phase, the UNDAF Evaluation Team Leader will assess the availability of evaluative evidence, and develop an operational plan (a ‘Harmonized Evaluation Plan’), which will include a design matrix, data collection and analysis methods and potential sites for field visits.

Phase 2 – Conduct of data collection activities and the preparation of the evaluation reports:

- Desk review of reference material: All Evaluation Team members are responsible for reviewing the reference documents, reports and any other data and information provided by the RCO.

- Main data collection mission: The Evaluation Team will conduct data collection activities as guided by the Harmonized Evaluation Plan. The team will conduct agreed-upon interviews with stakeholders, surveys, questionnaires and site visits etc. facilitated by the EMG.

- Data analysis and reporting: The Evaluation Team will conduct further data analysis based on all information collected, and present the preliminary findings to stakeholders prior to preparing a draft evaluation report. The UNDAF Evaluation Team will write and submit the draft report to the UNCT. The UNDAF Report will be written in accordance with it respective Terms of Reference, the Harmonized Evaluation Plan and other established guidance documents.

- Review of the draft report and finalisation of the report: the draft UNDAF Report will be submitted to key stakeholders for factual correction and feedback. The Evaluation Team Leader, in consultation with the UNCT, will prepare a comment matrix to indicate how the comments were taken into account, and together with the team of consultants, will finalise the UNDAF Evaluation Report. Stakeholder workshops: A meeting with the key stakeholders will be organized in the country, to present the UNDAF Evaluation results and discuss ways forward. UNCT to prepare a Management Response.

Phase 3 - Follow-up:

The UNCT together with the RCO will conduct follow-up activities, as guided by their respective processes and mandates. In the context of the UNDAF Evaluation:

- Organization of a stakeholders’ meeting/workshop to validate and refine findings, conclusions and recommendations, discuss dissemination and communication strategies and plan for implementation of evaluation recommendations.  The follow-up plan should determine a process for ensuring that lessons learnt are incorporated into the next UNDAF programming cycle.

- Dissemination of the evaluation findings and recommendations.

- Implementation of a follow-up plan, in particular focusing on the design of a new UNDAF cycle.

IV. TEAM STRUCTURE FOR THE UNDAF EVALUATION

The UNDAF Evaluation Team will be led by the UNDAF Evaluation Team Leader (UNDAF Evaluation Expert) and consist of the Team Leader plus a National Evaluation Specialist and National Evaluation Consultant. The Evaluation Team Leader will be an international position and all consultants will be mobilized through the individual contracting modality. The Evaluation Team will demonstrate a high level of capacity and experience with evaluations in the UN context, as well as knowledge and understanding of the four UNDAF outcome pillars and development context of PNG. The Evaluation Team Leader is tasked with managing and ensuring the quality of the work conducted by Evaluation Team members and has ultimate responsibility for delivering results- they will be responsible for the quality and timeliness of all deliverables and guide and supervise the National Evaluation Specialist and National Evaluation Consultant. Payment of Evaluation Team members is subject to validation of the quality and timeliness of their work by the Evaluation Team Leader.

All consultants shall be charged with incorporating human rights and gender equality assessments into their relevant portfolios. The selected consultants are expected to be independent and should not have been involved in the implementation of the UNDAF (2012-2017) in any of the UN agencies. See ANNEX 4 for outline of required expertise and qualifications of the Evaluation Team.

V. DELIVERABLES

- Inception report- The Evaluation Team will collect data using the proposed methodologies: surveys, questionnaires, desk review, observation, interviews and focus group discussions including participation of relevant stakeholders within DaO etc. The Evaluation Team will develop a full methodology and survey instruments and an Evaluation Plan as part of the Inception Report which will include a stakeholder stake map, the final list of evaluation questions, the evaluation matrix, the overall evaluation design and methodology, a detailed description of the data collection plan for the field phase, and a description of the roles and responsibilities of the individual team members.

- A PowerPoint presentation highlighting the main components of the final inception report, reflecting the comments provided by the EMG and key stakeholders, to be presented to the EMG and the UNCT.

- A PowerPoint presentation and stakeholder meeting to share and explain findings to stakeholders after data collection phase has ended.

- Draft UNDAF End of Programme Evaluation Report. The Evaluation Team will write a draft UNDAF report and a proposed action plan for implementation of evaluation recommendations (ANNEX 5), keeping in mind the proposed structure of the final UNDAF report (ANNEX 2) distributing to members of the EMG for review and comments. The revised draft report shall thereafter be submitted to the UNCT and Steering Committee with a validation workshop being held to validate the preliminary findings and recommendations.

- Final UNDAF End of Programme Evaluation Report. The final report should be based on two rounds of commenting on draft evaluation reports, taking into account potential comments from the Steering Committee, EMG and the UNCT. The final version will be submitted in English to the UN Country Team and Steering Committee through the Resident Coordinator for review by the Steering Committee. It will include a set of clear, forward-looking and actionable recommendations logically linked to the findings and conclusions, and identify lessons learnt to improve the strategies, implementation mechanism, and management of the next UNDAF as well as a proposed Action Plan for the next programme cycle. There will be clear guidance provided on mainstreaming the SDGs into the next UNDAF cycle.

VI. ESTIMATED BUDGET

International Consultant						US$

National Consultant(s)							US$

Internal Travel*								US$

Validation Workshop*							US$

Total Budget								US$

* Please note that internal travel and meetings/workshops/stakeholder consultations costings will not be required as these will be calculated according to the experiences of the UN in PNG. Outline proposed meetings, field visits and workshops including number of participants etc. and the costing will be worked out on a basis applicable to all received proposals.

The costs of the UNDAF evaluation will be covered by UNCT’s budget and payment of fees will be based on the delivery of outputs, as follows:

- Upon selection and signing of contract: 10%

- Upon satisfactory submission of the inception report: 10%

- Upon satisfactory submission of the draft evaluation report: 30%

- Upon satisfactory submission of the final evaluation report:  50%

UNDAF Evaluation ToR’s | Annexes I - VI

ANNEX 1: Management, Roles and Responsibilities

| Who: Actors and Accountability | What: Roles and Responsibilities |
| --- | --- |
| Steering Committee | Commission and oversee the evaluation. Ensure decisions are made on time. Provide the overall, high level, oversight and approval of the Evaluation process, findings, recommendations and all key deliverables. Develop a follow-up plan and management response to the evaluation and ensure the implementation of committed actions. |
| RC Office | Facilitate solicitation, selection and recruitment of the Evaluation Team members. Establish the Evaluation Management Group. Day-to-day management, in close coordination with the EMG (through Evaluation Manager). Ensure close communication with the Evaluation Team during the whole evaluation process. Facilitate communication between the Evaluation Team and the SC/UNCT/EMG Help arrange the travel to the project site and other logistic issues. Consolidate the feedback on the UNDAF Evaluation reports, and with the Team Leader in a timely manner. Facilitate dissemination of evaluation reports to stakeholders. |
| Evaluation Management Group | Prepare ToR for the evaluation. Rate and shortlist CVs choosing Evaluation Team. Contribute to the final selection of evaluation questions. Participate in the review of the evaluation methodology and provide comments to the Evaluation Team. Help identify the projects to be visited. Facilitate access of the Evaluation Team to information sources (documents and interviewees) to support data collection. Provide technical inputs, comments and quality assurance on the main deliverables of the evaluation, including the design, draft, and final reports. Clarify questions raised during the evaluation. Monitor the progress of the evaluation and report progress to UNCT. Safeguard the independence of the evaluation exercise and advise on the quality of the work done by the Evaluation Team. Assist in the integration of the findings, conclusions and recommendations of the evaluation into future programme design and implementation. Approve final report. Support the UNCT in the development of a management response. |
| United Nations Evaluation Development Group for Asia and the Pacific | Provide quality assurance support on evaluation process and tangible deliverables and products. Provide expertise and guidance as requested by the EMG. Support the use of global norms and standards in Asia and the Pacific and promote networking on evaluation as a profession across the region. |
| Evaluation Team | Have overall responsibility for producing the UNDAF Evaluation Report and for quality and timely submission of the same Report to the UN RC Office and UNCT. Lead the evaluation process in a timely manner. Produce the inception report including Harmonized Evaluation Plan outlining methodology and timeline. Agree final methodology and evaluation focus in consultation with EMG. Communicate with UN whenever it is needed, particularly the EMG on a regular basis highlighting progress made/challenges encountered. Conduct thorough desk review. Conduct field visits to the project sites identified and collect data. Conduct key informant interviews, focus group discussion etc. for data collection as needed. Conduct stakeholder consultations including validation workshop followed by presenting the UNDAF Evaluation results and ways forward upon submission and approval of the final report. Responsible for producing the UNDAF Evaluation draft and final reports and for quality and timely submission of the report to the EMG, UN RC office and the UNCT. |

ANNEX 2: Structure of the UNDAF Report

Title page

Name of programme or theme being evaluated

Country of project/programme or theme

Name of the organization to which the report is submitted

Names and affiliations of the evaluators

Date

Table of Contents

List of acronyms

Executive summary

- A self-contained paper of 1-3 pages.

- Summarize essential information on the subject being evaluated, the purpose and objectives of the UNDAF End of Programme Evaluation methods applied and major limitations, the most important findings, conclusions and recommendations in priority order. (Maximum 5 pages)

(Main Report; Maximum 35 pages)

Introduction

- (Context and national priorities, goals, and methodology, brief description of the results)

- Describe the project/programme/theme being evaluated. This includes the problems that the interventions are addressing; the aims, strategies, scope and cost of the intervention; its key stakeholders and their roles in implementing the intervention.

- Summarize the UNDAF purpose, objectives, and key questions. Explain the rationale for selection/non selection of evaluation criteria.

- Describe the methodology employed to conduct the UNDAF End of Programme Evaluation and its limitations if any.

- Detail who was involved in conducting the UNDAF End of Programme Evaluation and what were their roles.

- Describe the structure of the UNDAF End of Programme Evaluation report.

- A Reflection on the main findings which considers: (a) the results of the desk review of existing documentation available, and (b) the interviews conducted with Heads of UN Agencies, selected senior programme staff, and selected senior Government officials.

- Results by UNDAF Outcome: national progress, specific contribution of UN agencies and resources mobilized etc.

Partnership and collaboration strategy among UNCT and other donors; and evaluation of the efficiency and effectiveness of UNDAF as a partnership framework

Major Challenges

UNDAF Financial Management

Assessment of M&E process

Findings and conclusions

- State findings based on the evidence derived from the information collected. Assess the degree to which the intervention design is applying results based management principles and human rights based approach. In providing a critical assessment of performance, analyse the linkages between inputs, activities, outputs, outcomes and if possible impact. To the extent possible measure achievement of results in quantitative and qualitative terms. Analyse factors that affected performance as well as unintended effects, both positive and negative. Discuss the relative contributions of stakeholders to achievement of results. Assess how/if the intervention has contributed to gender equality and fulfilment of human rights.

- Conclusions should be substantiated by the findings and be consistent with the data collected.  They must relate to the UNDAF objectives and provide answers to the evaluation questions.  They should also include a discussion of the reasons for successes and failures, especially the constraints and enabling factors.

Recommendations and lessons learnt

- Based on the findings and drawing from the evaluator(s)’ overall experience in other contexts if possible provide lessons learned that may be applicable in other situations as well. Include both positive and negative lessons.

- Formulate relevant, specific and realistic recommendations that are based on the evidence gathered, conclusions made and lessons learned.  Discuss their anticipated implications. Consult key stakeholders when developing the recommendations.

- List proposals for action to be taken (short and long-term) by the person(s), unit or organization responsible for follow-up in priority order. Maximum of ten recommendation points.

Follow up Plan

- This may include current UNDAF

- Next UNDAF

- Provide suggested time lines and cost estimates (where relevant) for implementation.

Annexes may include the following (maximum 10-15 pages)

- Attach ToR (for the UNDAF End of Programme Evaluation).

- List persons interviewed, sites visited.

- List documents reviewed (reports, publications).

- Data collection instruments (e.g. copies of questionnaires, surveys, etc.).

  - Assessment of the progress by outcomes in relevance to the nationally defined goals.

  - Photos

  - Stories worth telling (Most Significant changes [MSC])

  - List of used documents and persons met.

*The UNDAF Evaluation Report should be developed in accordance with the UNEG “Standards for Evaluation in the UN system”, “Norms for Evaluation in UN System and “Ethical Guidelines for Evaluation.” Analysis should include an appropriate discussion of the relative contributions of stakeholders to results. It will consider the evaluation objectives as per relevance, effectiveness, efficiency, impact and sustainability of results, as well as the key issues of design, focus and comparative advantage.

ANNEX 3: Recommended List of Documents

- Papua New Guinea Medium Term Development Plan 2 2016-2017

http://www.planning.gov.pg/images/pdf/MTDP2.pdf

- Papua New Guinea Development Strategic Plan 2010-2030

http://www.health.gov.pg/publications/PNGDSP_Final%20Version%20for%20Print.pdf

- Papua New Guinea Vision 2050

http://www.treasury.gov.pg/html/publications/files/pub_files/2011/2011.png.vision.2050.pdf

- The Alotau Accord 2012

http://dfat.gov.au/about-us/publications/Documents/papua-new-guinea-alotau-accord-summary-oneill-gov-priorities.pdf

- Papua New Guinea National HIV & AIDS Strategy 2011-2015

http://www.nacs.org.pg/attachments/article/74/PNG_NHS_Implementation.pdf

- Papua New Guinea National Health Plan, 2011-2020

http://www.wpro.who.int/papuanewguinea/areas/papua_new_guinea_nationalhealthplan.pdf

- Papua New Guinea National Strategy for Sustainable Development 2nd Edition

http://www.planning.gov.pg/images/pdf/StaRS.pdf

- UN Annual Progress Reports and individual agency Annual Reports (2012-2015)

http://mptf.undp.org/factsheet/fund/PG100

Annual Progress Report 2014

Annual Progress Report 2013

Annual Progress Report 2012

- UNEG Evaluation Norms and Standards of Evaluation

https://www.iom.int/jahia/webdav/site/myjahiasite/shared/shared/mainsite/about_iom/eva_techref/UNEG_Standards_for_Evaluation.pdf

- UNEG Quality Checklist for Evaluation Reports

http://www.uneval.org/document/detail/607

- UNEG Quality Checklist for Evaluation Reports

http://www.uneval.org/document/detail/607

Survey and Studies

Demographic Health Survey 2006

http://phtpacific.org/sites/default/files/surveys_dev_reports/90/files/PNG_DemographicHealthSurvey-2006_2009-07_GoPNG.pdf

The National Population and Housing Census 2011

ANNEX 4: Required Expertise and Qualifications of the Evaluation Team

The Evaluation Team will be composed of three members, an international UNDAF Evaluation Team Leader, a National Evaluation Specialist and a National Evaluation Consultant. Each team member has a separate Terms of Reference attached to their Individual Consultant Procurement Notice for their reference and attention.

The evaluation members must have considerable experience in conducting evaluations and broad knowledge of the four UNDAF Outcome Pillars and cross-cutting issues (gender equality and human rights). The Evaluation Team Leader (UNDAF Evaluation Expert) should have profound knowledge of One UN reform and Delivering as One and experience conducting UNDAF End of Programme Evaluations.

The Evaluation Team Leader should be able to demonstrate:

  - A minimum of 10 years’ relevant professional experience in evaluation in developing countries is required.

  - Documented previous experience in managing and leading complex UNDAF evaluations, and a solid understanding on the use of evaluation methodologies.

  - Substantive knowledge of development issues, especially related to the four outcome pillars of the 2012-2017 UNDAF as well as strong understanding of and experience with gender equality, women’s empowerment and human rights as cross-cutting development themes.

  - Specialized experience and/or methodological/technical knowledge, including some specific data collection and analytical skills, particularly in the following areas: understanding of human rights-based approaches to programming; gender considerations; Results Based Management (RBM) principles; logic modelling/logical framework analysis; quantitative and qualitative data collection and analysis; participatory approaches.

  - Excellent knowledge of the UN system and UN common country programming processes.

  - Demonstrated knowledge of Delivering as One.

  - Knowledge and sensitivity in terms of the political context of Papua New Guinea.

  - Demonstrated capacity in strategic thinking, problem solving and policy advice.

  - Strong inter-personal, teamwork and organizational skills.

  - Excellent presentation and drafting, report writing skills, and familiarity with information technology, including proficiency in word processing, spreadsheets, and presentation software.

  - Ability to handle a large volume of work possibly under time constraints.

The National Evaluation Specialist should be able to demonstrate:

- Minimum 7 years’ experience in evaluation in developing countries.

- Documented previous experience in evaluations in the UN system, and a solid understanding on the use of evaluation methodologies.

- Substantive knowledge of development issues (in particular, programmatic areas covered by UNDAF in the country) and understanding of the development context of Papua New Guinea.

- Strong skills and experience in evaluating programmatic areas covered by UNDAF in the country (governance for equitable development, social justice, protection and gender equality, access to basic services and environment, climate change and disaster risk management).

- Demonstrated capacity in strategic thinking and policy advice.

- Strong inter-personal, teamwork and organizational skills.

- Excellent drafting skills and familiarity with information technology, including proficiency in word processing, spreadsheets, and presentation software.

- Conceptualizes and analyses problems to identify key issues, underlying problems, and how they relate.

- Ability to build and sustain effective dialogue with main constituents, communicate effectively and sensitively across different constituencies.

- Ability to handle a large volume of work possibly under time constraints.

- Fluency in written and spoken English and Tok Pisin.

The National Evaluation Consultant should be able to demonstrate:

- Proven experience in the field of development cooperation in Papua New Guinea.

- Experience conducting evaluations in Papua New Guinea, combined with a solid understanding on the use of evaluation methodologies.

- Substantive knowledge development issues in PNG and their institutional and social context.

- Familiarity with information technology, including proficiency in word processing, spreadsheets, and presentation software.

- Strong inter-personal, teamwork, organizational and interview skills.

- Knowledge of Papua New Guinea, its institutions, key development stakeholders and partners.

- Ability to build and sustain effective dialogue with main constituents, communicate effectively and sensitively across different constituencies.

- Fluency in written and spoken English and Tok Pisin.

- Ability to handle a large volume of work possibly under time constraints.

ANNEX 5: Suggested Format of Proposed Action Plan for Implementation of Evaluation Recommendations

| Recommendations | Strategy (how) | Responsible parties (who) | Deadline/ follow-up and note, if any |
| --- | --- | --- | --- |

ANNEX 6: The UNDAF End of Programme Evaluation Process & Timeframe

| DATE | ACTIVITY | RESPONSIBLE |
| --- | --- | --- |
| October- December 2015 | Preparatory Activities: | RCO, UNCT, Evaluation Management Group and RBM Committee |
|  | UNDAF ToR drafted, discussed, finalized & adapted in collaboration with GoPNG. |  |
|  | UNDAF conceptual framework & management arrangements organization in place |  |
|  | Secretariat to facilitate UNDAF process identified |  |
|  | Advertisement and evaluation of short listed consultants |  |
|  | Reference checks for shortlisted consultants |  |
|  | Contract signed with consultants |  |
| January-February 2016 | Consultants on board | EMG, RBM Committee and Consultants |
|  | Finalisation of methodology and Inception Report including Harmonized Evaluation Plan and PPT summary presentation to UNCT and EMG |  |
|  | Desk review |  |
|  | Participatory data gathering |  |
|  | Data analysis and report drafting |  |
| March 2016 | Workshop for review of preliminary findings and their shaping | Consultants, EMG and Evaluation Manager |
|  | First Interim Report |  |
|  | Review of the report by key stakeholders |  |
|  | 2nd Interim report (Draft UNDAF Report) |  |
| April 2016 | Submission of draft full report | Consultants & Steering Committee, EMG, RBM Committee & RCO |
|  | Validation workshop |  |
|  | Final report |  |

ANNEX III Individual Consultant Contract and General Terms and Conditions

UNITED NATIONS DEVELOPMENT PROGRAMME GENERAL CONDITIONS OF CONTRACTS FOR THE SERVICES OF INDIVIDUAL CONTRACTORS

- LEGAL STATUS

The Individual contractor shall have the legal status of an independent contractor vis-à-vis the United Nations Development Programme (UNDP), and shall not be regarded, for any purposes, as being either a “staff member” of UNDP, under the UN’ Staff Regulations and Rules, or an “official” of UNDP, for purposes of the Convention on the Privileges and Immunities of the United Nations, adopted by the General Assembly of the United Nations on 13 February 1946. Accordingly, nothing within or relating to the Individual Contract shall establish the relationship of employer and employee, or of principal and agent, between UNDP and the Individual contractor. The officials, representatives, employees or subcontractors of U ND P and of the Individual contractor, if any, shall not be considered in any respect as being the employees or agents of the other, and UNDP and the Individual contractor shall be solely responsible for all claims arising out of or relating to its engagement of such persons or entities.

- STANDARDS OF CONDUCT

In General: The Individual contractor shall neither seek nor accept instructions from any authority external to UNDP in connection with the performance of its obligations under the Individual Contract. Should any authority external to UNDP seek to impose any instructions on the Individual Contract regarding the Individual contractor’s performance under the Individual Contract, the Individual contractor shall promptly notify UNDP and shall provide all reasonable assistance required by UNDP. The Individual contractor shall not take any action in respect of its performance of the Individual Contract or otherwise related to its obligations under the Individual Contract that may adversely affect the interests of UNDP, and the Individual contractor shall perform its obligations under the Individual Contract with the fullest regard to the interests of UNDP. The Individual contractor warrants that it has not and shall not offer any direct or indirect benefit arising from or related to the performance of the Individual Contract or the award thereof to any representative, official, employee or other agent of UNDP. The Individual contractor shall comply with all laws, ordinances, rules and regulations bearing upon the performance of its obligations under the Individual Contract. In the performance of the Individual Contract the Individual contractor shall comply with the standards of conduct set in the Secretary General’s Bulletin ST/SGB/2002/9 of 18 June 2002, entitled “Regulations Governing the Status, Basic Rights and Duties of Officials other than Secretariat Officials, and Expert on Mission”.

The individual contractor must comply with all Security Directives issued by UNDP. Failure to comply with such security directives is grounds for termination of the Individual contractor for cause. Prohibition of Sexual Exploitation and Abuse: In the performance of the Individual Contract, the Individual contractor shall comply with the standards of conduct set forth in the Secretary-General’s bulletin ST/SGB/2003/13 of 9 October 2003, concerning “Special measures for protection from sexual exploitation and sexual abuse”. In particular, the Individual contractor shall not engage in any conduct that would constitute sexual exploitation or sexual abuse, as defined in that bulletin.

The Individual contractor acknowledges and agrees that any breach of any of the provisions hereof shall constitute a breach of an essential term of the Individual Contract, and, in addition to any other legal rights or remedies available to any person, shall give rise to grounds for termination of the Individual Contract. In addition, nothing herein shall limit the right of U N D P to refer any alleged breach of the foregoing standards of conduct to the relevant national authorities for appropriate legal action.

- TITLE RIGHTS, COPYRIGHTS, PATENTS AND OTHER PROPRIETARY RIGHTS

Title to any equipment and supplies that may be furnished by UNDP to the Individual contractor for the performance of any obligations under the Individual Contract shall rest with UNDP, and any such equipment shall be returned to UNDP at the conclusion of the Individual Contract or when no longer needed by the Individual contractor. Such equipment, when returned to UNDP, shall be in the same condition as when delivered to the Individual contractor, subject to normal wear and tear, and the Individual contractor shall be liable to compensate UNDP for any damage or degradation of the equipment that is beyond normal wear and tear.

UNDP shall be entitled to all intellectual property and other proprietary rights, including, but not limited to, patents, copyrights and trademarks, with regard to products, processes, inventions, ideas, know-how or documents and other materials which the Individual contractor has developed for UNDP under the I nd ivid ual Co ntract and which bear a direct relation to or are produced or prepared or collected in consequence of, or during the course of, the performance of the Individual Contract, and the Individual contractor acknowledges and agrees that such products, documents and other materials constitute works made for hire for UNDP. However, to the extent that any such intellectual property or other proprietary rights consist of any intellectual property or other proprietary rights of the Individual contractor: (a) that pre-existed the performance by the Individual contractor of its obligations under the Individual Contract, or (b) that the Individual contractor may develop or acquire, or may have developed or acquired, independently of the performance of its obligations under the Individual Contract, UNDP does not and shall not claim any ownership interest thereto, and the Individual contractor grants to UNDP a perpetual licence to use such intellectual property or other proprietary right solely for the purposes of and in accordance with the requirements of the Contract. At the request of UNDP, the Individual contractor shall take all necessary steps, execute all necessary documents and generally assist in securing such proprietary rights and transferring or licensing them to UNDP in compliance with the requirements of the applicable law and of the Individual Contract. Subject to the foregoing provisions, all maps, drawings, photographs, mosaics, plans, reports, estimates, recommendations, documents and all other data compiled by or received by the Individual contractor under the Individual Contract shall be the property of UNDP, shall be made available for use or inspection by UNDP at reasonable times and in reasonable places, shall be treated as confidential and shall be delivered only to UNDP authorized officials on completion of work under the Individual Contract.

- CONFIDENTIAL NATURE OF DOCUMENTS AND INFORMATION

Information and data that are considered proprietary by either UNDP or the Individual contractor or that are delivered or disclosed by one of them (“Discloser”) to the other (“Recipient”) during the course of performance of the Individual Contract, and that are designated as confidential (“Information”), shall be held in confidence and shall be handled as follows. The Recipient of such Information shall use the same care and discretion to avoid disclosure, publication or dissemination of the Discloser’s Information as it uses with its own similar information that it does not wish to disclose, publish or disseminate, and the Recipient may otherwise use the Discloser’s Information solely for the purpose for which it was disclosed. The Recipient may disclose confidential Information to any other party with the Discloser’s prior written consent, as well as to the Recipient’s employees, officials, representatives and agents who have a need to know such confidential Information solely for purposes of performing obligations under the Individual Contract. Subject to and without any waiver of the privileges and immunities of UNDP, the Individual contractor may disclose Information to the extent required by law, provided that the Individual contractor will give UNDP sufficient prior notice of a request for the disclosure of Information in order to allow UNDP to have a reasonable opportunity to take protective measures or such other action as may be appropriate before any such disclosure is made. UNDP may disclose Information to the extent as required pursuant to the Charter of the United Nations, resolutions or regulations of the General Assembly or its other governing bodies, or rules promulgated by the Secretary-General. The Recipient shall not be precluded from disclosing Information that is obtained by the Recipient from a third party without restriction, is disclosed by the Discloser to a third party without any obligation of confidentiality, is previously known by the Recipient, or at any time is developed by the Recipient completely independently of any disclosures hereunder. These obligations and restrictions of confidentiality shall be effective during the term of the Individual Contract, including any extension thereof, and, unless otherwise provided in the Individual Contract, shall remain effective following any termination of the Individual Contract.

- TRAVEL, MEDICAL CLEARANCE AND SERVICE-INCURRED DEATH, INJURY OR ILLNESS

If the Individual contractor is required by UNDP to travel beyond commuting distance from the Individual contractor’s usual place of residence, a n d upon prior written agreement, such travel shall be at the expense of UNDP . Such travel shall be at economy care when by air.

UNDP may require the Individual contractor to submit a Statement of Good Health from a recognized physician prior to commencement of work in any offices or premises of UNDP or before engaging in any travel required by UNDP or connected with the performance of the Individual Contract. The Individual contractor shall provide such a Statement of Good Health as soon as practicable following such request, and prior to engaging in any such travel, and the Individual contractor warrants the accuracy of any such Statement, including, but not limited to, confirmation that the Individual contractor has been fully informed regarding the requirements for inoculations for the country or countries to which travel may be authorized.

In the event of the death, injury or illness of the Individual contractor which is attributable to the performance of services on behalf of UNDP under the terms of the Individual Contract while the Individual contractor is traveling at UNDP expense or is performing any services under the Individual Contract in any offices or premises of UNDP, the Individual contractor or the Individual contractor’s dependents, as appropriate, shall be entitled to compensation equivalent to that provided under the UNDP insurance policy, available upon request.

- PROHIBITION ON ASSIGNMENT; MODIFICATIONS

The Individual contractor may not assign, delegate, transfer, pledge or make any other disposition of the Individual Contract, of any part thereof, or of any of the rights, claims or obligations under the Individual Contract except with the prior written authorization of UNDP, and any attempt to do so shall be null and void. The terms or conditions of any supplemental undertakings, licences or other forms of Individual Contract concerning any goods or services to be provided under the Individual Contract shall not be valid and enforceable against UNDP nor in any way shall constitute an Individual Contract by UNDP thereto, unless any such undertakings, licences or other forms of Individual Contract are the subject of a valid written undertaking by UNDP. No modification or change in the Individual Contract shall be valid and enforceable against UNDP unless provided by means of a valid written amendment to the Individual Contract signed by the Individual contractor and an authorized official or appropriate contracting authority of UNDP.

- SUBCONTRACTORS

In the event that the Individual contractor requires the services of subcontractors to perform any obligations under the Individual Contract, the Individual contractor shall obtain the prior written approval of UNDP for any such subcontractors. UNDP may, in its sole discretion, reject any proposed sub contractor or require such subcontractor’s removal without having to give any justification therefore, and such rejection shall not entitle the Individual contractor to claim any delays in the performance, or to assert any excuses for the non-performance, of any of its obligations under the Individual Contract. The Individual contractor shall be solely responsible for all services and obligations performed by its subcontractors. The terms of any subcontract shall be subject to, and shall be construed in a manner that is fully in accordance with, all of the terms and conditions of the Individual Contract.

- USE OF NAME, EMBLEM OR OFFICIAL SEAL OF THE UNITED NATIONS

The Individual contractor shall not advertise or otherwise make public for purposes of commercial advantage or goodwill that it has a contractual relationship with UNDP, nor shall the Individual contractor, in any manner whatsoever, use the name, emblem or official seal of UNDP, or any abbreviation of the name of UNDP, in connection with its business or otherwise without the written permission of UNDP.

- INDEMNIFICATION

The Individual contractor shall indemnify, defend, and hold and save harmless UNDP, and its officials, agents and employees, from and against all suits, proceedings, claims, demands, losses and liability of any kind or nature, including, but not limited to, all litigation costs and expenses, attorney’s fees, settlement payments and damages, based on, arising from, or relating to: (a) allegations or claims that the use by UNDP of any patented device, any copyrighted material or any other goods or services provided to UNDP for its use under the terms of the Individual Contract, in whole or in part, separately or in combination, constitutes an infringement of any patent, copyright, trademark or other intellectual property right of any third party; or (b) any acts or omissions of the Individual contractor, or of any subcontractor or anyone directly or indirectly employed by them in the performance of the Individual Contract, which give rise to legal liability to anyone not a party to the Individual Contract, including, without limitation, claims and liability in the nature of a claim for workers’ compensation.

- INSURANCE

The Individual contractor shall pay UNDP promptly for all loss, destruction or damage to the property of UNDP caused by the Individual contractor, or of any subcontractor, or anyone directly or indirectly employed by them in the performance of the Individual Contract.

The Individual contractor shall be solely responsible for taking out and for maintaining adequate insurance required to meet any of its obligations under the Individual Contract, as well as for arranging, at the Individual contractor’s sole expense, such life, health and other forms of insurance as the Individual contractor may consider to be appropriate to cover the period during which the Individual contractor provides services under the Individual Contract. The Individual contractor acknowledges and agrees that none of the insurance arrangements the Individual contractor may make shall, in any way, be construed to limit the Individual contractor’s liability arising under or relating to the Individual Contract.

- ENCUMBRANCES AND LIENS

The Individual contractor shall not cause or permit any lien, attachment or other encumbrance by any person to be placed on file or to remain on file in any public office or on file with UNDP against any monies due to the Individual contractor or to become due for any work donor or against any goods supplied or materials furnished under the Individual Contract, or by reason of any other claim or demand against the Individual contractor.

- FORCE MAJEURE; OTHER CHANGES IN CONDITIONS

In the event of and as soon as possible after the occurrence of any cause constituting force majeure, the Individual contractor shall give notice and full particulars in writing to UNDP of such occurrence or cause if the Individual contractor is thereby rendered unable, wholly or in part, to perform its obligations and meet its responsibilities under the Individual Contract. The Individual contractor shall also notify UNDP of any other changes in conditions or the occurrence of any event, which interferes or threatens to interfere with its performance of the Individual Contract. Not more than fifteen (15) days following the provision of such notice of force majeure or other changes in conditions or occurrence, the Individual contractor shall also submit a statement to UNDP of estimated expenditures that will likely be incurred for the duration of the change in conditions or the event. On receipt of the notice or notices required hereunder, UNDP shall take such action as it considers, in its sole discretion, to be appropriate or necessary in the circumstances, including the granting to the Individual contractor of a reasonable extension of time in which to perform any obligations under the Individual Contract.

If the Individual contractor is rendered permanently unable, wholly or in part, by reason of force majeure to perform its obligations and meet its responsibilities under the Individual Contract, UNDP shall have the right to suspend or terminate the Individual Contract on the same terms and conditions as are provided for below, under “Termination”, except that the period of notice shall be five (5) days instead of any other period of notice. In any case, UNDP shall be entitled to consider the Individual contractor permanently unable to perform its obligations under the Individual Contract in the case of the Individual contractor’s suffering any period of suspension in excess of thirty (30) days.

Force majeure as used herein means any unforeseeable and irresistible act of nature, any act of war (whether declared or not), invasion, revolution, insurrection, or any other acts of a similar nature or force, provided that such acts arise from causes beyond the control and without the fault or negligence of the Individual contractor. The Individual contractor acknowledges and agrees that, with respect to any obligations under the Individual Contract that the Individual contractor must perform in or for any areas in which UNDP is engaged in, preparing to engage in, or disengaging from any peacekeeping, humanitarian or similar operations, any delay or failure to perform such obligations arising from or relating to harsh conditions within such areas or to any incidents of civil unrest occurring in such areas shall not, in and of itself, constitute force majeure under the Individual Contract.

- TERMINATION

Either party may terminate the Individual Contract, in whole or in part, upon giving written notice to the other party. The period of notice shall be five (5) days in the case of Individual Contracts for a total period of less than two (2) months and fourteen (14) days in the case of contracts for a longer period. The initiation of conciliation or arbitral proceedings, as provided below, shall not be deemed to be a “cause” for or otherwise to be in itself a termination of the Individual Contract. UNDP may, without prejudice to any other right or remedy available to it, terminate the Individual Contract forthwith in the event that: (a) the Individual contractor is adjudged bankrupt, or is liquidated, or becomes insolvent, applies for moratorium or stay on any payment or repayment obligations, or applies to be declared insolvent; (b) the Individual contractor is granted a moratorium or a stay or is declared insolvent; the Individual contractor makes an assignment for the benefit of one or more of its creditors; (c) a Receiver is appointed on account of the insolvency of the Individual contractor ; (d) the Individual contractor offers a settlement in lieu of bankruptcy or receivership; or (e) UNDP reasonably determines that the Individual contractor has become subject to a materially adverse change in its financial condition that threatens to endanger or otherwise substantially affect the ability of the Individual contractor to perform any of its obligations under the Individual Contract.

In the event of any termination of the Individual Contract, upon receipt of notice of termination by UNDP, the Individual contractor shall, except as may be directed by UNDP in the notice of termination or otherwise in writing: (a) take immediate steps to bring the performance of any obligations under the Individual Contract to a close in a prompt and orderly manner, and in doing so, reduce expenses to a minimum; (b) refrain from undertaking any further or additional commitments under the Individual Contract as of and following the date of receipt of such notice; (c) deliver all completed or partially completed plans, drawings, information and other property that, if the Individual Contract had been completed, would be required to be furnished to UNDP thereunder; (d) complete performance of the work not terminated; and (e) take any other action that may be necessary, or that UNDP may direct in writing, for the protection and preservation of any property, whether tangible or intangible, related to the Individual Contract that is in the possession of the Individual contractor and in which UNDP has or may be reasonably expected to acquire an interest.

In the event of any termination of the Individual Contract, UNDP shall only be liable to pay the Individual contractor compensation on a pro rata basis for no more than the actual amount of work performed to the satisfaction of UNDP in accordance with the requirements of the Individual Contract. Additional costs incurred by UNDP resulting from the termination of the Individual Contract by the Individual contractor may be withheld from any amount otherwise due to the Individual contractor from UNDP.

- NON-EXCLUSIVITY

UNDP shall have no obligation respecting, and no limitations on, its right to obtain goods of the same kind, quality and quantity, or to obtain any services of the kind described in the Individual Contract, from any other source at any time.

- TAXATION

Article II, section 7, of the Convention on the Privileges and Immunities of the United Nations provides, inter alia, that the United Nations, including its subsidiary organs, is exempt from all direct taxes, except charges for public utility services, and is exempt from customs restrictions, duties and charges of a similar nature in respect of articles imported or exported for its official use. In the event any governmental authority refuses to recognize the exemptions of the United Nations from such taxes, restrictions, duties or charges, the Individual contractor shall immediately consult with UNDP to determine a mutually acceptable procedure. UNDP shall have no liability for taxes, duties or other similar charges payable by the Individual contractor in respect of any amounts paid to the Individual contractor under this Individual Contract, and the Individual contractor acknowledges that UNDP will not issue any statements of earnings to the Individual contractor in respect of any such payments.

- AUDIT AND INVESTIGATION

Each invoice paid by UNDP shall be subject to a post-payment audit by auditors, whether internal or external, of UNDP or by other authorized and qualified agents of UNDP at any time during the term of the Individual Contract and for a period of two (2) years following the expiration or prior termination of the Individual Contract. UNDP shall be entitled to a refund from the Individual contractor for any amounts shown by such audits to have been paid by UNDP other than in accordance with the terms and conditions of the Individual Contract.

The Individual contractor acknowledges and agrees that, from time to time, UNDP may conduct investigations relating to any aspect of the Individual Contract or the award thereof, the obligations performed under the Individual Contract, and the operations of the Individual contractor generally relating to performance of the Individual Contract. The right of UNDP to conduct an investigation and the Individual contractor’s obligation to comply with such an investigation shall not lapse upon expiration or prior termination of the Individual Contract. The Individual contractor shall provide its full and timely cooperation with any such inspections, post-payment audits or investigations. Such cooperation shall include, but shall not be limited to, the Individual contractor’s obligation to make available its personnel and any relevant documentation for such purposes at reasonable times and on reasonable conditions and to grant to UNDP access to the Individual contractor’s premises at reasonable times and on reasonable conditions in connection with such access to the Individual contractor’s personnel and relevant documentation. The Individual contractor shall require its agents, including, but not limited to, the Individual contractor’s attorneys, accountants or other advisers, to reasonably cooperate with any inspections, post-payment audits or investigations carried out by UNDP hereunder.

- SETTLEMENT OF DISPUTES

Amicable Settlement: UNDP and the Individual contractor shall use their best efforts to amicably settle any dispute, controversy or claim arising out of the Individual Contract or the breach, termination or invalidity thereof. Where the parties wish to seek such an amicable settlement through conciliation, the conciliation shall take place in accordance with the Conciliation Rules then obtaining of the United Nations Commission on International Trade Law (“UNCITRAL”), or according to such other procedure as may be agreed between the parties in writing.

Arbitration: Any dispute, controversy or claim between the parties arising out of the Individual Contract, or the breach, termination, or invalidity thereof, unless settled amicably, as provided above, shall be referred by either of the parties to arbitration in accordance with the UNCITRAL Arbitration Rules then obtaining. The decisions of the arbitral tribunal shall be based on general principles of international commercial law. For all evidentiary questions, the arbitral tribunal shall be guided by the Supplementary Rules Governing the Presentation and Reception of Evidence in International Commercial Arbitration of the International Bar Association, 28 May 1983 edition. The arbitral tribunal shall be empowered to order the return or destruction of goods or any property, whether tangible or intangible, or of any confidential information provided under the Individual Contract , order the termination of the Individual Contract, or order that any other protective measures be taken with respect to the goods, services or any other property, whether tangible or intangible, or of any confidential information provided under the Individual Contract, as appropriate, all in accordance with the authority of the arbitral tribunal pursuant to Article 26 (“Interim Measures of Protection”) and Article 32 (“Form and Effect of the Award”) of the UNCITRAL Arbitration Rules. The arbitral tribunal shall have no authority to award punitive damages. In addition, unless otherwise expressly provided in the Individual Contract, the arbitral tribunal shall have no authority to award interest in excess of the London Inter-Bank Offered Rate (“LIBOR”) then prevailing, and any such interest shall be simple interest only. The parties shall be bound by any arbitration award rendered as a result of such arbitration as the final adjudication of any such dispute, controversy or claim.

- LIMITATION ON ACTIONS:

Except with respect to any indemnification obligations in Article 7, above, or as are otherwise set forth in the Individual Contract, any arbitral proceedings in accordance with Article 17 above, arising out of the Individual Contract must be commenced within three years after the cause of action has accrued. The Parties further acknowledge and agree that, for these purposes, a cause of action shall accrue when the breach actually occurs, or, in the case of latent defects, when the injured Party knew or should have known all of the essential elements of the cause of action, or in the case of a breach of warranty, when tender of delivery is made, except that, if a warranty extends to future performance of the goods or any process or system and the discovery of the breach consequently must await the time when such goods or other process or system is ready to perform in accordance with the requirements of the Individual Contract, the cause of action accrues when such time of future performance actually begins.

- PRIVILEGES AND IMMUNITIES

Nothing in or relating to the Individual Contract shall be deemed a waiver, express or implied, of any of the privileges and immunities of the United Nations, including its subsidiary organs.