{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["BOQ"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"BOQ","index":0,"n_rows":86,"n_cols":6,"rows_kept":86,"cut":false,"hidden":false,"merged":[[5,1,5,5],[8,1,8,5],[0,0,0,5],[1,1,1,5],[2,1,2,5],[3,1,3,5],[4,1,4,5],[6,1,6,5],[7,1,7,5]]}
["Rehabilitation of 50 Housing Units in Batnaya subdistrict-Talkif district-Ninawa Governorate-ITB-786-18"]
[null,"General Specification "]
[1,"All works and the materials supplied by the contractor must be in according with the relevant Iraq's standard Specifications ( It’s the contractor responsibility to obtain any relevant Iraqi specifications by visiting ministry of construction and housing web site: www.moch.gov.iq (or physically obtain those documents from the mentioned ministry) in addition to Iraqi technical specification for building works."]
[2,"Permanent signage (after implementation is completed): (60cm x 40cm), printed on white aluminum composite (trade name – Dibond). To be placed in a prominent position at the main entry door of the site, at eye level."]
[3,"Temporary signage (during implementation): (W 190cm x H 90cm) printed on mounted plastic sheeting"]
[4,"The contractor must provide samples, mockup, catalogues for testing / inspection and approval by the site engineer."]
[5,"Contractor must pay the cost for samples including any laboratory tests, both inside and outside the country as required."]
[6,"The price of works includes all job requirements as per Iraq's standard specification."]
[7,"The contractor must provide PPE for all laborer's, personnel, engineers and possible visitors to the site."]
["#","Item Description","Unit","Qty","Price$","Total $"]
[null,"CIVIL WORKS"]
[1,"Site preparation:\nSupply of materials, tools, machineries and manpower for site preparation. The work includes :     \n1-Clearing, stripping and levelling of the site with garden.\n2-Removing all the damaged roofing layers, slabs, walls, fences, finishing materials, flooring tiles, tile bedding, etc.     \n3-Dumping of all the debris and rubble to a site approved by the local authorities.      \n All needed work to complete the job will be included within the price.","NO.",50,null,{"$f":"D12*E12","v":0}]
[2,"Plain Concrete Foundation:\nSupply of materials, tools and manpower for casting plain concrete (C25MPa) using sulphate resistance cement for foundations of (fences, walkways, apron, etc.). The price includes adding bonding agent material between the old and new concrete(if any). All needed works to complete the job will be included within the price.","M3",4,null,{"$f":"D13*E13","v":0}]
[3,"Plain Concrete Floor:\nSupply of materials, tools and manpower to cast plain concrete (C25MPa) for floors, 10 cm thickness using sulphate resistant cement. The work includes laying 10cm crushed stone beneath the plain concrete.  All needed work to complete the job will be included within the price.","M2",120,null,0]
[4,"Repairing of Beam, Columns :\nSupply of materials, tools, machinery and manpower for repairing of reinforced concrete  Beam, Columns by demolition of the destroyed area of the Beam, Columns and dumping of all debris and rubble to a site approved by local authorities. Price will include recasting a reinforced concrete ( same as the existing) for the damaged area using concrete (C25MPa) , providing formwork, rebar and using bonding agent (like SBR) to create a bonding slurry when mixed with cement. All needed works to complete the job, will be included within the price.","M3",8,null,0]
[5,"Repairing of Slab:\nSupply of materials, tools, machinery and manpower for repairing of reinforced concrete slab by demolition of the destroyed area of the slab and dumping of all debris and rubble to a site approved by local authorities. Price will include recasting a reinforced concrete 20cm thickness (or same as the existing) for the damaged area of the slab using concrete (C25MPa) , providing formwork, rebar Ø12mm@150mm both directions and top and bottom and using bonding agent (like SBR) to create a bonding slurry when mixed with cement. The new slab must rest on the old slab by a minimum distance not less than 50 cm and treat both contacted slab by isolated material to prevent water leakage.  All needed works to complete the job, will be included within the price.","M3",9,null,0]
[6,"Reconstruction of Damaged Walls:\nSupply of materials, tools and manpower to demolish the damaged parts of the walls and remove all the debris to a site approved by local authorities, then reconstruction of the walls using solid concrete block (15x20x40cm) (20cm width) with cement sand mortar (same as the existing walls). The wall should be levelled vertically and horizontally. All needed works to complete the job, will be included within the price","M2",530,null,0]
[7,"Reconstruction of Damaged Fences, parapet:\nSupply of materials, tools and manpower to rebuild fence wall (20cm width) using hollow concrete blocks (20x20x40) cm with cement sand mortar (1:3). The wall should be levelled vertically and horizontally. The price includes demolishing of the damaged fence and removing of all debris and rubble to a dump site approved by the local authority, providing concrete block columns (40x40cm) every 5m and providing expansion joints(including Styrofoam 2cm) every 10m. All needed works to complete the job will be included within the price. ","M2",80,null,0]
[8," Roof Waterproofing Works:\nSupply of materials, tools and manpower for roof repairing work. By cleaning concrete surface and follow up steps as below:\n1- Treatment of cracks and wall connection area with roof, by using polyurethane foam\n2- Apply one layer of polyurethane primer coat\n3- Painting the surface by using 3 layers of polyurethane (rubber membrane paint) of 2 mm thickness \nAll needed works to complete the job will be included within the price. ","M2",120,null,0]
[9,"Sandwich Panel Roof: \nSupply of materials, tools and manpower to remove the damage sandwich panel, removing of all the debris and rubble to a site approved by the local authority, then provide a roofing structure using rectangular steel tube (80x40x2mm) every 80cm and install new sandwich panel for roofing (5cm thickness). The work includes painting the frame with anti-rust paint and two layers of oil paints and fixing with screws. All needed works to complete the job will be included within the price.","M2",55,null,{"$f":"D20*E20","v":0}]
[10,"Gypsum plastering with crack repairing:\nSupply of all necessary materials, tools and manpower to remove the damaged gypsum plastering of internal walls & ceiling and plastering with new gypsum plastering  in 2 layers minimum thickness 20mm.The work includes repairing of wall cracks by removing the damaged gypsum plastering 25cm at each side of the crack, then filling the cracks with cement mortar 1:3 and using SBR at a rate of 50gr per m2 , later putting a layer of plastic mesh on the area under the gypsum plastering. All needed works to complete the job, will be included within the price.","M2",1600,null,0]
[11,"Cement plastering with crack repairing:\nSupply of materials, tools and manpower to repair wall cracks and remove the damaged cement plastering of external walls & fence by removing the damaged cement plastering minimum 35cm at each side of the crack, then treat the cracks with crack filler approved by manufacture with cement mortar 1:3 and using SBR at a rate of 50gr per m2, later putting a layer of metal chicken mesh 10 cm overlap each side on the area with 3 layers of cement plastering 1:3. All needed works to complete the job, will be included within the price.","M2",750,null,0]
[12,"Plastic Suspended Ceiling :\nSupply of materials, tools and manpower to install plastic suspended ceiling 60x60 cm, 7mm thickness, by using necessary accessories L, T sections, hold down clips, galvanized steel rod 5mm (1.2x1.2m) for fixing with the ceiling by screws. The price includes the removal of old damaged suspended ceiling, dumping of all debris to a site approved by local authorities, in case it is needed. All needed work to complete the job will be included within the price. See attached drawing.","M2",450,null,0]
[13,"Acoustic Suspended Ceiling :\nSupply of materials, tools and manpower to install  gypsum board suspended ceiling 60x60 cm, 8mm thickness, by using necessary accessories L, T sections, hold down clips, galvanized steel rod 5mm (1.2x1.2m) for fixing with the ceiling by screws. The price includes the removal of old damaged suspended ceiling, dumping of all debris to a site approved by local authorities, in case it is needed. All needed work to complete the job will be included within the price. See attached drawing.","M2",1250,null,0]
[14,"Terrazzo(Mosaic) tiles for Floors:\nSupply of materials, tools and manpower to remove the damaged mosaic tiles and dumping it to a place approved by local authority, then apply mosaic tiles grade #4 for floors (30x30cm) or same as the existing size and color, using cement sand mortar(1:3), filling the joints with white cement paste. All needed work to complete the job will be included within the price.","M2",150,null,0]
[15,"Ceramic tiles for Walls:\nSupply of materials, tools and manpower to remove the damaged ceramic tiles and dumping it to a place approved by local authority, then apply ceramic tiles for walls (30x60cm) or same as the existing size and color, using cement sand mortar(1:3), filling the joints with white cement paste. All needed work to complete the job will be included within the price.","M2",170,null,0]
[16,"Emulsion painting:\nSupply of materials, tools and manpower to paint the interior walls and ceilings, with 3 layers of emulsion painting (Jotun, Betek, CAPAROL, Polisan, dyo or equivalent). The paint should be diluted (10%--15%) with water to achieve the coverage of painting of not more than (10-12) m2/Liter/layer. The job includes cleaning the walls and ceilings, removing the dirt and dust, repairing all the cracks and filling all the holes before painting. All needed works to complete the job, shall be included within the price.","M2",24700,null,0]
[17,"Plastic painting:\nSupply of materials, tools and manpower to paint the exterior walls and fence, with three layers of plastic (silicon water proof) paint (Jotun, Betek, CAPAROL, Polisan, dyo or equivalent). The paint should be diluted (10%--15%) with water to achieve the coverage of painting of not more than (10-12) m2/Liter/layer.  The job includes cleaning the walls, removing the dirt and dust, repairing all the cracks and filling all the holes before painting. All needed works to complete the job, shall be included within the price.","M2",10000,null,0]
[18,"Oil Painting:\nSupply of materials, tools and manpower to paint the, and internal walls with a paint  using 3 layers of oil paint (Jotun, Betek, CAPAROL, Polisan, dyo or equivalent). The paint should be diluted (10%--15%) with paint thinners to achieve the coverage of painting of not more than (10-12) m2/Liter/layer.  The job includes cleaning the walls, removing the dirt and dust, repairing all the cracks and filling all the holes before painting. All needed works to complete the job, shall be included within the price.","M2",2650,null,0]
[19,"Repair PVC Windows:\nSupply of materials, tools, machineries and manpower to repair the damaged PVC windows, including anti-insects wire mesh for openable parts and handle. All needed works to complete the job, will be included within the price.","M2",15,null,{"$f":"D30*E30","v":0}]
[20,"Repair Steel Windows:\nSupply of materials, tools, machineries and manpower to repair the damaged steel windows, including welding, painting, anti-insects wire mesh for openable parts and handle. All needed works to complete the job, will be included within the price.","M2",960,null,0]
[21,"Repair Aluminum  Windows:\nSupply of materials, tools, machineries and manpower to repair the damaged aluminum windows, including anti-insects wire mesh for openable parts and handle. All needed works to complete the job, will be included within the price.","M2",5,null,0]
[22,"PVC windows:\nSupply of materials, tools and manpower to install  PVC windows (frames of minimum 60 mm width). The price of works includes anti-insects wire mesh for openable parts, hinges, handles, crystal clear glass 4mm thickness. All needed work to complete the job will be included within the price.","M2",200,null,0]
[23,"Steel windows:\nSupply of materials, tools and manpower to install steel windows (using T, L and Z shapes). The price of works includes anti rust painting and two layers of oil painting, anti-insects wire mesh, handles, windows stopper and crystal clear class 4mm thickness with paste. All needed work to complete the job will be included within the price.","M2",25,null,0]
[24,"Windows Burglar:\nSupply of materials, tools and manpower to make steel burglar for the windows using  12mm square steel bar every 15cm and the outer frame of angle section 50x50x2mm. The price of works includes anti rust painting and two layers of oil painting. All needed work to complete the job will be included within the price. See attached drawing.","M2",60,null,0]
[25,"Repair steel doors:\nSupply of materials, tools, machineries and manpower to repair the damaged steel doors. Price of works shall include door lock, handles, hinges, oil painting and accessories. All needed work to complete the job will be included within the price.","NO.",120,null,0]
[26,"Repair wooden doors:\nSupply of materials, tools, machineries and manpower to repair the damaged wooden doors. Price of works shall include door lock, handles, hinges, teak painting and varnish painting and accessories. All needed work to complete the job will be included within the price.","NO.",155,null,0]
[27,"Repair PVC doors:\nSupply of materials, tools, machineries and manpower to repair the damaged PVC doors. Price of works shall include door lock, handles, hinges and accessories. All needed work to complete the job will be included within the price.","NO.",4,null,0]
[28,"Repair aluminum doors:\nSupply of materials, tools, machineries and manpower to repair the damaged aluminum doors. Price of works shall include door lock, handles, hinges and accessories. All needed work to complete the job will be included within the price.","NO.",4,null,0]
[29,"PVC Doors with Frame(0.9x2.00m):\nSupply of materials, tools and manpower to install PVC doors with frame. The PVC section should be wide section. The lower 1.0m portion of the door to be covered by PVC sheets and the upper portion will be covered by frosted glass 6mm. The price includes hinges, handles, locks and frosted glass (6mm) . All needed works to complete the job, will be included within the price. See attached drawing.","NO.",120,null,0]
[30,"PVC Doors with Frame(1.0x2.10m):\nSupply of materials, tools and manpower to install PVC doors with frame. The PVC section should be wide section. The lower 1.0m portion of the door to be covered by PVC sheets and the upper portion will be covered by frosted glass 6mm. The price includes hinges, handles, locks and frosted glass (6mm) . All needed works to complete the job, will be included within the price. See attached drawing.","NO.",150,null,0]
[31,"PVC Doors with Frame(1.1x2.40m) Double Leaves:\nSupply of materials, tools and manpower to install PVC doors with frame. The PVC section should be wide section. The lower 1.0m portion of the door to be covered by PVC sheets and the upper portion will be covered by frosted glass 6mm. The price includes hinges, handles, locks and frosted glass (6mm) . All needed works to complete the job, will be included within the price. See attached drawing.","NO.",40,null,0]
[32,"Steel Door with the Frame(1.0x2.10m):\nSupply of materials, tools and manpower to install steel door with frame, with steel plate gauge 18(1.41mm) on double face, using steel tube 40x40x2mm, including a layer of Styrofoam to be placed between the two faces, hinges, doors handles, locks and fixing a stopper on the floor or wall. The price of work includes the painting of steel door using anti-rust and 2 layers of oil paint. All needed work to complete the job will be included within the price. See attached drawing.","NO.",60,null,0]
[33,"Steel Door with the Frame(1.5.0x2.40m) Double Leaves:\nSupply of materials, tools and manpower to install steel door with frame, with steel plate gauge 18(1.41mm) on double face, using steel tube 40x40x2mm, including a layer of Styrofoam to be placed between the two faces, hinges, doors handles, locks and fixing a stopper on the floor or wall. The price of work includes the painting of steel door using anti-rust and 2 layers of oil paint and   frosted glass (6mm). All needed work to complete the job will be included within the price. See attached drawing.","NO.",30,null,0]
[34,"Wooden doors with Frame(1.0x2.10m):\nSupply of materials, tools and manpower to install teak (saj) wooden doors with red cedar (jaw) frame. Price of the work shall include removing the damaged doors and frames, door locks, handles, hinges, teak painting and varnish painting. Also repairing the gypsum plastering and cement plastering of the edges .All needed work to complete the job will be included within the price. See attached drawing.","NO.",80,null,0]
[35,"Main gate (H1.6m,W2.8m) Two leaves:\nSupply of materials , tools and manpower to install new main gate steel doors, (two leaves) by using plate gauge 18 (1.41mm) and steel tube 40x40x2mm, including door handles, hinges and locks. Price of the work shall include painting of steel door with anti-rust and two layers of oil paints. The price also includes removing of the damaged door and dump it to a place approved by local authority. All needed work to complete the job will be included within the price. See attached drawing.","NO.",42,null,0]
[36,"Sliding Steel Door (1.6x3.0m) Two Leaves:                                                                     Supply of materials, tools and manpower to remove the damaged sliding steel door and removing the debris and rubble to a site approved by local authority, then install new slide steel door (two leaves), including plate gauge 18(1.41mm) on double faces, the gate has a frame of square steel pipe (75x75x3mm) and sub divider of pipe (50x50x3mm) @ 40cm c/c, slide steel frame U channel (84mm) top and bottom. The price of work shall include painting with anti-rust and 2 layers oil paint, rollers, door handles and locks. All needed works to complete the job, will be included within the price. See attached drawing.","NO.",10,null,0]
[37,"Aluminum Handrails:\nSupplying and installation of aluminum handrails (height of 90cm) with all accessories. The price includes removing the old steel handrails and providing bigger column sections at the beginning, turning and at the ends. All needed work to complete the job will be included within the price. See attached annex.","NO.",70,null,0]
[38,"Steel Handrail:\nSupply of materials, tools and manpower to install steel handrail  (height of 90cm) for staircases and openings, using steel tubes as per the drawing. The price includes anti rust and three layers of oil painting. All needed work to complete the job will be included within the price. See attached drawing.","NO.",80,null,0]
[null,"SUB TOTAL FOR CIVIL WORKS ",null,null,null,{"$f":"SUM(F12:F49)","v":0}]
[null,"SANITARY WORKS"]
[1,"Water tank:\nSupply of materials, tools and manpower for installing galvanized water tank of 1250 liters. Cylindrical shape and with plate gauge 18(1.41mm), supported by steel base made with 50mm (2\") angle shape, including the connection of the inlet and outlet pipes. The price of work includes all piping and fittings, valves, float valves, accessories. All needed work to complete the job will be included within the price.","NO.",50,null,{"$f":"D52*E52","v":0}]
[2,"Siphon (Flush Tank):\nSupply of materials, tools and manpower to install siphon, valves and all needed accessories for completing water connections. All needed works to complete the job, will be included within the price.","NO.",15,null,0]
[3,"Taps: \nSupply of materials, tools and manpower to connect chrome water taps 1/2\" or 3/4\". Price of the work shall include water connections. All needed work to complete the job will be included within the price.","NO.",200,null,0]
[4,"Mixer taps :                                                                                                                        Supply of  materials, tools and manpower to install mixer taps , locks and all  accessories with complete water connections. All needed work to complete the job will be included within the price.","NO.",40,null,0]
[5,"Ceramic wash basin:                                                                                                        Supply of materials , tools and manpower to install ceramic wash basin with stand, mixer taps , valves , mirror(60x50)cm and all  fittings with complete water connections . All needed work to complete the job will be included within the price.","NO.",44,null,0]
[6,"Shower head and mixer taps:\nSupply of materials, tools and manpower to install mixer taps with shower head. The price of works includes all needed fittings.  All needed work to complete the job will be included within the price.","NO.",46,null,0]
[7,"Stainless steel single bowl, double wings sink:\nSupply of materials, tools and manpower to install and commission of stainless steel double wings sink (135x60cm). Complete with: chrome mixer for sinks, supports, waste outlet, tail piece, P-trap chrome, chrome plated 14mm and required parts for the water supply line. All needed work to complete the job will be included within the price.","NO.",45,null,0]
[8,"Eastern toilet:\nSupply of materials, tools and manpower to remove the damaged eastern toilet pan and to install new ceramic eastern toilet. Including siphon(flush tank),  gully trap Ø100mm (4\"), flexible hose and water connections. All needed work to complete the job will be included within the price.","NO.",6,null,0]
[9,"Western toilet:\nSupply of materials, tools and manpower to install ceramic western toilet. Including siphon,  gully trap Ø100mm (4\"), flexible hose 5mm, water connections and flushing tank. All needed work to complete the job will be included within the price.","NO.",8,null,0]
[10,"Clean the sewerage : \n Supply of materials, machine and manpower to clean the sewerage pipes net starting from the toilets, manholes to the main septic tank using high pressure air/water. The work includes replace the damaged manhole covers and others with new one.  All needed work to complete the job will be included within the price.","NO.",50,null,0]
[11,"Roof Drain pipes (3\"):\nSupply of materials, tools and manpower to remove the damaged water roof drain pipes and install new PVC pipes 3\" (76mm). Including all connections and needed accessories to fix on roof and walls. All needed work to complete the job will be included within the price. See attached drawing.","M.L",350,null,0]
[12,"PVC pipe 4\" (Ø 100mm):\nSupply, installation, testing and commissioning of PVC 4\"(100mm) 6 bar for drainage and ventilation pipes down to manholes with all required fittings including excavation, back filling, incasing with sulphate resistant cement concrete and roof vent caps. All needed works to complete the job, will be included within the price","M.L",60,null,0]
[13,"Galvanized iron water pipes(1/2\"):\nSupply and install galvanized water pipes. The price includes all fittings and accessories, excavation, backfilling, painting the pipes using 3 layers of anti rust then isolate all hot water pipes by using arm flex and thermal tape and Teflon seal  for connections of cold and hot water pipes and concreting 10cm around the pipes. All needed work to complete the job will be included within the price.","M.L",100,null,0]
[14,"Galvanized iron water pipes(3/4\"):\nSupply and install galvanized water pipes. The price includes all fittings and accessories, excavation, backfilling, painting the pipes using 3 layers of anti rust then isolate all hot water pipes by using arm flex and thermal tape and Teflon seal  for connections of cold and hot water pipes and concreting 10cm around the pipes. All needed work to complete the job will be included within the price.","M.L",80,null,{"$f":"D65*E65","v":0}]
[15,"Galvanized iron water pipes(1\"):\nSupply and install galvanized water pipes. The price includes all fittings and accessories, excavation, backfilling, painting the pipes using 3 layers of anti rust then isolate all hot water pipes by using arm flex and thermal tape and Teflon seal  for connections of cold and hot water pipes and concreting 10cm around the pipes. All needed work to complete the job will be included within the price.","M.L",20,null,0]
[16,"Masonry manholes: \nSupply of materials and construction of manholes of different depths with internal dimension (30x30cm) using solid concrete blocks 15X20X40 cm for walls. The price includes excavation, crushed stone, plain concrete, walls, plastering both sides, &  cast iron covers. See attached drawing.","NO.",8,null,0]
[17,"Masonry manholes: \nSupply of materials and construction of manholes of different depths with internal dimension (60x60cm) using solid concrete blocks 15X20X40 cm for walls. The price includes excavation, crushed stone, plain concrete, walls, plastering both sides, &  cast iron covers. See attached drawing.","NO.",7,null,0]
[null,"SUB TOTAL FOR SANITARY WORKS ",null,null,null,{"$f":"SUM(F52:F68)","v":0}]
[null,"ELECTRICAL WORKS"]
[null,"Note:- The price include removal and disposal all defective and damage items to designated stores \"The following items shall include supply, replace, replace, connect and commission all lighting points and power points. All the necessary equipment/items ( if any) must be earthed properly with specific wire/cable size."]
[1,"Inspection all electric network :\nSupply of materials, tools and manpower to Comprehensive inspection of electrical installations of homes with repair and replacement of damaged wiring. All needed work to complete the job will be included within the price.","NO.",50,null,{"$f":"E72*D72","v":0}]
[2," Electrical bell:   \n Supplying & Installing  for electrical call bell  with 2x 1.5 Sqmm , 1.0kV grade , PVC insulated copper conductor in existing or new PVC surface conduit  /casing capping including one way electrical bell switch , connections, painting, testing and commissioning etc. as required   ","NO.",45,null,0]
[3,"Ceiling fan:\nSupply, replace, test and commission of ceiling fan (240 volt A.C 1400 rpm,1400mm sweep with 56\") , down rod of standard length up to 300mm,sweep 3 Nos.,canopy 2 Nos., condenser and fan body and fan regulator includes rewiring/connecting with 1.0 kV grade 2*1.5mm² PVC insulated copper cable/wires laid inside existing concealed PVC pipe and if required laid through new surface PVC pipe (20 mm dia) with all accessories. The price includes supplying,replacing,connecting,laying, drilling & cutting ( concrete wall if required ) and commissioning to complete works as required.","NO.",100,null,0]
[4,"Exhaust fan(30cm):                                       \nSupplying, replacing and connecting of exhaust fan 240 volt A.C 1400 rpm & 450mm sweep  (30cm) includes rewiring/connecting with 1.0 kV grade 2*1.5mm² PVC insulated copper cable/wires laid inside existing concealed PVC pipe and if required laid through new surface PVC pipe (20 mm dia) with 6 A switches with all accessories. The price includes supplying,replacing,connecting,laying, drilling & cutting ( concrete wall if required ) and commissioning to complete works as required.   ","NO.",50,null,{"$f":"E75*D75","v":0}]
[5,"Exhaust fan(15cm)                                       \nSupplying, replacing and connecting of exhaust fan 240 volt A.C 1400 rpm & 450mm sweep  (15cm) includes rewiring/connecting with 1.0 kV grade 2*1.5mm² PVC insulated copper cable/wires laid inside existing concealed PVC pipe and if required laid through new surface PVC pipe (20 mm dia) with 6 A switches with all accessories. The price includes supplying,replacing,connecting,laying, drilling & cutting ( concrete wall if required ) and commissioning to complete works as required.   ","NO.",50,null,{"$f":"E76*D76","v":0}]
[6,"Electrical Water Heater : \nSupply, replace,  connect, and commission electrical heater 150 Liter capacity 3 kW, with complete fittings & accessories includes rewiring/connecting with 1.0 kV grade 3*4 mm² PVC insulated copper cable/wires laid inside existing concealed PVC pipe and if required laid through new surface PVC pipe (20 mm dia) with all accessories. The price includes supplying,replacing,connecting,laying, drilling & cutting ( concrete wall if required ) and commissioning to complete works as required.   ","NO.",50,null,0]
[7,"Power Cable (2x10mm2):\nSupplying, laying and connecting of one number PVC insulated and sheathed power cable copper, unarmored 1.0KV grade 2 core 10 Sq.mm from the plastic distribution board located on the wall of the building  to (DB Board) distribution board inside each flat as required.  The price of works shall include all accessories as well as all  works to complete the job.","M.L",900,null,0]
[8,"DB Board:\nSupply, install, test, commission prefabricated Main Distribution Board (MDB) (60cm x 40cmx 30cm), using rubber gaskets and equipped with the following items, Plastic trunk for wiring,  the price also include the required, glands, screws, insulators, and etc., all items should be arranged properly, affords a high degree of safety operation,  incorporated in DIN bar with following  incoming and outgoing as:\nA - [(1 No.)  40A,  Single Ph. MCB type].\nB - (2 No.) Indicator lamp 220VAC/5A.\nC - Single phase, two wires Kilowatt-hour meter, with separate earth strip, with all accessories  for necessary cutting, drilling, testing etc. to complete works as required.      \n ","NO.",48,null,0]
[9,"Socket Switch(13A):\nSupplying ,Installation and  fixing of combine 13A, 5 pin universal switch-socket with shuttered & indicator outlet, on PVC molded tough surface box includes wiring/connecting with 1.0 kV grade 3*2.5mm² PVC insulated copper cable/wires laid inside existing concealed PVC pipe and if required laid through new surface PVC pipe (20 mm dia)  with all accessories. The price includes supplying,installing,connecting,laying, drilling & cutting ( concrete wall if required ) and commissioning to complete works as required.   ","NO.",600,null,0]
[10,"Fluorescent Lighting:                \nSupplying ,Installation, testing and commissioning of prewired fluorescent fittings of all pendant type complete set with tube rod 36W/19mm dia( 4feet) includes wiring/connecting with 1.0 kV grade 2*1.5mm² PVC insulated copper cable/wires laid inside existing concealed PVC pipe and if required laid through new surface PVC pipe (20 mm dia) with 6 A switches  with all accessories. The price includes supplying,installing,connecting,laying, drilling & cutting ( concrete wall if required ) and commissioning to complete works as required.   ","NO.",700,null,0]
[11,"Bracket waterproof wall:           \nSupplying & Installing of bracket waterproof wall  prewired outdoor lighting luminaries suitable for GLS lamp 230VAC/23 watts complete with all accessories such as base, LED drive & LED bulb, glass, reflector, louvered, includes wiring/connecting with 1.0 kV grade 2*1.5mm² PVC insulated copper cable/wires laid inside existing concealed PVC pipe and if required laid through new surface PVC pipe (20 mm dia) with 6 A switches with all accessories. The price includes supplying,installing,connecting,laying, drilling & cutting ( concrete wall if required ) and commissioning to complete works as required.   ","NO.",100,null,0]
[12,"Sub Distribution Boards ( 12 ways):\nSupplying, installing, testing and commissioning of for 12 ways, TPN DB (DIN type, horizontal/vertical) with single door complete set to accommodate incoming miniature circuit breaker (MCCB) triple pole, 1 x 63 Amps, and outgoing SP MCB 9 x 32 Amps on/in prefabricated  MS surface /MS cubical control panel board with neutral strip/bar with all accessories. The price includes supplying, installing, connecting, drilling & cutting ( concrete wall if required ) and commissioning include (cable termination with Cu lugs at end) to complete works as required. ","NO.",43,null,0]
[13,"Outdoor Lighting fixture:\nSupply and install of prewired indoor recessed down light luminaries fixture suitable for GLS/reflector lamp 1x100 watts/230 VAC complete set with all accessories such as base, holder & bulb, glass globe, reflector, fixing clip, etc., includes supplying & laying/connecting of single way (6 Amps) lighting switch with 2x 1.5 mm²,1.0KV grade cable, PVC insulated copper conductor cable laid through PVC conduit pipe (Ø20 mm) with all accessories as circular junction box, square plastic box, adapter with cable holder on walls and ceiling as required. The price includes supplying,installing,connecting,laying, drilling, cutting  and commissioning to complete works as required.","NO.",90,null,0]
[null,"SUB TOTAL FOR ELECTRICAL WORKS",null,null,null,{"$f":"SUM(F72:F84)","v":0}]
[null,"TOTAL",null,null,null,{"$f":"F85+F69+F50","v":0}]