Terms of Reference – National Consultant to conduct a diagnostic situational analysis of Rakhine State

Title: National Consultant to support a diagnostic situational analysis of Rakhine State

Department/Unit: Office of the United Nations Resident Coordinator

Expected Places of Travel: Yangon and Rakhine State

Duration of Assignment: 60 days (from January 2020 to March 2020)

# Background

Myanmar has embarked on a major social and economic transition to achieve a peaceful and more democratic society with greater opportunities for prosperity. The Government is committed to aligning its national priorities with the universally applicable 2030 Sustainable Development Agenda and the Sustainable Development Goals.

While this triple transition has yielded important results in some areas, the Government and the people of Myanmar are facing challenges to end long-lasting armed conflicts and find a model of state that addresses the country’s diversity, promotes socio-economic opportunities for all and addresses the long term and the emerging urgent needs of its population.

The UN system works with the Government and the people in Myanmar across all the UN pillars to achieve peace, security and sustainable development while addressing human rights challenges and providing humanitarian assistance to the people in need.

The UN Resident Coordinator leads the UN Country Team in Myanmar. The purpose of the Resident Coordinator system is to bring together the different UN agencies to improve the efficiency and effectiveness of operational activities at the country level, helping the UN to be a more relevant partner for the government.

The UN Resident Coordinator Office (RCO) supports the roles and functions of the UN Resident Coordinator and UN Country Team. The RCO provides inter-agency coordination support to the UN Country Team (UNCT) and its various inter-agency working mechanisms, including theme groups. Key functions of the RCO include: strategic analysis, planning and positioning of the Country Team; preparation and monitoring of the United Nations Sustainable Development Cooperation Framework; support to joint UN programming and operations management; policy guidance; joint advocacy and communications in order to enhance UN coherence and improve overall programme impact of the UN System.

The UN System in partnership with the Government of Japan provides development and humanitarian assistance to communities living in areas affected by armed and/or ethnic conflict. With a focus on Rakhine, Kachin, and northern Shan states, currently eight UN agencies are delivering development and humanitarian assistance as part of the Japan Supplementary Budget Programme (JSBP) in areas ranging from health to food security, nutrition, housing, inclusive and responsive service delivery, social cohesion, empowerment of women, WASH, protection/gender-based violence, creating the conditions for return of refugees, and promoting durable solutions for internally displaced persons. In the JSBP, the RCO is tasked with inter-agency coordination for coherent programme implementation and reporting, promoting the development, humanitarian and peace nexus approach.

The Muslim community who self-identify as Rohingya have faced decades of systematic discrimination, statelessness and targeted violence in Rakhine state. Such persecution has forced them into Bangladesh for many years. Yet it was August 2017 that triggered by far the largest and fastest refugee influx into Bangladesh. Since then, an estimated 745,000 Rohingya have fled into Cox’s Bazaar. The immediate cause of their flight was described by the UN-mandated Independent International Fact-Finding Mission on Myanmar as a “widespread and systematic attack on [civilians]”.

In August 2017, the Rakhine Advisory Commission (RAC) — formed to support the Government of Myanmar (GoM) in addressing the challenges of Rakhine State — issued an analysis and recommendations for support, highlighting priorities for Rakhine in terms of (i) socioeconomic development that ought to give a voice to local communities in their development process; (ii) the recognition of legal rights to all, including clear, voluntary and equal pathway to citizenship and freedom of movement; (iii) communal participation and representation in decision-making providing scope for women representation; (iv) the return to places of origin or choice of refugees and internally displaced persons (IDPs) in a voluntary, safe, dignified and sustainable manner; and, (v) fostering intercommunal dialogue to strengthen cohesion among the population in Rakhine, and between the state and the Union.

The GoM has accepted the RAC report and established a Committee for the Implementation of Recommendations on Rakhine State (CIRR) in October 2017. The Office of the Resident Coordinator, on behalf of the UN and international partners, has led efforts to support the CIRR and national institutions’ implementation of the RAC recommendations. The UN acknowledges the steps that the Government has undertaken to address the recommendations of the Advisory Commission and reiterates that the UN stands ready to offer more support if given the space and opportunity.

In October 2017, State Counsellor of Myanmar Aung San Suu Kyi further announced the establishment of the Union Enterprise for Humanitarian Assistance, Resettlement and Development in Rakhine to invite local and foreign organizations to work with the GoM towards: (i) the repatriation of those who fled to Bangladesh and the provision of humanitarian assistance; (ii) the resettlement and rehabilitation of refugees; and (iii) the development of the region and the establishment of durable peace.

UN High Commissioner for Refugees (UNHCR), UN Development Programme (UNDP) and the GoM signed a tripartite Memorandum of Understanding (MoU) on 6 June 2018 as a first step to establish a framework for cooperation between the UN and the GoM aimed at creating conducive conditions for the voluntary, safe, dignified and sustainable repatriation of refugees from Bangladesh as well as supporting recovery and resilience-based development for the benefit of all communities living in Rakhine State. The MoU was extended for another year in May 2019.

Against this background, this consultancy is being implemented through the JSBP, in which the RCO is expected to provide assessment on JSBP’s programme contribution to the implementation of RAC recommendations, MSDP (Myanmar Sustainable Development Plan), and Rakhine Strategic Framework.

# Objective

The National Consultant will be responsible for supporting a diagnostic situational analysis of recent developments in Rakhine State, with a focus on the JSBP’s contribution towards achieving the RAC recommendations, MSDP and Rakhine Strategic Framework; identifying needs to be supported considering the overall context, existing programme interventions and comparative advantages and capacities on the ground of each UN agency; and identifying gaps and opportunities to inform future programming, joint advocacy and resource mobilization efforts by examining synergies and linkages created under the programme. The Consultant will also support the facilitation of validation workshops in Sittwe, Rakhine and the capital city of Yangon and one workshop on the results of the diagnostic situational analysis with donors, UN agencies and international non-governmental organizations. The Consultant will work closely with an International Consultant assigned to complete the diagnostic situational analysis, the Coordination and Reporting Specialist in Sittwe and Senior Adviser for Rakhine State, under the overall supervision of the Senior Development Coordination Officer, Strategic Planning and RCO Team Leader based in Yangon.

Expected Key Deliverables and Timelines
A diagnostic situational analysis is an assessment and analysis of the situation that will serve to increase understanding and to identify necessary action on issues affecting the realization of the RAC recommendations, MSDP and Rakhine Strategic Framework. The process will increase understanding on the progress of the above-mentioned goals and frameworks, in particular the implementation of RAC recommendations, with a focus on contribution made by the UN agencies operating in Rakhine State, including as part of the JSBP. Essential elements of the diagnostic situational analysis include: a disaggregated assessment of the status of RAC recommendations and trends; an analysis of the immediate, underlying and structural causes of the disparities across various groups; how the UN agencies including JSBP activities are contributing to the achievement of the RAC recommendations; where there are gaps and opportunities; and concrete policy and programmatic recommendations to address the disparities and accelerate progress. Considering sensitivities around the issues in Rakhine State, the analysis should be nuanced and contextualized based on thorough understanding of the recent developments and the reality on the ground, followed by actionable recommendations.

More specifically, the purpose of conducting a diagnostic situational analysis is as follows:

- Improve the understanding of decision-makers, partners and all other relevant stakeholders of the current status of the RAC recommendations and the causes of shortfalls and inequities, as the basis for recommending actions for further support from the RCO, UN, and international partners, to support principled implementation of the recommendations.

- Support planning and development processes, including influencing policies, strategies, and budgets to contribute towards an enabling environment for the RAC recommendations.

- Strengthen the knowledge base to support the programming, joint advocacy and resource mobilization efforts for UN agencies and other relevant stakeholders in Rakhine State.

- Contribute to national research and leverage UNRCO’s power to foster and support knowledge generation with government, civil society and private sector stakeholders.

In order to fulfill the above, the diagnostic situational analysis process should include the following.

- Completion of a desk review, including of research carried out by UN agencies and other partners and use of available data and other information to accurately identify recent trends, patterns, incidence and causes of key deprivations, disaggregated by relevant segments of the population in the evolving situation on the ground.

- Identification and analysis of the barriers and bottlenecks that prevent vulnerable people in Rakhine State from benefiting from required interventions and services, including the social, political and economic conditions that result in shortfalls in the creation of an enabling environment for the realization of the RAC recommendations.

- Assessment of the extent to which UN agencies’ interventions including the JSBP have been contributing to the realization of RAC recommendations, MSDP and Rakhine Strategic Framework through a participatory approach.

- Identification of needs to be supported considering the overall context, existing programme interventions and comparative advantages and capacities on the ground of each UN agency.

- Analysis of synergies and interlinkages across different sectors and identify gaps and opportunities for better collaboration of different actors in order to better contribute to the achievement of above frameworks.

| Ref | Key Tasks | Deliverables | Estimated Timelines |
| --- | --- | --- | --- |
| 1 | Support collection and review of available publications (relevant to the scope & breadth of the diagnostic situational analysis ToR), and identification of key gaps in the information base. | Summary of publications relevant for the situational analysis | 5 days |
| 2 | Support the preparation of a final and agreed conceptual and analytical framework for the situational analysis based on this ToR. | Conceptual and analytical framework for the situational analysis | 3 day |
| 3 | Support a review of all relevant data sources and preparation of a situational analysis inception report that summarizes the following: methodology; availability of data sources, clustered by thematic focus areas; information gap analysis; and, schedule of activities and timeline | Draft and finalize an inception report with all the drafted background papers annexed | 3 days |
| 4 | Support key component analyses based on field work including visit to project sites, IDP camps, key informant interviews, and focal group discussions to capture various stakeholders’ viewpoints. Conduct additional research and analysis as required and produce a research paper, according to methodology agreed in conceptual and analysis framework. | Field work in Rakhine state and analysis | 25 days |
| 5 | Support the development of a complete draft situational analysis report. | Draft report available for review by UNRCO | 6 days |
| 6 | Support validation of the situational analysis findings through a participatory approach with a cross-section of stakeholders in Sittwe and Yangon. | Facilitation of workshops | 2 days |
| 7 | Support production of a final report of the situational analysis, integrating inputs from the validation workshops and comments on the first draft, with accompanying background papers according to an agreed format. | Final situational analysis report | 6 days |
| 8 | Support the preparation of materials for and facilitate dissemination workshop of situational analysis results. | Dissemination workshop | 3 day |
| 9 | Support the production of a situational analysis report including main findings and recommendations. | Final report | 7 days |

# Resources and working arrangements

The consultant will be provided with a working station and connectivity as when required.

# Education, experience, competencies & language skills

## Education and experience

- Bachelor’s degree with minimum of five years demonstrated experience in stated field or master’s degree or equivalent in social sciences (such as political sciences, economics, peace and conflict studies, international relations, public policy, sociology, development studies) or related fields relevant for the assignment with minimum of three years of experience.

- Outstanding ability to gather relevant information and analyze political dynamics and socio-economic development in fragile contexts including conflict and/or post conflict situations.

- Excellent facilitation and interview skills.

- Proven experience in writing analytical papers and/or reports.

- Familiarity with the UN’s work at the country level.

- Programme-related experience such as planning and/or evaluating humanitarian and/or development projects and/or programmes at a country level highly desirable.

- Familiarity with development-humanitarian-peace nexus approach an asset.

- Familiarity with Rakhine State context an asset.

## Competencies

- Excellent communication, networking and negotiation skills;

- Ability to deliver quality reports/analysis and results in line with established deadlines;

- Demonstrated ability to work with minimum supervision, be dynamic and proactive;

- Understanding of key issues in the delivery of development and humanitarian assistance;

- Ability to work in diverse teams with cultural, gender, religion, race, nationality, and age sensitivity;

- Demonstrated openness to change and ability to manage complexities; and

- Excellent computer skills.

## Language skills

- Fluency in oral and written English and Myanmar languages.

The consultant will be asked to submit 2 samples of previous comparable work produced and at least 3 references.

# Evaluation

## Cumulative analysis

The proposals will be evaluated using the cumulative analysis method with a split 70% technical and 30% financial scoring.

The proposal with the highest cumulative scoring will be awarded the contract.

Applications will be evaluated technically, and points are attributed based on how well the proposal meets the requirements of the Terms of Reference using the guidelines detailed in the table below: When using this weighted scoring method, the award of the contract may be made to the individual consultant whose offer has been evaluated and determined as:

- Responsive/compliant/acceptable, and

- Having received the highest score out of a pre-determined set of weighted technical and financial criteria specific to the solicitation.

Technical Criteria weighting: 70%

Financial Criteria weighting: 30%

Only candidates obtaining a minimum of 49 points in the Technical Evaluation would be considered for the Financial Evaluation.

Interviews may be conducted as part of technical assessment for shortlisted proposals.

| Criteria | Points | Percentage |
| --- | --- | --- |
| Qualification |  | 30% |
| Advanced university degree in social sciences and 3 years of experience or bachelor’s degree and 5 years of experience. | 30 |  |
| Experience |  | 30% |
| Ability to gather relevant information and analyze political dynamics and socio-economic development in fragile contexts including conflict and/or post-conflict situations. | 10 |  |
| Proven experience in writing analytical papers or reports. | 10 |  |
| Familiarity with the UN’s work at the country level. | 10 |  |
| Competencies |  | 10% |
| Excellent communication, networking and negotiation skills; Ability to deliver quality reports/analysis and results in line with established deadlines; Demonstrated ability to work with minimum supervision, be dynamic and proactive; Understanding of key issues in the delivery of development and humanitarian assistance; Ability to work in diverse teams with cultural, gender, religion, race, nationality, and age sensitivity; Demonstrated openness to change and ability to manage complexities; and Fluency in oral and written English and Myanmar language | 1 1 1 2 1 1 3 |  |
| Technical Criteria *If necessary, interviews shall also be conducted as part of the technical evaluation to ascertain best value for money. |  | 70% |
| Financial Criteria – Lowest Price |  | 30% |
| Total |  | 100% |

# Documents to be included when submitting Consultancy Proposals

The following documents may be requested;

  - Duly accomplished Letter of Confirmation of Interest and Availability using the template provided by UNDP (Separate file from technical proposal (P11 and Brief description), password protected). Password for financial proposal must not be provided to UNDP until requested by UNDP. The Technical Proposal shall not include any price or financial information. A Technical Proposal containing material financial information may be declared non-responsive.

  - Signed P11, indicating all past experience from similar projects, as well as the contact details (email and telephone number) of the Candidate and at least three (3) professional references;

  - Brief description of why the individual considers him/herself as the most suitable for the assignment, and a methodology, if applicable, on how they will approach and complete the assignment. A methodology is recommended for intellectual services, but may be omitted for support services (Limit of 500 characters)

  - Financial Proposal that indicates the all-inclusive fixed total contract price, supported by a breakdown of costs, as per template provided. If an Offeror is employed by an organization/company/institution, and he/she expects his/her employer to charge a management fee in the process of releasing him/her to UNDP under Reimbursable Loan Agreement (RLA), the Offeror must indicate at this point, and ensure that all such costs are duly incorporated in the financial proposal submitted to UNDP. The financial proposal must be submitted separately from other documents and password protected. Password for financial proposal must not be provided to UNDP until requested by UNDP.

## Lump sum contracts

The financial proposal shall specify a total lump sum amount, and payment terms around specific and measurable (qualitative and quantitative) deliverables (i.e. whether payments fall in instalments or upon completion of the entire contract). Payments are based upon output, i.e. upon delivery of the services specified in the TOR. In order to assist the requesting unit in the comparison of financial proposals, the financial proposal will include a breakdown of this lump sum amount (including travel, living expenses, and number of anticipated working days).

## Travel

All envisaged international travel costs must be included in the financial proposal. This includes all travel to join duty station/repatriation travel. In general, UNDP should not accept travel costs exceeding those of an economy class ticket. Should the Consultant wish to travel on a higher class he/she should do so using their own resources. Domestic travels will be arranged, and the related cost borne by the office.

In the case of unforeseeable travel, payment of travel costs including tickets, lodging and terminal expenses should be agreed upon, between the respective business unit and Consultant, prior to travel for reimbursement.