## BoQ
BIIL OF QUANTITIES
No | Description | Unit | Quantity | Unit Price (US$) | Amount (US$)
1 | 2 | 3 | 4 | 5 | 6=4X5
I | Preparation Works
1 | Mobilization and Demobilization | ls | 1
2 | Project Sign Board (1000x1200mm) | ls | 1
3 | Reporting and Documentation | ls | 1
Sub Total - I
II | Demolition Work
1 | Removed existing ventilation at Yoga room and cafe | unit | 6
2 | Removed existing door at Yoga room | unit | 1
3 | Removed existing window at Yoga room | unit | 1
4 | Demolish existing concrete wall at Yoga room - 2000mm from top beam included disposal | m2 | 60
5 | Demolish existing partition wall between Yoga room and cafe | m2 | 23.7
Sub Total - II
III | Stone Masonry and Concrete Work
1 | Concrete pouring at table tennis room | m3 | 1.68
2 | Repair and make good all concrete cracked at recreation area | ls | 1
Sub Total - III
IV | Tile Work
1 | Install new ceramic tile 600x600mm at meeting room and Caffe | m2 | 215.3
2 | Install new squinting tile 100x600mm at meeting room and Caffe | m1 | 102
Sub Total - IV
V | Ceiling Work
1 | Repair existing ceiling frame at meeting room and cafe | ls | 1
2 | Install new kalciboard ceiling, 6mm thickness at meeting room and cafe | m2 | 222
3 | Install new ceiling squirting at meeting room and cafe | m1 | 145
Sub Total - V
VI | Wall, Door and Window Work
1 | Supply and install new glasses 5mm thickness wall partition include frame (aluminum frame) and all accessories at meeting room and café | m2 | 81.9
2 | Supply and install new folding door (2300mm x 6000mm) frame by aluminum and leaf by glasses with all accessories, between meeting room and café | Unit | 1
3 | Supply and install new sliding glasses door with aluminum frame include all accessories | unit | 2
Sub Total - VI
VII | Furniture and Others Work
1 | Supply and install new Bar Table at Café room - material by wooden, see drawing | unit | 1
2 | Install new zinc at kitchen include all accessories | unit | 1
Sub Total - VII
VIII | Electrical and Mechanical Work
1 | Repair and fix electrical accessories (Switches, outlet, ceiling fan etc..) | ls | 1
2 | Install new TL LED lighting 2x18watt covered with acrylic at meeting room and cafe area | unit | 15
3 | Install new TL LED lighting 2x18watt with acrylic cover at stage area | unit | 6
4 | Ceiling Paint | m2 | 118.54
Sub Total VIII
IX | Painting
18 | Interior and exterior painting for meeting room and Caffe | m2 | 0
17 | Ceiling paint for meeting room and Caffe | m2 | 92
5 | Interior and exterior painting | m2 | 85.12
4 | Ceiling Paint | m2 | 65
Sub Total IX
GRAND TOTAL

## SUMMARY BoQ
SUMMARY OF WORKS TO BE CONDUCTED
NO | DESCRIPTION | Total Amount (US$)
1 | 2
I | Preparation Works
II | Demolition Work
III | Stone Masonry and Concrete Work
IV | Tile Work
V | Ceiling Work
VI | Wall, Door and Window Work
VII | Furniture and Others Work
VIII | Electrical and Mechanical Work
IX | Painting
GRAND TOTAL

## Time Schedule
Annex 4 - TIME SCHEDULE
No | Description | WEEK
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
I | Preparation Works | bar: WEEK 1
II | Demolition Work | bar: WEEK 2
III | Stone Masonry and Concrete Work | bar: WEEK 3
IV | Tile Work | bar: WEEK 3 to WEEK 4
V | Ceiling Work | bar: WEEK 4 to WEEK 5
VI | Wall, Door and Window Work | bar: WEEK 5 to WEEK 8
VII | Furniture and Others Work | bar: WEEK 2 to WEEK 5
VIII | Electrical and Mechanical Work | bar: WEEK 8 to WEEK 9
IX | Painting | bar: WEEK 10