REQUEST FOR QUOTATION (RFQ)

| UNDP BIH Zmaja od Bosne bb; Sarajevo | DATE: 14th February 2020 |
| --- | --- |
|  | REFERENCE: BIH/RFQ/014/20 |

Dear Sir / Madam:

We kindly request you to submit your quotation for:

Supervision over the construction of water - tower in Domaljevac – Šamac Municipality, Bosnia and Herzegovina

When preparing your quotation, please be guided by the form attached hereto as Annex 1 and Annex 2.

# Quotations may be submitted on or before 25th February 2020, 17:00 h, via courier mail to the address below:

# United Nations Development Programme

Zmaja od Bosne bb, Sarajevo 71000

General Service

Ref: BIH/RFQ/014/20

It shall remain your responsibility to ensure that your quotation will reach the address above on or before the deadline. Quotations that are received by UNDP after the deadline indicated above, for whatever reason, shall not be considered for evaluation.

Please take note of the following requirements and conditions pertaining to the supply of the abovementioned service/s:

| Delivery Terms [INCOTERMS 2010] (Pls. link this to price schedule) | N/A |
| --- | --- |
| Exact Address/es of Delivery Location/s (identify all, if multiple) | Municipality of Domaljevac - Šamac (more detailed in Anex II) |
| UNDP Preferred Freight Forwarder, if any | n/a |
| Distribution of shipping documents (if using freight forwarder) | n/a |
| Latest Expected Delivery Date and Time (if delivery time exceeds this, quote may be rejected by UNDP) | Service to be completed within 180 calendar days in period from March 2020 until September 2020 following the contarct commencement date |
| Preferred Currency of Quotation | Local Currency: BAM |
| Value Added Tax on Price Quotation | Must be exclusive of VAT and other applicable indirect taxes; (VAT and custom stated separately) |
| Deadline for the Submission of Quotation | Tuesday , February 25, 2020, 17:00 h |
| All documentations, including catalogs, instructions and operating manuals, shall be in this language | Local language and/or English |
| Documents to be submitted | •Certified copy of bidder’s registration (Ovjerena kopija registracije ponuđača) •Certified copies of Bidder’s license for preparation of project documentation for hydrotechnical buildings and installations issued by the relevant institution- Federal Ministry of physical planning (Ovjerena kopija licence ponuđača za za projektovanje građevina i zahvata iz područja hidrotehnike koju izdaje Federalno ministarstvo prostornog uređenja •Reference list indicating successfully implemented projects of similar nature and complexity within the last 5 (five) years on the company memorandum letter; (Referens lista na memorandum firme u kojoj se naznačuju uspješno realizovani projekti slične prirode i kompleksnosti u toku posljednjih 5 (pet) godina) •Purchasers’ recommendation letters indicating the value, nature complexity and date of project completion, for at least 2 (two) projects implemented within the last 5 (five) years. Letters should include purchasers’ contact details. (Pisma preporuke od naručilaca, sa naznačenom vrijednošću, kompleksnošću i datumom završetka projekta, za najmanje 2 (dva) projekta realizovana u posljednjih 5 (pet) godina. Pisma trebaju sadržati kontakt detalje naručioca.) •List of team members to be engaged for the contract (names, education, skills, years of experience); (Lista članova tima koji će biti angažovani na ovo poslu (imena, obrazovanje, vještine, godine iskustva)) •Original certificate issued by relevant Tax Administration Office (for bidders registered in Bosnia and Herzegovina) or other authorized government body, confirming contributions paid for all registered (full-time) employees, not older than three months. The certificate must attain the certified list of employees; (Original izvod iz Poreske uprave (za ponuđače registrovane u Bosni i Hercegovini) ili druge ovlašćenog vladinog organa, kojom se potvrđuju doprinosi uplaćeni za sve registrovane stalno zaposlene, ne stariji od tri mjeseca. Izvod mora sadržavati ovjerenu listu uposlenika) •CV of each team member with references and letters of recommendation; (CV (životopis) svakog člana tima sa referensama i pismima preporuke) •Copies of professional exam certificates for each team member; (Kopije uvjerenja o položenom stručnom ispitu za svakog člana tima) •Statement on availability and exclusivity during the entire contracted period, signed by each team member; (Izjava o raspoloživosti i ekskluzivnosti za čitavo vrijeme trajanja ugovora, potpisana od strane svakog člana tima) |
| Period of Validity of Quotes starting the Submission Date | 240 days In exceptional circumstances, UNDP may request the Proposer to extend the validity of the Quotation beyond what has been initially indicated in this RFQ. The Proposer shall then confirm the extension in writing, without any modification whatsoever on the Proposal. |
| Partial Quotes | Partial Quotes are not permitted |
| Payment Terms | Upon succesfuly perfomed services |
| Evaluation Criteria | Technical responsiveness/Full compliance to requirements Lowest priced technically responsive quotation Company must have: •Registration to perform the requested services as a legal entity; (Registracija pravnog lica za obavljanje predmetnih usluga) •Authorisation for services of design and supervision over the subject works as a legal entity, issued by relevant government authority and valid at minimum until the end of the construction period; (Ovlaštenje pravnog lica za obavljanje poslova projektovanja i nadzora nad izvođenjem predmetnim radova, izdata od strane relevantnog organa vlasti i važeća najmanje do kraja perioda predviđenog za građenje) •At least two successfully implemented projects within the last 5 (five) years, related to design and/or supervision over the execution of the subject works on projects of similar nature and complexity, as a legal entity. (Najmanje 2 (dva) uspješno realizovana projekta od strane pravnog lica u toku posljednjih 5 (pet) godina vezana za projektovanje i/ili nadzor nad izvođenjem predmetnih radova na projektima slične prirode i kompleksnosti ) Team composition and competences of the team members: Sastav i kompetencije članova tima: •One graduate civil engineer (construction) - Lead supervisor, full time employed, with professional exam certificate, with min 10 years of experience in design and supervision over the construction works on buildings of similar nature and complexity (Jedan diplomirani građevinski inženjer (konstruktivni smijer) - vodja tima, stalno zaposlen kod pružaoca usluga, sa položenim stručnim ispitom, sa najmanje 10 godina iskustva u projektovanju I nadzoru nad izvođenjem građevinskih radova na objektima iste ili slične prirode I kompleksnosti •One graduate civil engineer (construction), full time employed, with professional exam certificate, with min 5 years of experience in design and supervision over the construction works on buildings of similar nature and complexity (Jedan diplomirani građevinski inženjer (konstruktivni smijer), stalno zaposlen kod pružaoca usluga, sa položenim stručnim ispitom, sa najmanje 5 godina iskustva u projektovanju I nadzoru nad izvođenjem građevinskih radova na objektima iste ili slične prirode I kompleksnosti •One graduate civil engineer (hydro), full time employed or engaged under contract with Service Provider, with professional exam certificate, with min 5 years of experience in design and supervision over the construction works on buildings of similar nature and complexity (Jedan diplomirani građevinski inženjer (hidro smijer), stalno zaposlen kod pružaoca usluge ili angažovan po ugovoru o poslovno tehničkoj saradnji, sa položenim stručnim ispitom, sa najmanje 5 godina iskustva u projektovanju I nadzoru nad izvođenjem građevinskih radova na objektima iste ili slične prirode I kompleksnosti •One graduate electrical engineer, full time employed or engaged under contract with Service Provider, with professional exam certificate, with min 5 years of experience in design and supervision over the execution of electrical installations on buildings of similar nature and complexity (Jedan diplomirani elektro inženjer, stalno zaposlen kod pružaoca usluga ili angažovan po ugovoru o poslovno tehničkoj saradnji, sa položenim stručnim ispitom, sa najmanje 5 godina iskustva u projektovanju I nadzoru nad izvođenjem građevinskih radova na objektima iste ili slične prirode I kompleksnosti •One graduate electrical engineer (automatic control and electronic), full time employed or engaged under contract with Service Provider, with professional exam certificate, with min 5 years of experience in design and supervision over the execution of electrical installations on buildings of similar nature and complexity (Jedan diplomirani elektro inženjer (atomatika I elektronika), stalno zaposlen kod pružaoca usluga ili angažovan po ugovoru o poslovno tehničkoj saradnji, sa položenim stručnim ispitom, sa najmanje 5 godina iskustva u projektovanju I nadzoru nad izvođenjem građevinskih radova na objektima iste ili slične prirode I kompleksnosti •One graduate mechanical engineer, full time employed or engaged under contract with Service Provider, with professional exam certificate, with min 5 years of experience in design and supervision over the execution of electrical installations on buildings of similar nature and complexity (Jedan diplomirani masinski inženjer, stalno zaposlen kod pružaoca usluga ili angažovan po ugovoru o poslovno tehničkoj saradnji, sa položenim stručnim ispitom, sa najmanje 5 godina iskustva u projektovanju I nadzoru nad izvođenjem građevinskih radova na objektima iste ili slične prirode I kompleksnosti *NOTE: Official version of RFQ document is in English, while attached partial translation into local language is only for courtesy translation. In case of different interpretation, English version will prevail. *NAPOMENA: Zvanična verzija RFQ dokumenta je na engleskom jeziku, dok su djelomični prevodi na lokalnom jeziku priloženi iz kurtoazije. U slučaju razlika u prevodu, engleska verzija će preovladati. |
| UNDP will award to: | Only one service provider, depending on the following factors: Technical responsiveness/Full compliance to requirements Lowest priced offer of technically qualified/responsive Bid |
| Type of Contract to be Signed | Contract for Services |
| Special conditions of Contract | n/a |
| Conditions for Release of Payment | Based upon Invoices submitted by the Contractor and Interim Payment Certificates issued by the Engineer, UNDP shall make progress payments. The period covered by each Invoice shall be twenty days during the Time for completion. Invoices shall indicate the percentage of completion of each portion of Services as of the end of the period covered by the Invoice. UNDP shall effect payments to the Contractor for performed services within 30 (thirty) days of the date of their receipt and acceptance by UNDP. |
| Annexes to this RFQ | -Form for Submission of Quotation (Annex I) -Detailed ToR, Technical description and design documentation (Annex II and Annex II a) provided as separated documents. -General Terms and Conditions/Special Conditions (Annex III) Non-acceptance of the terms of the General Terms and Conditions (GTC) shall be grounds for disqualification from this procurement process. General Terms and Conditions/Special Conditions (Annex 3): Link: English version Non-acceptance of the terms of the General Terms and Conditions (GTC) shall be grounds for disqualification from this procurement process. |
| Contact Person for Inquiries (Written inquiries only) | UNDP BIH - GENERAL SERVICES registry.ba@undp.org Tel: 033 293 400 Fax: 033 552 330 Any delay in UNDP’s response shall be not used as a reason for extending the deadline for submission, unless UNDP determines that such an extension is necessary and communicates a new deadline to the Proposers. |
| Other information | The required services include but not limit to the following: 1.Supervision over compliance of construction works with the contracted Bill of Quanities, Detail Design documents, Entity Spatial Planning and Construction Acts and relevant by-laws, technical regulations, general and special technical conditions and professional codes; 2.Supervision over the quality of construction works and quantity of the in-built materials; 3.Verification of the interim and final payment certificates; 4.Review and signing of the daily construction log and construction book of measurements; 5.Supervision over the completion deadlines; 6.Preparation of reports on the status of works; 7.Preparation of the final supervision report. 8.Participation in the technical inspection and takeover of the facility; For more details please see attached ToR (Annex II and Annex IIa) and Annex 1 Expected duration of work is throughout the months of March 2020 – September 2020 For more details please see attached ToR (Annex II and Annex IIa). Target start date is 01 March 2020. |

Goods offered shall be reviewed based on completeness and compliance of the quotation with the minimum specifications described above and any other annexes providing details of UNDP requirements. The quotation that complies with all of the specifications, requirements and offers the lowest price, as well as all other evaluation criteria indicated, shall be selected.  Any offer that does not meet the requirements shall be rejected.

Any discrepancy between the unit price and the total price (obtained by multiplying the unit price and quantity) shall be re-computed by UNDP.  The unit price shall prevail and the total price shall be corrected.  If the supplier does not accept the final price based on UNDP’s re-computation and correction of errors, its quotation will be rejected.

After UNDP has identified the lowest price offer, UNDP reserves the right to award the contract based only on the prices of the goods in the event that the transportation cost (freight and insurance) is found to be higher than UNDP’s own estimated cost if sourced from its own freight forwarder and insurance provider.  At any time during the validity of the quotation, no price variation due to escalation, inflation, fluctuation in exchange rates, or any other market factors shall be accepted by UNDP after it has received the quotation.

At the time of award of Contract or Purchase Order, UNDP reserves the right to vary (increase or decrease) the quantity of services and/or goods, by up to a maximum twenty five per cent (25%) of the total offer, without any change in the unit price or other terms and conditions.

Any Purchase Order that will be issued as a result of this RFQ shall be subject to the General Terms and Conditions attached hereto. The mere act of submission of a quotation implies that the vendor accepts without question the General Terms and Conditions of UNDP herein attached as Annex 2.

UNDP is not bound to accept any quotation, nor award a contract/Purchase Order, nor be responsible for any costs associated with a Supplier’s preparation and submission of a quotation, regardless of the outcome or the manner of conducting the selection process.

Please be advised that UNDP’s vendor protest procedure is intended to afford an opportunity to appeal for persons or firms not awarded a purchase order or contract in a competitive procurement process.  In the event that you believe you have not been fairly treated, you can find detailed information about vendor protest procedures in the following link: http://www.undp.org/procurement/protest.shtml

UNDP encourages every prospective Vendor to avoid and prevent conflicts of interest, by disclosing to UNDP if you, or any of your affiliates or personnel, were involved in the preparation of the requirements, design, specifications, cost estimates, and other information used in this RFQ.

UNDP implements a zero tolerance on fraud and other proscribed practices and is committed to identifying and addressing all such acts and practices against UNDP, as well as third parties involved in UNDP activities.  UNDP expects its suppliers to adhere to the UN Supplier Code of Conduct found in this link: http://www.un.org/depts/ptd/pdf/conduct_english.pdf

Thank you and we look forward to receiving your quotation.

Sincerely yours,

UNDP BIH

Annex I

FORM FOR SUBMITTING SUPPLIER’S QUOTATION

(This Form must be submitted only using the Supplier’s Official Letterhead/Stationery)

We, the undersigned, hereby accept in full the UNDP General Terms and Conditions, and hereby offer to supply the items listed below in conformity with the specification and requirements of UNDP as per RFQ Reference BIH/RFQ/014/20:

Supervision over the construction of water - tower in Domaljevac – Šamac Municipality, Bosnia and Herzegovina

- Cost Breakdown by Cost Component (in Bosnian Convertible Marks – BAM):

| Supervision over the construction of water - tower in Domaljevac – Šamac Municipality |
| --- |
| Description of Activity | Remuneration per day (all inclusive) | Total Period of Engagement/ PERSON DAYS | No. of Personnel | Total Rate for the Period |
| I. Personnel Services |  |  |  |  |
| 1. Services on production hall, supervision of production of water-tower elements (over the period of 150 calendar days) |
| 1.1 Lead Supervisor/civil engineer – construction (1 engineer) |  | 30 | 1 |  |
| 1.2 Site works supervisor, civil engineer-construction (1 engineer) |  | 30 | 1 |  |
| 2. Services on Construction site, supervision on site in Domaljevac (over the period of 90 days) |
| 1.1 Lead Supervisor/civil engineer – construction (1 engineer) |  | 14 | 1 |  |
| 1.2 Site works supervisor, civil engineer-construction (1 engineer) |  | 14 | 1 |  |
| 1.3 Site works supervisor, civil engineer-hydro (1 engineer) |  | 8 | 1 |  |
| 1.4 Electrical installations supervisor (1 engineer) |  | 8 | 1 |  |
| 1.5 Electrical installations supervisor -automatic control (1 engineer) |  | 8 | 1 |  |
| 1.6 Mechanical installations supervisor (1 engineer) |  | 8 | 1 |  |
| 3. Services from Home Office (over the period of 180 days) |
| 1.1 Lead Supervisor/civil engineer – construction (1 engineer) |  | 12 | 1 |  |
| 1.2 Site works supervisor, civil engineer-construction (1 engineer) |  | 6 | 1 |  |
| 1.3 Site works supervisor, civil engineer-hydro (1 engineer) |  | 3 | 1 |  |
| 1.4 Electrical installations supervisor (1 engineer) |  | 3 | 1 |  |
| 1.5 Electrical installations supervisor -automatic control (1 engineer) |  | 3 | 1 |  |
| 1.6 Mechanical installations supervisor (1 engineer) |  | 3 | 1 |  |
| TOTAL cost |  |

- TOTAL cost

| Description of Activity | TOTAL (BAM) without VAT | VAT Amount (17 %) | TOTAL with VAT |
| --- | --- | --- | --- |
| Supervision over the construction of water – tower in Domaljevac – Šamac Municipality (all inclusive) |
| TOTAL |  |  |  |

Offer to Comply with Other Conditions and Related Requirements

| Other Information pertaining to our Quotation are as follows: | Your Responses |
| --- | --- |
|  | Yes, we will comply | No, we cannot comply | If you cannot comply, pls. indicate counter proposal |
| Delivery Lead Time: 180 calendar days for completion of works |  |  |  |
| Total Period of Engagement/ PERSON DAYS: 150 (one hundred fifty) engineers business days, as divided in Cost breakdown by Cost Components table |  |  |  |
| Validity of Quotation: 120 days |  |  |  |
| All Provisions of the UNDP General Terms and Conditions |  |  |  |

All other information that we have not provided automatically implies our full compliance with the requirements, terms and conditions of the RFQ.

[Name and Signature of the Supplier’s Authorized Person]

[Date]

Annex II

Terms of Reference

SCOPE OF WORK

The following scope of work is the subject of supervision services:

- Construction works on finalization of water – tower in Domaljevac-Šamac municipality.

The first phase of water – tower construction was performed by Domaljevac-Šamac municipality authorities, during 2018 – 2019. That include water – tower foundations, water - well and reservoir facility.

Subject of this tender procedure is finalization of the works on water – tower, that include:

- steel structure construction of water – tower, production of steel elements in production hall and assembly on site in Domaljevac-Šamac

- electrical and water installations

- automatic control

- landscaping and infrastructure works

- Planned duration of supervising service is over the period of 180 calendar days. Supervising service is divided in three phases, as stated in Cost breakdown by Cost Components table:

- Services on production hall – Supervision of production of water – tower elements (over the period of 150 calendar days). Production hall is distanced up to cca 150 km.

- Services on Construction site - Supervision over site works in Domaljevac-Šamac (over the period of 90 days)

- Services from Home Office (over the period of 180 days)

Please refer to attached Gantogram in Annex II a.

Project Design and General and Technical Conditions for Works within Ammunition Storage Sites are provided at the following link:

http://documents.undp.ba/procurement/BIH-RFQ-014-20.zip

To fulfill and conduct supervision of the works, the following activities shall be carried out:

Preparatory activities:

- Audit of the Bill of Quantities, Contract document with General Terms and Conditions for Works in terms of their completeness,

- Survey of the production facilities with the Investor and the Contractor(s).

Supervision of works:

- Technical consulting with the Contractor(s) and the Investor,

- Supervision of regular execution of works in accordance with the construction standards, as well as written instructions and regulations,

- Control of fulfillment of certain requirements giving instructions to the Contractor(s),

- Pointing out to any violations of construction regulations by responsible Contractor(s) and the Contractor’s experts, especially when failing to comply with safety-at-work regulations, fire-protection regulations as well as General and Technical Conditions,

- Pointing out severe defects, danger of delays in the form of written notification to UNDP’s Contract Administrator, with a request for further instructions,

- Providing to the UNDP proposals about the necessary removal of unsuitable representatives of the Contractor(s),

- Control of development and implementation of the construction time schedule plan, supervision of construction deadlines,

- Should the Contractor be responsible for the delay, a proposal to the UNDP on defining a new deadline for completion of the Contract and notification of occurrence of contractual penalties,

- Inspection of the delivered construction material, construction elements concerning their completeness and compliance with contractual requirements (required standards, compliance with offered factory products, certificates of compliance, etc.),

- Preparation of conclusions necessary for calculation in accordance with the sequence of works,

- Control of submitted accounts of units and quantities, verification of correctness of deliveries and executed works and financial control of invoices,

- Control of submitted certificates for payments and for determination of the account payable,

- Providing expert statements on delivery and works not included in the Contract(s).

Submission of reports/ notices:

- Keeping the necessary archive or registry of all documents within the responsibility of expert supervision,

- Establishing and keeping the construction log,

- Submission of the inception report, the interim reports (weekly) and the final report to the UNDP on the execution of the planned works as well as special reports, if necessary,

- Proper and timely notification to the UNDP of all important circumstances of the quality and quantity of works, construction that is non-compliant to the regulations and professional code, construction non-compliant to the project designs, delay or acceleration of construction deadlines, improper keeping of the construction log and time-book, improper invoicing in the interim and final certificates, potential occurrence or occurrence of damage, potential occurrence or occurrence of force majeure, defects of construction and other important issues and especially of the causes, quantities and need to execute unforeseen works, additional works, increase or decrease of quantity of works in relation to the contracted Bill of Quantities or the Contract Price.  Supervision service provider is not authorized to approve any unforeseen works, additional works, or increase or decrease of quantity of works.

Handover and completion of construction works:

- Preliminary and final inspection of overall construction works, or each completed section of works, together with the Investor and the Contractor(s) and preparation of minutes with the set deadlines for removal of possible deficiencies,

- Instructions to the operating staff based on manufacturer’s operation and maintenance manuals submitted by the Contractor(s),

- Participation in the final inspection and handover of the reconstructed facilities.

Technical Documentation:

In terms of executing expert supervision, Supervision service provider should ensure and check whether the Contractor has furnished the construction site with the following:

- Construction Contract(s) (original/ copy),

- Decision on Entry into the Court Register or Trade License of the Contractor(s),

- Notice of appointment of the Main Site Engineer, Site Engineer i.e. Construction Manager,

- Notice of appointment of the Supervising Engineers i.e. Main Supervising Engineer,

- List of employees at the site,

- Construction log, time-book, bills of quantity,

- Proofs of compliance for installed construction products in accordance to the applicable laws,

- Necessary certification of the constructed parts of the facility and current construction and other works in progress,

- Site-specific safety plan,

- Supervising engineer’s report for final payment certificate,

- Written statement of the Contractor on executed works and conditions for the maintenance of the facility,

- Supervising engineer’s reports following the execution of works,

- Other documents permits and approvals as prescribed by general and special national regulation regulations.

The Contractor shall be notified of the appointment of experts supervision.

Presence at the Construction Site:

Working hours for supervision and providing instructions concerning construction and time spent on the construction site should be determined and allocated so that all tasks can be fulfilled diligently and conscientiously.

The travel costs will be paid by Supervision service provider.

Duration of Supervision:

Construction supervision starts with issuance of the Notice to Commence by UNDP’s Contract Administrator to the Contractor.

The Contract(s) for the execution of works is expected to begin works on 01 March 2020. The deadline for the completion of works is 31 August 2020 with possibility of deadline extension due to weather conditions. The estimated engagement for the supervision services is over the period of 180 (one hundred eighty) calendar days, with total of 150 (one hundred fifty) engineers business days, as divided in Cost breakdown by Cost Components table.

Supervision is conducted under the obligation of duration to the end of control of calculation and possible legal dispute related to the construction.

Management and Hierarchy:

The Supervision service provider is the representative of the Investor (UNDP) at the site.

Supervision service provider cannot be employee of the Construction Contractor neither connected to Construction Contractor in any way. For this reason, Supervision service provider must not perform any activity which would place him/ her in the domain of or make him/ her responsible to the Contractor. Supervision service provider is thus not responsible to the Construction Manager for organization of the construction site.

For any alterations to the Bill of Quantities, Contract document with General Terms and Conditions for Works, Supervision service provider shall obtain prior consent of the Investor (UNDP).

Annex II a

TECHNICAL DESCRIPTION, GANTOGRAM AND DESIGN DOCUMENTATION

http://documents.undp.ba/procurement/BIH-RFQ-014-20.zip

Annex III

General Terms and Conditions for Services

Link: English version