PROJECT: RENOVATIONS OF STATE REVENUE OFFICES

SCOPE OF WORK

This document serves as a Scope of Work (SOW) to the Independent Contractor Agreement for the renovation of State Revenue Authority Offices in Malakal, Bentiu, Wau and Rumbek

1.         Description of Services.

Location: Contractor (s) agree(s) to perform all required contracting Services relating to the renovation of State Revenue Authority Offices in Malakal, Bentiu, Wau and Rumbek, South Sudan. Supplying all required materials in good quality, providing labour, while executing works taking all precaution to damage any kind of property.

Method of Performing Services: Contractor will determine the method, details, and means of completing the Project. Contractor (s) agree(s) to devote the required personnel for a minimum 150 calendar days to the Project.

Tools and Instrumentalities: Contractor, at its own expense, will supply all tools, instrumentalities and all building and installation materials for the Project, including without limitation gravel, sand, concrete pavers, paint, steel metal frames.

Finishing Materials: Company shall be responsible for procuring the finishing materials as provided herein in the BOQ.

Work Items:

A) SITE CLEARANCE

Cutting and removal vegetation growth and loose soils

B) FOUNDATION EXCAVATIONS AND FOUNDATION WORKS (CONCRETING, PLINTH WALLING, BACKFILL)

Foundation excavation according to drawings, levelling, filling and compacting of the ground with gravel, Sand or both ready to receive concrete.

Placing of concrete

C) SUPERSTRUCTURE WALL WORKS

Building of wall with good quality blocks or bricks while keeping the mortar bed thin to avoid shrinkage

D) ROOFING WORKS

Properly constructed roof made out metal or well-seasoned timber

E) FITTING AND FINISHING WORKS: shall be conducted as per the BOQ

2.    Contractor’s payments.

Considering the Scope of works, UNDP agrees to pay Contractor the amount awarded based on the following payment schedule/milestones:

| SRA Rumbek |
| --- |
| Milestones | Descriptions | % | Amount |
| Milestone 1 | Upon mobilisation and foundation works | 30% |  |
| Milestone 2 | Upon superstructure & roofing works | 30% |  |
| Milestone 3 | Upon fitting and finishing works | 35% |  |
| Milestone 4 | Retention (upon snag repairs) | 5% |  |
|  | Total |  |  |

1.       Milestones 1-3: 95% of contract amount upon approval of satisfactory completion of all activities as per stated in the bills of quantities;

2.      Milestone 4: 05% after defect liability period of 12-month;

3. Deadline.

Contractor shall complete the Project within 150 calendar days.

Additional duration; the conditions stated in the conditions of contract shall apply.