TERMS OF REFERENCE

| Service | National Individual Consultant (IC) on Supporting the Inception Phase of the United Nations Partnership on the Rights of Persons with Disabilities (UNPRPD) Project |
| --- | --- |
| Duty station: | Ha Noi |
| Expected Duration and Timing | The IC is expected to provide services specified in this TOR during the inception phase of UNPRPD from Mar to 30 June 2021 (with possible extension to the implementation phase of the project) |
| Supervision: | The IC will report to UNDP Disability Rights Officer |

Background

The United Nations Partnership on the Rights of Persons with Disabilities Multi-Partner Trust Fund (UNPRPD MPTF) is a unique partnership that brings together UN entities, governments, organizations of persons with disabilities (OPDs), and broader civil society to advance the implementation of the Convention on the Rights of Persons with Disabilities (CRPD) and disability inclusive Sustainable Development Goals (SDGs) at the country level around the world. It was established in 2011 to foster collaboration between its members and support their work disability inclusion through UN join programming.

This MPTF aims at

(1) advancing CRPD implementation at the country level by focusing on the essential preconditions for disability inclusion across sectors, translating these into concrete policies, programs, and / or services which lead to systemic changes through a cohesive, inter-sectoral approach.

- improving and increasing the implementation of disability inclusive SDGs at the country level by providing fundamental support to the UN’s collective response to the SDGs to address national priorities and gaps concerning persons with disabilities in national planning.

UNPRPD MPTF's Strategic Operational Framework (SOF) 2020-2025 marks a shift from reactive to more proactive, results-oriented programming to drive implementation of the CRPD and disability inclusive SDGs with the meaningful participation of OPDs. This will be achieved by encouraging and supporting countries to develop and reform policies, plans, budgets, programs, and services to comply with the CRPD and SDGs by applying both disability-specific and disability-mainstreamed interventions through a multi-stakeholder approach. A critical new element of the SOF is a focus on the essential preconditions to disability inclusion. These are the foundational aspects that are indispensable in addressing the requirements of persons with disabilities (PWDs) across all sectors, such as accessibility, access to disability support services, protection from discrimination, and more.

Three cross-cutting approaches are intrinsically applied across all of UNPRPD MPTF's work, including its structures, programs, and processes:

• Enabling full and effective participation of persons with disabilities through their representative organizations;

• Ensuring the inclusion of marginalized and underrepresented groups of persons with disabilities; and

• Addressing gender inequality and advancing the rights of women and girls with disabilities.

This fourth funding round focuses on three major themes: reforms for CRPD and SDG implementation, country level focus through a multi-stakeholder approach, and COVID-19 response and recovery. In each country, at least two UN agencies will jointly run the programme for two years (2021-2023), comprising of an inception phase and an implementation phase.

In the inception phase, each country will receive $100,000 to conduct a five-day induction workshop and various consultations with stakeholders to write a situation analysis and a full proposal by June 2021;

In the implementation phase, each country will be funded between $700,000 and $900,000 to implement their project for two years.

With our wealth of experience and achievements in the previous UNPRPD project, culminating in Viet Nam’s ratification of the Convention of the Rights of Persons with Disabilities (CRPD) in 2015, thanks to great partnership and support from the government and organizations of persons with disabilities, Viet Nam has successfully passed the first round of Expression of Interest of this fourth UNPRPD funding call and was selected amongst 26 countries which proceed to the next round of writing a full proposal. In this project, the following areas will be prioritized in UN Viet Nam’s interventions:

Strengthen alignment of the legal framework with the CRPD;

Combatting stigma and discrimination;

Strengthen availability, quality, and coordination of services; and

Empowering OPDs and PWDs.

2. Objective

This assignment is aimed at supporting the UN Viet Nam to complete the situational analysis and the full proposal to be submitted to the UNPRPD Technical Secretariat as the grounds for the project implementation starting July 2021.

# 3. Expected Outputs

The IC, according to the following terms of reference and under the coordination of UNDP and UN Viet Nam, shall deliver the following services:

| Outputs | Description | Expected Results | Deadlines |
| --- | --- | --- | --- |
| Output 1 | Attend the five-day induction workshop: with all partners (30 participants max) to establish an agreement on targets, roles, and timelines of the UNPRPD project as well as to provide basic training on the CRPD and SDGs; Conduct pre-training and post-training survey with participants as guided by UNPRPD | A report on the induction workshop | 25 May 2021 |
| Output 2 | Five consultation workshops: 1 national in Ha Noi, two regionals in Hue and Can Tho, and 2 thematic workshops on specified priorities for the situational analysis and full proposal in Ha Noi (50 participants each) | Draft Situational analysis; and Draft Full proposal for the UNPRPD project | 05 June 2021 05 July 2021 |
| Output 3 | Consultation on the draft situational analysis and full proposal | Finalized Situational analysis and full proposal to be submitted to UNPRPD Technical Secretariat | 31 July 2021 |

# 4. Scope of Work

# The IC will work to complete the Outputs outlined in section 3 above through the following specific activities:

Conducting desk reviews for the situational analysis;

Providing technical support for the adaptation of induction materials and substances of consultation workshops;

Participating in all workshops to conduct necessary interviews and collect inputs from participants to draft the situational analysis and full proposal;

Collecting feedback on the draft situational analysis and full proposal from stakeholders via e-mails;

Analysing and synthesizing data to write up the situational analysis and full proposal to be submitted to UNPRPD Technical Secretariat;

Other technical support for the Inception Phase of UNPRPD Project.

# 5. Expected Qualifications

The IC conducting activities under this TOR is expected to meet the following qualifications:

Minimum master’s degree in disability studies, human rights, law, development, social science, or related fields;

At least 5 years of experience in the area of development and/or human rights, preferably in the disability field;

Proven experience in project planning and management;

Proven capacity of conducting research and drafting project reports and other documents;

Proven ability to work with colleagues and collaborators of diverse ability status and national and cultural backgrounds;

Proven proficiency in English and Vietnamese, especially in academic writing.

6. Evaluation Criteria

Individual (IC/RLA)

| Consultant(s)’ experiences/qualification related to the services |
| --- |
| 1.1 | Minimum master’s degree in disability studies, human rights, law, development, social science, or related fields; | 200 |
| 1.2 | At least 5 years of experience in the area of development and/or human rights, preferably in the disability field; | 200 |
| 1.3 | Proven experience in project planning and management; | 150 |
| 1.4 | Proven capacity of conducting research and drafting project reports and other documents; | 250 |
| 1.5 | Proven proficiency in English and Vietnamese, especially in academic writing with submission of two reports in English and Vietnamese | 200 |
| Total |  |  |  | 1000 |

# 7. Timing, duration and location

The IC will work closely with UNDP to deliver final outputs as described in Section 3 above from April to July 2021 mostly in Ha Noi and 2 one-day mission trips to the Center and the South for consultations.

# 8. Contract payment

UNDP shall process payments for RLA upon the UN’s satisfaction with expected deliverables set forth in Section 3 above. Payments shall be made upon satisfactory outputs by the tentative schedule set forth for each output below:

| Stage | Expected Outputs | Payment Amount | Tentative Payment Schedule |
| --- | --- | --- | --- |
| Output 1 | Submission and approval of A report on the induction workshop | 30% | 30 May 2021 |
| Output 2 | Submission and approval of the first draft of the situational analysis and full proposal | 30% | 10 July 2021 |
| Output 3 | Submission and approval of the final UNPRPD situational analysis and full proposal | 40% | 10 August 2021 |

# All travel and related costs to this assignment should be requested in a lump sum by the IC in his /her financial proposal.

# 9. Provision of monitoring and progress controls

- UNDP shall be responsible for quality control of the outputs.

- The IC will report directly to UNDP.

10) CONSULTANT PRESENCE REQUIRED ON DUTY STATION/UNDP PREMISES

INTERMITTENT