EU-UN Spotlight Initiative Project

UNDP Phase 2 Implementation Plan

Information for Consultancy Call for GBV Advisers to support 4 components

May to December 2022

| Component 1 – Joint Deliverables |
| --- |
| PROVINCE | ACTIVITIES | MONTH | DELIVERABLE |
| Institutional set-up of Provincial GBV Secretariat |
| Targeted Provinces | Conduct Assessment of Provincial Administration Capacities to set up GBV Secretariate Costing for Running a GBV Secretariat | May – November 2022 | Scoping Report with key issues, recommendations on structural set up to establish GBV Secretariats, costings of running a secretariat and next Steps. |
| National level support | Develop template for Provincial GBV Strategy & Implementation Plan | April- May 2022 | GBV Strategy & Implementation Plan (Template) |
| National level support | Develop 1 -2 pager clear steps on process of getting GBV positions created within existing Provincial Structure (in consultation with DPM) | April – June 2022 | Instruction Paper on GBV Positions in the province |
| Establishment of Provincial GBV Secretariats |
| Provincial GBV Stakeholders Consultations (Non-Spotlight Provinces) |
| AROB | Conduct consultations with local provincial administration, CSOs, FBOs, NGOs and GBV service providers for the establishment of the Provincial GBV Secretariat | May -June | Detailed Mission Report with Checklist for GBV Status in AROB |
| Manus |  | June -July | Detailed Mission Report with Checklist for GBV Status in Manus |
| Central |  | May -June | Detailed Mission Report with Checklist for GBV Status in Central |
| Western |  | July-August | Detailed Mission Report with Checklist for GBV Status in Western |
| Gulf |  | July -August | Detailed Mission Report with Checklist for GBV Status in Gulf |
| Madang |  | May – July | Detailed Mission Report with Checklist for GBV Status in Madang |
| New Ireland |  | June -July | Detailed Mission Report with Checklist for GBV Status in New Ireland |
| Oro Province |  | May-June | Detailed Mission Report with Checklist for GBV Status in Oro |
| Support Services Consultant |
| (b)Support Provincial GBV Administration & Operational Set up |
| EHP, Simbu, Jiwaka, WHP, SHP, Enga, Hela, WNBP, ESP, Milne Bay, Sandaun | From Equipment Assessment Report: Support Procurement of Desks + chair, Computer (laptop or desktop), Printer/scanner/photocopier, Filing cabinet /Printing paper/ etc… Procure Office Pull Up Banners (22 Provinces) | May –August | Media Update on support Provided |
| Selected Provinces (TBC) | Purchase Crisis Support Vehicles Maintenance /Service /Fuel arrangement with service providers | August -December | Media Update on Vehicles Procured per Province Support with Procurement actions (Documentation) |
| Component 2 – Specific Deliverables |
| Provincial GBV Strategy and Implementation Plan |
| Provincial Adviser: Highlands and MOMASE |
| Highlands Region |
| EHP | Review & finalise Draft GBV Strategy, Workplan & Budget | April -May | Finalised GBV Strategy, Workplan & Budget for EHP |
|  | Activity /Implementation Plan for 2022 | April | 2022 Activity Plan |
|  | Stakeholders Validation Workshop | May | Validation Workshop Report |
|  | Submission to PEC& Endorsement of Workplan & Budget | April -May | PEC Submission /Endorsement – Media Update |
|  | Layout /Artwork & Printing & Launching | May -June | GBV Strategy Launching Report /Media Updates |
| Simbu | Review & finalise Draft GBV Strategy, Workplan & Budget | April -May | Finalised GBV Strategy, Workplan & Budget for Simbu |
|  | Activity /Implementation Plan for 2022 | April | 2022 Activity Plan |
|  | Stakeholders Validation Workshop | May | Validation Workshop Report |
|  | Submission to PEC& Endorsement of Workplan & Budget | April -May | PEC Submission /Endorsement – Media Update |
|  | Layout /Artwork & Printing & Launching | May -June | GBV Strategy Launching Report /Media Updates |
| Jiwaka | Review Validated Draft GBV Strategy, Workplan & Budget | April | Finalised GBV Strategy, Workplan & Budget for Jiwaka |
|  | Activity /Implementation Plan for 2022 | April | 2022 Activity Plan |
|  | Final Stakeholders Validation Workshop | May | Validation Workshop Report |
|  | Submission to PEC& Endorsement of Workplan & Budget | May | PEC Submission /Endorsement – Media Update |
|  | Layout /Artwork & Printing & Launching | May | GBV Strategy Launching Report /Media Updates |
| WHP | Develop GBV Strategy, Workplan & Budget | April – May | Finalised GBV Strategy, Workplan & Budget for WHP |
|  | Activity /Implementation Plan for 2022 | April | 2022 Activity Plan |
|  | Stakeholders Validation Workshop | May | Validation Workshop Report |
|  | Submission to PEC & Endorsement of Workplan & Budget | May -June | PEC Submission /Endorsement – Media Update |
|  | Layout /Artwork & Printing & Launching | May -June | GBV Strategy Launching Report /Media Updates |
| SHP | Develop GBV Strategy, Workplan & Budget | April – May | Finalised GBV Strategy, Workplan & Budget for SHP |
|  | Activity /Implementation Plan for 2022 | April | 2022 Activity Plan |
|  | Stakeholders Validation Workshop | May -June | Validation Workshop Report |
|  | Submission to PEC& Endorsement of Workplan & Budget | May -June | PEC Submission /Endorsement – Media Update |
|  | Layout /Artwork & Printing & Launching | May -June | GBV Strategy Launching Report /Media Updates |
| Enga | Review & finalise Draft GBV Strategy, Workplan & Budget | April -May | Finalised GBV Strategy, Workplan & Budget for Enga |
|  | Activity /Implementation Plan for 2022 | April | 2022 Activity Plan |
|  | Stakeholders Validation Workshop | May | Validation Workshop Report |
|  | Submission to PEC& Endorsement of Workplan & Budget | April -May | PEC Submission /Endorsement – Media Update |
|  | Layout /Artwork & Printing & Launching | May -June | GBV Strategy Launching Report /Media Updates |
| Hela | Review & finalise Draft GBV Strategy, Workplan & Budget | April -May | Finalised GBV Strategy, Workplan & Budget for Hela |
|  | Activity /Implementation Plan for 2022 | April | 2022 Activity Plan |
|  | Stakeholders Validation Workshop | May -June | Validation Workshop Report |
|  | Submission to PEC & Endorsement of Workplan & Budget | May -June | PEC Submission /Endorsement – Media Update |
|  | Layout /Artwork & Printing & Launching | May -June | GBV Strategy Launching Report /Media Updates |
| Momase Region |
| Morobe | Draft GBV Strategy, Workplan & Budget | April -May | Finalised GBV Strategy, Workplan & Budget for Morobe |
|  | Activity /Implementation Plan for 2022 | April | 2022 Activity Plan |
|  | Stakeholders Validation Workshop | May -June | Validation Workshop Report |
|  | Submission to PEC & Endorsement of Workplan & Budget | May -June | PEC Submission /Endorsement – Media Update |
|  | Layout /Artwork & Printing & Launching | May -June | GBV Strategy Launching Report /Media Updates |
| East Sepik | Review & finalise GBV Strategy, Workplan & Budget | April -May | Finalised GBV Strategy, Workplan & Budget for East Sepik |
|  | Activity /Implementation Plan for 2022 | April | 2022 Activity Plan |
|  | Final Stakeholders Validation Workshop | May -June | Validation Workshop Report |
|  | Submission to PEC & Endorsement of Workplan & Budget | May -June | PEC Submission /Endorsement – Media Update |
|  | Layout /Artwork & Printing & Launching | May -June | GBV Strategy Launching Report /Media Updates |
| Sandaun | Develop GBV Strategy, Workplan & Budget | April – May | Finalised GBV Strategy, Workplan & Budget for Sandaun |
|  | Activity /Implementation Plan for 2022 | April | 2022 Activity Plan |
|  | Stakeholders Validation Workshop | May -June | Validation Workshop Report |
|  | Submission to PEC& Endorsement of Workplan & Budget | May -June | PEC Submission /Endorsement – Media Update |
|  | Layout /Artwork & Printing & Launching | May -June | GBV Strategy Launching Report /Media Updates |
| Madang | Develop GBV Strategy, Workplan & Budget | May -June | Finalised GBV Strategy, Workplan & Budget for Madang |
|  | Activity /Implementation Plan for 2022 | April | 2022 Activity Plan |
|  | Stakeholders Validation Workshop | June | Validation Workshop Report |
|  | Submission to PEC & Endorsement of Workplan & Budget | June -July | PEC Submission /Endorsement – Media Update |
|  | Layout /Artwork & Printing & Launching | June -July | GBV Strategy Launching Report /Media Updates |
| Provincial Adviser: New Guinea Islands and Southern |
| New Guinea Islands (NGI) |
| West New Britain | Activity /Implementation Plan for 2022 | April | 2022 Activity Plan |
|  | Layout /Artwork & Printing | April - May | Printed GBV Strategy for WNBP |
|  | Submission to PEC& Endorsement of Workplan & Budget & Launching | April - May | PEC Submission /Endorsement & Launching – Media Update |
| East New Britain | Develop GBV Strategy, Workplan & Budget | April – May | Finalised GBV Strategy, Workplan & Budget for ENBP |
|  | Activity /Implementation Plan for 2022 | April | 2022 Activity Plan |
|  | Stakeholders Validation Workshop | May | Validation Workshop Report |
|  | Submission to PEC& Endorsement of Workplan & Budget | May -June | PEC Submission /Endorsement – Media Update |
|  | Layout /Artwork & Printing & Launching | May -June | GBV Strategy Launching Report /Media Updates |
| New Ireland | Develop GBV Strategy, Workplan & Budget | May -July | Finalised GBV Strategy, Workplan & Budget for New Ireland |
|  | Activity /Implementation Plan for 2022 | April | 2022 Activity Plan |
|  | Stakeholders Validation Workshop | May -July | Validation Workshop Report |
|  | Submission to PEC& Endorsement of Workplan & Budget | May -July | PEC Submission /Endorsement – Media Update |
|  | Layout /Artwork & Printing & Launching | July -August | GBV Strategy Launching Report /Media Updates |
| Manus | Develop GBV Strategy, Workplan & Budget | May -June | Finalised GBV Strategy, Workplan & Budget for Manus |
|  | Activity /Implementation Plan for 2022 | April | 2022 Activity Plan |
|  | Stakeholders Validation Workshop | May-June | Validation Workshop Report |
|  | Submission to PEC& Endorsement of Workplan & Budget | June -July | PEC Submission /Endorsement – Media Update |
|  | Layout /Artwork & Printing & Launching | July | GBV Strategy Launching Report /Media Updates |
| Bougainville (ARB) | Develop GBV Strategy, Workplan & Budget | May -June | Finalised GBV Strategy, Workplan & Budget for ARB |
|  | Activity /Implementation Plan for 2022 | April | 2022 Activity Plan |
|  | Stakeholders Validation Workshop | May | Validation Workshop Report |
|  | Submission to PEC& Endorsement of Workplan & Budget | June -July | PEC Submission /Endorsement – Media Update |
|  | Layout /Artwork & Printing & Launching | June -July | GBV Strategy Launching Report /Media Updates |
| Southern Region |
| NCD | Develop GBV Strategy, Workplan & Budget (2023 onwards) | Aug-Nov | Finalised GBV Strategy, Workplan & Budget for NCD |
|  | Activity /Implementation Plan for 2022 | April | 2022 Activity Plan |
|  | Stakeholders Consultation Workshop | June -July | Workshop Report |
|  | Submission to NCDC management for Endorsement of Workplan & Budget | Nov-Dec | PEC Submission /Endorsement – Media Update |
|  | Layout /Artwork & Printing & Launching | Nov-Dec | GBV Strategy Launching Report /Media Updates |
| Milne Bay | Develop GBV Strategy, Workplan & Budget (2023 onwards) | Aug-Nov | Finalised GBV Strategy, Workplan & Budget for Milne Bay |
|  | Activity /Implementation Plan for 2022 | April | 2022 Activity Plan |
|  | Stakeholders Validation Workshop | June -July | Validation Workshop Report |
|  | Submission to PEC& Endorsement of Workplan & Budget | Nov-Dec | PEC Submission /Endorsement – Media Update |
|  | Layout /Artwork & Printing & Launching | Nov-Dec | GBV Strategy Launching Report /Media Updates |
| Oro | Develop GBV Strategy, Workplan & Budget | May -June | Finalised GBV Strategy, Workplan & Budget for Oro |
|  | Activity /Implementation Plan for 2022 | April | 2022 Activity Plan |
|  | Stakeholders Validation Workshop | May | Validation Workshop Report |
|  | Submission to PEC& Endorsement of Workplan & Budget | May -June | PEC Submission /Endorsement – Media Update |
|  | Layout /Artwork & Printing & Launching | May -June | GBV Strategy Launching Report /Media Updates |
| Gulf | Develop GBV Strategy, Workplan & Budget | May – August | Finalised GBV Strategy, Workplan & Budget for Gulf |
|  | Activity /Implementation Plan for 2022 | April | 2022 Activity Plan |
|  | Stakeholders Validation Workshop | July-August | Validation Workshop Report |
|  | Submission to PEC& Endorsement of Workplan & Budget | July -Aug | PEC Submission /Endorsement – Media Update |
|  | Layout /Artwork & Printing & Launching | July -August | GBV Strategy Launching Report /Media Updates |
| Western (Fly River) | Develop GBV Strategy, Workplan & Budget | May -June | Finalised GBV Strategy, Workplan & Budget for Western |
|  | Activity /Implementation Plan for 2022 | April | 2022 Activity Plan |
|  | Stakeholders Validation Workshop | June -July | Validation Workshop Report |
|  | Submission to PEC& Endorsement of Workplan & Budget | July | PEC Submission /Endorsement – Media Update |
|  | Layout /Artwork & Printing & Launching | July | GBV Strategy Launching Report /Media Updates |
| Central | Develop GBV Strategy, Workplan & Budget | May-June | Finalised GBV Strategy, Workplan & Budget for Central |
|  | Activity /Implementation Plan for 2022 | April | 2022 Activity Plan |
|  | Stakeholders Validation Workshop | June | Validation Workshop Report |
|  | Submission to PEC& Endorsement of Workplan & Budget | June -July | PEC Submission /Endorsement – Media Update |
|  | Layout /Artwork & Printing & Launching | June -July | GBV Strategy Launching Report /Media Updates |
| Component 3 – Joint Deliverables |
| Provincial Workshop/ Trainings Capacity Development |
| GBV Capacity Development Trainings |
| Targeted Provinces with GBV Strategy, Workplan & Budget NOTE: Training services will be procured directly by UNDP Trainings are not limited to this list | Gender Sensitisation Training | May – December | Provincial Trainings Needs Assessment report Training Reports Procurement actions documentations to verify support provided. Media Updates shared on NGBVS Website |
|  | Survivors Advocacy Training (1 week training on GBV laws /policies, psychosocial support etc for survivors) |  |  |
|  | Standard operating procedures (SOPs) for Family Support centres (clinical management of GBV survivors, including roles, duties of health care workers & referral pathways |  |  |
|  | Family Sexual Violence (FSV) Sensitisation, application of Law, trauma-informed care and case management |  |  |
|  | SOPs for Safe House, guidelines for admission, case management & referral pathways. |  |  |
|  | Trauma Counselling Training |  |  |
|  | Referral pathways standard Operating Procedures (SOP) |  |  |
|  | Male Advocacy for Women’s Human rights & gender equality Training |  |  |
| Provincial GBV Focal Points Workshops -Venue TBC |
| All Provinces to attend | Provincial Workshop on Coordinated Planning and Budgeting to Address GBV | April | Workshop Report with Media Updates |
| All Provinces to attend | Provincial Workshop on GBV Prevention and Response – 2022 Workplan Implementation Update (Results, Challenges, next Steps) & Budget for 2023 | November | Workshop Report with Media Update |
| Component 4 – Specific Deliverables |
| Support Services Consultant. |
| Crisis Response Services |
| Targeted Provinces | Strengthen Police Family Sexual Violence Unit (FSVU) | May – December | Report of Family Sexual Violence Unit establishment within Police Stations |
|  | Establish and/or strengthen Family Support Centre (FSC) |  | Report of Family Support Centre establishment within Clinical setups (Hospitals/health centres) |
|  | Establish and/or strengthen Safe Houses | May – December | Report on number of Safe Houses established /strengthened |
|  | Grants Administration for CSOs : Counselling service providers (TBC) Human Rights Defenders for SARV response, rescue & repatriation services Trainings & Awareness | May – December | Grants administration and monitoring reports |
| GBV Prevention Interventions |
| All Provinces | Coordination - 20 days of GBV/Human Rights Activism Activities (Nov 20 to Dec 10) – | Oct -Dec | Calendar of Provincial Events 20 days activism media updates |
| As requested by provinces | Development of IEC materials /knowledge products on GBV /printing | May -Dec | Finalised IEC Materials |
| Support to National GBV Secretariat -DfCDR |
| Administration / Operations |
| National Level (DfCDR) | Support with recruitment of NGBVS Staff | May – July | Recruitment Report |
|  | Office Set Up Support Procurement of Desks + chair, Computer (laptop or desktop), Printer/scanner/photocopier, Filing cabinet /Printing paper etc | May -July | Office Setup Report |
|  | Maintenance /Service /Fuel arrangement with service providers for NGBVS Bus (Operations) & Management Support Vehicle (x1) | May -Dec | Vehicle compliance system in place for accountability (fuel logs etc) -Report |
|  | Procure Vehicle for NGBVS Vehicle (management support) | August -Dec | Vehicle Procured. |
| Coordination & Programme Management |
| National Level (DfCDR) | Budget and Workplan for K7.9 million | May | NGBVS Workplan for 2022 |
|  | National GBV Advisory Committee Meeting (x 2) June & November 2022 | May – Nov | Meeting Minutes & |
|  | GBV Data Information Management System Consultation / workshops Recruitment of firm to Develop GBV IMS | May -Dec | GBV National Data base established |
| National Level (DfCDR) | Monthly Brief on Activity Progress Update | May - Dec | Monthly Secretary Brief |
|  | Newsletter article /Media Updates for GBV Website /UNDP Newsletter | May -Dec | Media Updates |
| Targeted Provinces | Provincial M&E Visits | June -Dec | M&E Visit Report |
| UNDP Spotlight Project Support |
| UNDP Spotlight Programme Team /Consultants – Port Moresby NCD | Programme Team -Weekly Meeting | May -Dec | Weekly Brief on Activity Update Meeting Minutes |
|  | UNDP Dashboard Reporting -May to June | May -June | Dashboard Report |
|  | UNDP Dashboard Reporting -July -August | July -Aug | Dashboard Report |
|  | UNDP Dashboard Reporting -September to October | Sep -Oct | Dashboard Report |
|  | UNDP Dashboard Reporting -November to December | Nov- Dec | Dashboard Report |
|  | Spotlight 2022 Annual Report | Nov -Dec | 2022 Annual Report |
|  | Spotlight AWP -2023 | Nov-Dec | Activity Plans for 2023 |
| Parliamentary Committee on GBV /Coalition of MPS against GBV |
|  | Meeting of the Coalition of Parliamentarians and the Specialist Parliamentary Committee on GBV | August 2022 to May 2023 | Information for meetings |