TERMS OF REFERENCE

May 24, 2022

| Project title: | “Towards a Professional and Citizen-Centered Civil Service in Mongolia” |
| --- | --- |
| Title of the assignment: | Support to the Ethics Councils of the Statutory agencies |
| Type of contract: | Individual contract |
| Contract duration | Up to 60 working days from June 2022 through December 2022 |

- Project Description

The project “Towards a Professional and Citizen-centred Civil Service in Mongolia” (“Project”), was approved in February 2018 and will be implemented in 2018-2021, jointly with the Parliament of Mongolia, the Civil Service Council (CSC), the Cabinet Secretariat (CS) and other agencies involved in training of civil servants. The project is funded by the Government of Canada. The project will support the implementation of the civil service reform priorities towards creating a stable, impartial, professional and citizen-centred civil service and their implementation through capacity-building.

The year 2021 was marked by a significant increase in Ethics Councils at public institutions, both at the central and sub-national levels. The number of Ethics Councils more than doubled in one year, rising from 1,194 (Sep 2020) to 2,711 by the end of 2021.

A newly designed participatory ethics training was delivered to over 550 members of 226 Ethics Councils, across the country. It was for the first time in the history of the CSC that a formal ethics training programme was adopted and rolled out widely to government entities.

In October 2021, the Parliamentary Standing Committee on Ethics, Discipline and Accountability (SCEDA) heard the presentation by the CSC on the Ethics Councils in the public administration. SCEDA members noted the encouraging sign seen across the administration, with more than half of 4,105 public institutions already having their Ethics councils; ongoing ethics trainings, and an integrated register of all Ethics Councils in use by CSC.19 In view of the recent high profile unethical behavior and unethical conducts of civil servants, the SCEDA also advised the CSC to scale up the current training to Ethics Councils to Aimags and to make the training content available immediately to all civil servants.

All ethics training sessions used participatory methods, highlighting the need for prevention rather than punishment after incidents. Feedback from participants was very positive, and the Project received numerous requests from public institutions to organize ethics training for them.

Previously, regarded as a ’dormant’ structure, some Ethics Councils now report their activities at a management meeting on challenges and results, enabling management to take a more supporting role.

The purpose of this assignment is to equip, nurture and strengthen newly established Councils through implementation of the national strategy, educational content, and conducting monitoring oversight.

- Scope of Work

- Support to the implementation of the national strategy for Ethics Councils of the Statutory agencies:

  - Assist in the formalization of the national register of newly formed Ethics Councils at local level and define a route to link with the Human Resources management system developed by the CSC.

  - Contribute towards the design of an annual training schedule program drawing from the Toolkit.

  - Provide qualitative support to the Annual Business Plan of the Public administration organization as stipulated in the Art 53.1 of the Civil service law.

- Support in the roll-out of the ethics trainings of the statutory agencies:

  - Partner with the CSC’s Dispute Inspection Department in organizing, facilitating, monitoring, and collating feedback of the training for Parliament, President, and Cabinet Secretariat.

  - Co-draft integrated annual report of Ethics Councils of the statutory agencies, including qualitative review on status of adherence to the code of conduct and ethics.

  - By partnering and exploring with the Ethics councils gather, classify at least 30 cases by nature, frequency, and detriment.

- Support in the Training for national and sub-national government level Ethics Councils

  - Co-organize up to 3 trainings for Parliament, President, and Cabinet Secretariat. Training shall be conducted in close coordination and synergy with the Competency based HRM team.

  - Contribute towards the development and launch of the online training for Ethics Councils with full access to all members of the ethics councils. Online training content shall be developed according to the methodology used by the Competency based HRM team: use of Google platform, four modules, interactive quizzes, self-assessment etc. must liaise closely with the Competency based HRM team.

- Expected Deliverables and Payment Schedule

| Payment installments | Deliverables | Target Due Dates |
| --- | --- | --- |
| 30% of the total fee | Progress report for Output 1 (tasks a-c) | By 1 August 2022 |
| 30% of the total fee | Progress report for Output 2 (tasks a-c) | By 1 October 2022 |
| 40% of the total fee | Progress report for Output 3 (task b) | By 1 December 2022 |

- Institutional Arrangement

The contractor shall report to the Project Manager. During the assignment, the consultant will work closely with the Civil Service Council of Mongolia, Cabinet Secretariat, and on needs basis with the Standing Committee on Ethics, Discipline and Accountability. The contractor shall provide feedback and draw lessons from the roll-out of the Competency Framework in the civil service which the Project is supporting.

- Qualifications of the Successful Individual Contractor

- Master’s degree in philosophy, politics, law, public policy, public administration, economics, and other related fields.

- At least 3 years of work experience in the public administration in Mongolia.

- Previous work experience at Civil Service Council is a plus.

- A proven track record of providing quantative and qualitative data support in drafting policy documents, ethics related legal acts.

- Excellent facilitation skills as demonstrated by past trainings and workshops.

- Excellent writing skills in Mongolian language.

- Knowledge of English is an advantage.

- Criteria for Selection of the Best Offer

Criteria for evaluation and selection of the best offer will be the Combined Scoring Method.

Technical scores – 70% and will, in turn, include the sum of written test (70%) and interview scores (30%);

Finance scores (price offer) - 30%.

| Criteria | Weight | Max. Point |
| --- | --- | --- |
| Technical criteria 1: Relevant experience |  | 50 |
| At least 3 years of work experience in the public administration in Mongolia. |  | 30 |
| A proven track record of providing quantative and qualitative data support in drafting policy documents, ethics related legal acts |  | 10 |
| Excellent facilitation skills as demonstrated by past trainings and workshops |  | 10 |
| Technical criteria 2: Educational background |  | 20 |
| Master’s degree in philosophy, politics, law, public policy, public administration, economics, and other related fields. |  | 20 |
| Technical criteria 3: Technical proposal |  | 30 |
| A brief proposal describing the methodologies, work plan and timeframe |  | 30 |
| Technical Score | 70 | 100 |

Documents to be submitted as part of the application:

- Letter of Confirmation of Interest and Availability using the template provided by UNDP.

- Personal CV or P11, indicating all experience from similar projects, as well as the contact details (email and telephone number) of the Candidate and at least three (3) professional references.

- Brief description of why the individual considers him/herself as the most suitable for the assignment, and a methodology, if applicable, on how they will approach and complete the assignment.

- Financial Proposal that indicates the all-inclusive fixed total contract price, supported by a breakdown of costs, as per template provided.

- Approval

The ToR is prepared and submitted by:

Name: Khulangoo.P

Designation: Project Manager

The ToR is approved by:

Name: Barkhas L.

Designation: Program Officer

See the project document at www.mn.undp.org

Local governments for pilot have been identified by 5 January 2022 CSC’s all member meeting