{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["Rijeka Trstionica"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Rijeka Trstionica","index":0,"n_rows":15,"n_cols":33,"rows_kept":15,"cut":false,"hidden":false,"merged":[[8,1,11,1],[8,2,8,13],[8,32,14,32],[9,12,9,17],[4,2,4,31],[5,2,5,31],[6,2,6,31]]}
[]
[null,"ANNEX 4  (dinamički plan i plan resursa)"]
[]
[]
[null,"PONUĐAČ"]
[null,"UKUPAN BROJ GRAĐEVINSKIH RADNIKA"]
[null,"UKUPAN BROJ DANA TRAJANJA RADOVA",30]
[null,"Dan",1,2,3,4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,25,26,27,28,29,30]
[null,"Regulacija potoka Radinovac u dužini od 840 m, općina Sanski Most.","Inžinjer za navedenu grupu objekata (Šef gradilišta):",{"$nulls":11},"upisati ime ",{"$nulls":17},"Linijom označiti dužinu trajanja izvođenja pojedine grupe radova. Naznačiti broj radnika istovremeno angažovanih na pojedinoj grupi radova."]
[null,null,"Broj angažovanih radnika:                                      ",{"$nulls":9},"upisati broj radnika"]
[null,null,"Početak radova                                 ( .........dan)"]
[null,null,"Završetak radova                             (......... dan)"]
[null,"1. ČIŠĆENJE KORITA RIJEKE"]
[null,"2. SANACIJA OŠTEĆENIH DIJELOVA KAMENOG ZIDA"]
[null,"3. OSTALI RADOVI"]