**INDIVIDUAL CONSULTANT PROCUREMENT NOTICE** 

 Date: 5th October. 2022

**Country: UGANDA**

**Description of the assignment: National Consultant to undertake Feasibility Study for the Establishment of an Agritech Database in Uganda.**

**Post Level**: National Individual Consultant

**Period of assignment/services:** 3 months

Proposal should be submitted to the UNDP jobs website no later than *Sunday 16th October 2022.*

Any request for clarification must be sent in writing, or by standard electronic communication to ug.procurement@undp.org. UNDP will respond by standard electronic mail with an explanation of the query without identifying the source of inquiry, to all candidates.

**1. BACKGROUND**

|  |
| --- |
| *This assignment is commissioned by UNCDF Uganda in partnership with the Uganda Bankers’ Association (UBA) and Financial Technology Association of Uganda (FITSPA). We are looking for a consultant to undertake a study on the feasibility of establishing an Agritech Database in Uganda.* *Rationale for the Assignment:**The Agricultural sector is critical to Uganda’s economic development. It contributed 23.7% to the overall GDP (2019/20), accounts for 20% of total value of exports and employs about 72% of the total workforce in Uganda. Uganda’s National Development Plan III identifies the agriculture sector as a key catalytic sector for the development of Uganda’s economy and has focused initiatives to develop and industrialize agriculture.* *Access to finance remains a key bottleneck to the growth of the agricultural sector. In Uganda, lending to the agricultural sector accounted for 12.7% of total bank lending by the end of February 2021, from 6.7% in the period December 2020. The share of this financing that goes to small businesses in agriculture and small holder farmers is even much lower. Financial institutions decry the risks prevalent in the sector plus limited and unreliable data on which to base their lending decisions. This is a long-standing challenge.* *The growing availability of alternative data thanks to digitalization efforts in Agriculture could hold a potential solution to alleviating the challenge of access to finance. Various fintech's and Agritech collect a lot of data from customers through farmer profiling, production and sales data, digital payments, etc. This data which currently lies in independent databases could be aggregated and made accessible to financial service providers to enable farmer credit scoring and thus unlock financing to the agricultural sector.* *UNCDF, in partnership with UBA and FITSPA, seek to deeply investigate this potential – by undertaking a feasibility study for the establishment of an aggregated Agritech Database****Objective of the assignment****The consultancy aims to achieve the following objectives:**- Assess the desirability, feasibility and viability of an Agritech database for Uganda**•* ***Desirability:*** *Deeply understand the level of need for such a solution among key stakeholders (financial services providers, fintechs, agritechs, public and development sector actors in the agriculture and finance sectors). This includes collection of stakeholder perspectives on what it would take for them to uptake / join such a solution/platform.* *•* ***Feasibility:*** *Assess the feasibility for such a solution from a technical and organizational point of view, including collection of perspectives from key stakeholders on the feasibility aspects.* *•* ***Viability:*** *A critical assessment of what it would take for such a platform / solution to be viable and sustainable as a business model.**- Propose the potential structure, design, and business model for establishing such a platform for Uganda, should it be found to be feasible*  |

**2. SCOPE OF WORK, RESPONSIBILITIES AND DESCRIPTION OF THE PROPOSED ANALYTICAL WORK**

|  |
| --- |
| For detailed information, please refer to TOR |

**3. REQUIREMENTS FOR EXPERIENCE AND QUALIFICATIONS**

|  |
| --- |
| Qualifications:Academic qualifications:* + Postgraduate degree (Masters) in International Development, ICT, Economics, Management or closely related field.

Skills and Experience: * + Minimum 7 years of technical experience in business development, financial sector development, leading projects in fintech / Agritech
	+ Demonstrable experience and/or understanding of the financial sector and Fintech / Agritech industry in Uganda or other East African countries, with exposure to other emerging / developed markets.
	+ Substantial relevant experience in undertaking feasibility studies, designing and implementation of innovative digital projects.
	+ Experience in economic and financial analysis for project viability and budget formulation.
	+ Experience in the formulation and management of similar / related projects and innovations:
	+ Working with multi-disciplinary teams, including local and expatriate technical experts.
	+ Strong analytical skills; Exceptional ability in communication and networking, negotiations and writing.
	+ Flexibility and ability to operate in different cultural settings and with a variety of stakeholders, culturally and gender sensitive.
 |

**4. DOCUMENTS TO BE INCLUDED WHEN SUBMITTING THE PROPOSALS.**

|  |
| --- |
| 1. **Letter of Interest**
2. **Personal CV** indicating all experience from similar projects, as well as the contact details (email and telephone number) and at least three (3) professional references.
3. **Brief description** of why the Consultant considers her/himself as the most suitable for the assignment, **and a methodology** on how to approach and accomplish the assignment.
4. **Financial Proposal** that indicates the all-inclusive fixed total contract price in Uganda Shillings, supported by a breakdown of costs.
 |

**5. FINANCIAL PROPOSAL**

|  |
| --- |
| Financial proposal that indicates the all-inclusive fixed total contract price, supported by a breakdown of costs, as per template provided (Annex 2).The lump sum amount is all inclusive of subsistence allowance, health insurance and all other expensesThe contract price is fixed regardless of changes in the cost of the components of the Contract,Travel to and from UNDP Offices or any other venues for scheduled review meetings should be factored in the Lump Sum Amount by the IC.Travel costs to the region, including the payment of the UN’s applicable Daily SubsistenceAllowance (DSA) rates will be borne by UNDP. |

**6. EVALUATION**

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Individual consultants will be evaluated based on the following methodology:****Cumulative analysis: The award of the contract shall be made to the individual consultant whose offer has been evaluated and determined as:*** Responsive/compliant/acceptable; and
* Having received the highest score out of a pre-determined set of weighted technical and financial criteria specific to the solicitation. 70%-30%.

Technical Criteria weight; [70%]; Financial Criteria weight; [30%]Only candidates obtaining a minimum of 49 points (70% of the total technical points) would be considered for the Financial Evaluation**.****Technical Criteria – Maximum 70 points:**

|  |  |
| --- | --- |
| **Criteria** | **scoring** |
| 1. Academic qualifications of the consultant

Postgraduate degree (Masters) in International Development, ICT, Economics, Management, or closely related field | **7 points** |
| 1. Experience of the consultant
* experience in undertaking feasibility studies, designing and implementation of innovative digital projects
* technical experience in business development, financial sector development, leading projects in fintech / Agritech
* experience and/or understanding of the financial sector and Fintech / Agritech industry in Uganda or other East African countries, with exposure to other emerging / developed markets
* Experience in the formulation and management of similar / related projects and innovations
 | **28 points**  |
| 1. Quality of the technical proposal
* The proposed approach and methodology to the study
* The proposed workplan
 | **35 points** |

Financial proposal (Maximum 30 points): appropriateness shall be computed as a ratio of the proposal’s offer to the lowest price among the proposals received by UNDP.**Financial assessment: A lump sum amount approach shall be used with the following expectations:*** The lump sum amount must be “all-inclusive”
* The contract price is fixed regardless of changes in the cost of components.
* For duty travels, UN’s Daily Subsistence Allowance (DSA) rates prevailing at the time of sourcing, for the duty station and all other cities indicated in the TOR as part of duty travel destinations will be used.  This will give offerors an indication of the cost of living in a duty station/destination, to aid their determination of the appropriate fees and financial proposal amount, but it does not imply that Offerors are entitled to DSA payment; and

The initial payment includes the actual cost of the IC’s travel to arrive at the designated Duty Station. This implies that the completion of the journey can be considered as one of the deliverables payable upon arrival.                                                |

**ANNEX**

**ANNEX 1- TERMS OF REFERENCES (TOR)**

**ANNEX 2 – LETTER OF CONFIRMATION OF INTEREST TEMPLATE**

**ANNEX 3- INDIVIDUAL CONSULTANT GENERAL TERMS AND CONDITIONS**

 **Annex I**

TERMS OF REFERENCE

|  |  |
| --- | --- |
| Place of Assignment | **Kampala, Uganda** |
| Agency | **UNCDF** |
| Assignment Description | **National Consultant to undertake Feasibility Study for the Establishment of an Agritech Database in Uganda** |
| Post Level | **National Consultant** |
| Type of Contract | **Individual consultant** |
| Languages Required | **English** |
| Starting date | **November 1st 2022** |
| Expected Duration of Assignment | **3 months** |

**PROJECT DESCRIPTION**

***About UNCDF***

The United Nations Capital Development Fund (UNCDF) makes public and private finance work for the poor in the world’s 47 least developed countries. With its capital mandate and instruments, UNCDF offers “last mile” finance models that unlock public and private resources, especially at the domestic level, to reduce poverty and support local economic development. UNCDF’s financing models work through two channels: financial inclusion that expands the opportunities for individuals, households and small businesses to participate in the local economy, providing them with the tools they need to climb out of poverty and manage their financial lives; and by showing how localized investments — through fiscal decentralization, innovative municipal finance and structured project finance — can drive public and private funding that underpins local economic expansion and sustainable development. By strengthening how finance works for poor people at the household, small enterprise and local infrastructure levels, UNCDF contributes to the Sustainable Development Goals (SDGs), particularly Goal 1 on eradicating poverty and Goal 17 on the means of implementation. UNCDF also contributes to other SDGs by identifying those market segments where innovative financing models can have transformational impact in helping to reach the last mile and address exclusion and inequalities of access. To achieve these goals, UNCDF is providing financial support and technical expertise to the public and the private sector. It provides capital financing – in the form of grants, soft loans and credit enhancement products – and the technical expertise to unleash sustainable financing at the local level.

***UNCDF in Uganda***

UNCDF has been present in Uganda since 1982, supporting the Government to create a functional planning and financial system for sustainable and inclusive local development. With the support of the Sweden Development Agency (SIDA) - is implementing the “Leaving No One Behind in the Digital Era” programme that aims to empower rural community members to lead productive and healthy lives, by expanding access and usage of digital services.

**BACKGROUND OF THE ASSIGNMENT:**

This assignment is commissioned by UNCDF Uganda in partnership with the Uganda Bankers’ Association (UBA) and Financial Technology Association of Uganda (FITSPA). We are looking for a consultant to undertake a study on the feasibility of establishing an Agritech Database in Uganda.

***Rationale for the Assignment:***

The Agricultural sector is critical to Uganda’s economic development. It contributed 23.7% to the overall GDP (2019/20), accounts for 20% of total value of exports and employs about 72% of the total workforce in Uganda. Uganda’s National Development Plan III identifies the agriculture sector as a key catalytic sector for the development of Uganda’s economy and has focused initiatives to develop and industrialize agriculture.

Access to finance remains a key bottleneck to the growth of the agricultural sector. In Uganda, lending to the agricultural sector accounted for 12.7% of total bank lending by the end of February 2021, from 6.7% in the period December 2020. The share of this financing that goes to small businesses in agriculture and small holder farmers is even much lower. Financial institutions decry the risks prevalent in the sector plus limited and unreliable data on which to base their lending decisions. This is a long-standing challenge.

The growing availability of alternative data thanks to digitalization efforts in Agriculture could hold a potential solution to alleviating the challenge of access to finance. Various fintech's and agritechs collect a lot of data from customers through farmer profiling, production and sales data, digital payments, etc. This data which currently lies in independent databases could be aggregated and made accessible to financial service providers to enable farmer credit scoring and thus unlock financing to the agricultural sector.

UNCDF, in partnership with UBA and FITSPA, seek to deeply investigate this potential – by undertaking a feasibility study for the establishment of an aggregated Agritech Database.

***Objective of the assignment***

The consultancy aims to achieve the following objectives:

* Assess the desirability, feasibility and viability of an Agritech database for Uganda
	+ **Desirability:** Deeply understand the level of need for such a solution among key stakeholders (financial services providers, fintechs, agritechs, public and development sector actors in the agriculture and finance sectors). This includes collection of stakeholder perspectives on what it would take for them to uptake / join such a solution/platform.
	+ **Feasibility:** Assess the feasibility for such a solution from a technical and organizational point of view, including collection of perspectives from key stakeholders on the feasibility aspects.
	+ **Viability:** A critical assessment of what it would take for such a platform / solution to be viable and sustainable as a business model.
* Propose the potential structure, design, and business model for establishing such a platform for Uganda, should it be found to be feasible

**SCOPE OF WORK**

Under the supervision of the UNCDF Technical Advisor – Inclusive Digital Economy, the Consultant will deliver on the below scope:

|  |
| --- |
| **Phase 1: Feasibility Assessment** |
| * Establish what data exists:
	+ Reviewing existing databases available within fintech's/Agritechs that already support the agricultural sub sector
	+ Assess the quality and relevance of the data as is available and the feasibility / suitability for aggregation / migration into a unified database.
* Investigate the potential of such a platform for the Ugandan market?
	+ Engage with potential stakeholders as part of background information gathering on their views on the proposed information platform
	+ Readiness to participate and contribute data to the platform
	+ Conducting community consultations to assess the social impact of the proposed intervention, the required support and subsequent considerations.
	+ Dimension the benefits (value proposition) envisaged for all parties/stakeholders
	+ Confirm the key data points as will be accepted by the various stakeholders in the Agritech ecosystem, and the framework that will enable the input of, and maintenance of said data.
* What might be working elsewhere?
	+ Conduct a desk review of where related initiatives have been developed and how they work.
	+ Investigate what platforms / business models can be benchmarked
* What barriers and risks exist in the establishment of such a platform?
	+ Identify the barriers, risk and challenges that could determine the sustainability of the project and make recommendations to manage the same and limit the impact on the project success.
	+ Identify and analyze any governance and capacity issues that will be critical during the implementation of the project as well as to ensure sustainability of the project.
 |
| **Phase 2: Proposed concept and design of the Agritech Database for Uganda**  |
| * Propose what might work for Uganda?
	+ Conceptualize how the proposed information platform will work including the operating framework, business model, standard operating procedures and rules of engagement.
	+ Dimension the roles of the various stakeholders (Agritechs, Supervised Financial Institutions, Benefiting Farmers, BOU, the regulator) including benefits to each
	+ Recommend the framework data collection, collation and input into the database, as well as maintenance and use of the same.
	+ In collaboration with the engineering team, design and prepare schematic drawings with technical specification of the proposed Agritech information platform
	+ In collaboration with the engineering team, provide an indication of the cost of setting up and running such Agritech information platform.
	+ Develop the initial project plan with key phases and activities for setting up such a platform.
 |

**EXPECTED DELIVERABLES AND SCHEDULES**

The table below outlines the key activities, deliverables and estimated timeline.

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **Activity**  | **Output**  | **Target due date** | **% Payment**  |
| 1 | * Inception meeting conducted
* Drafting of the inception report.
 | Minutes to the Inception meeting and attendance register of the meeting submitted. Inception report approved. | October 2022 | 20% |
| 2 | * Undertake feasibility assessment as per the scope of the assignment
 | Draft Feasibility Assessment report covering the phase 1 scope of work submitted and approved | November 2022 | 30% |
| 3 | * Validation debriefing and presentation of the draft feasibility report, its findings, and recommendations to stakeholders. This validation should lead to the finalization of the feasibility assessment report.
 | Final Feasibility Assessment Report – Delivered and approved | November 2022 | 20% |
| 4  | Proposal document: concept and design of the Agritech Database for Uganda* Drafted
* Presented / discussed
* Approved
 | Concept proposal containing operating framework, business model, standard operating procedures and rules of engagement for Agritech Database for Uganda submitted and approved | December 2022  | 30% |
|  | **Total** |  |  | **100%** |

**Institutional Arrangement**

This assignment is commissioned by UNCDF in partnership with UBA and FITSPA. A steering committee – composed of members from the partner institutions - will be set up to oversee the assignment.

* The consultant is expected work closely with the steering committee through the assignment
	+ Project meetings will be held at the submission of each milestone.
	+ Other technical meetings might be held as deemed necessary through the course of the assignment
* Approval of deliverables will do by the steering committee.
* Payments shall be made only upon satisfactory completion and UNCDF’s written acceptance of each deliverable duly approved by the UNCDF Digital Country Lead
* Disbursement of the final payment shall require a signed performance evaluation of the consultant.

**Facilities to be provided by UNCDF**

* For validation meetups or workshops with stakeholders, UNCDF and the partners will provide premises and conferencing tools.

**Duration of the work**

* The duration of the study is 50 working days spread across 3 months.
* The target date of commencement is 1st November 2022, and the expected completion date is 30th January 2023.

**Duty Station**

* The consultant will be remote based (in Kampala) unless called upon for meetings by the partners.

**Travel**

* There is no travel required for this assignment

**Qualifications of the Successful Contractor:**

The successful consultant will have a background in ICT / digital transformation applied to the financial sectors and/or extensive functional experience in Fintech / Agritech in Uganda or other East African countries with strong technical skills in project design and management.

Academic qualifications:

* + Postgraduate degree (Masters) in International Development, ICT, Economics, Management or closely related field.

Skills and Experience:

* + Minimum 7 years of technical experience in business development, financial sector development, leading projects in fintech / Agritech
	+ Demonstrable experience and/or understanding of the financial sector and Fintech / Agritech industry in Uganda or other East African countries, with exposure to other emerging / developed markets.
	+ Substantial relevant experience in undertaking feasibility studies, designing and implementation of innovative digital projects.
	+ Experience in economic and financial analysis for project viability and budget formulation.
	+ Experience in the formulation and management of similar / related projects and innovations:
	+ Working with multi-disciplinary teams, including local and expatriate technical experts.
	+ Strong analytical skills; Exceptional ability in communication and networking, negotiations and writing.
	+ Flexibility and ability to operate in different cultural settings and with a variety of stakeholders, culturally and gender sensitive.

Personal Competencies

* Demonstrates integrity by modeling the UN's values and ethical standards.
* Advocates and promotes the vision, mission, and strategic goals of the UN.
* Displays cultural, gender, religion, race, nationality and age sensitivity and adaptability.
* Treats all people fairly without favoritism.
* Demonstrates and promotes the values of the UN in actions and decisions and acts in accordance with the standard of conduct for international civil servants.
* Shows willingness to work without bias with all persons regardless of gender, nationality, religion, or culture.
* Contributes effectively to team-based activities, working collaboratively and sharing information openly; works effectively with colleagues inside the UN as well as its partners and other stakeholders to pursue common goals.

Language requirements

* Fluent command of written and spoken English is mandatory

**APPLICATION PROCESS AND EVALUATION METHOD**

**APPLICATION PROCESS**

Interested individuals must submit the following documents as proposals to demonstrate their qualifications.

The application must contain the following:

(a) Personal Profile:

Cover letter demonstrating the Approach/Methodology on how the assignment will be executed (1 page).

Duly accomplished Letter of Confirmation of Interest and Availability

**A Curriculum Vitae (CV) or P.11 Personal History Form** (available at <http://sas.undp.org/documents/p11_personal_history_form.doc>), stipulating applicant’s official names, their qualifications and professional experiences (with similar projects) relevant to the assignment/TOR and the contact details (email address, telephone numbers) of 3 professional references.

 (b) **A signed financial proposal for the assignment,** Completed and duly signed Letter of Confirmation of Interest and Availability, quoted in **Uganda Shillings**, outlining the all-inclusive fee, supported by a breakdown of reimbursable – direct and indirect – costs (if applicable). (see click here for document)

Incomplete applications will not be considered. Please make sure you have provided all requested documents.

Proposal should be submitted through <http://jobs.undp.org> , no later than 16th October 2022.

**EVALUATION METHOD, Applications will be scored based on technical and financial submissions. The following selection method will be used: Highest rated proposal using the combined scoring method, which assigns the weight distribution between the technical and financial proposals. The weight distribution shall be 70% technical and 30%**

Only candidates obtaining a minimum of 49 points (70% of the total technical points) will be considered as technically qualified and will be reviewed further for the Financial Evaluation

Technical Criteria –70 %

The technical criteria will comprise of two parts:

Part 1 - will contribute 50% to the technical evaluation. Candidates scoring a minimum of 70 points will be considered for the oral interview. The following will be considered:

|  |  |
| --- | --- |
| **Criteria** | **scoring** |
| 1. Academic qualifications of the consultant

Postgraduate degree (Masters) in International Development, ICT, Economics, Management, or closely related field | **7 points** |
| 1. Experience of the consultant
* experience in undertaking feasibility studies, designing and implementation of innovative digital projects
* technical experience in business development, financial sector development, leading projects in fintech / Agritech
* experience and/or understanding of the financial sector and Fintech / Agritech industry in Uganda or other East African countries, with exposure to other emerging / developed markets
* Experience in the formulation and management of similar / related projects and innovations
 | **28 points**  |
| 1. Quality of the technical proposal
* The proposed approach and methodology to the study
* The proposed workplan
 | **35 points** |

Part 2 – the oral interview will contribute 50% to the technical evaluation. Candidates that pass the technical assessment will be invited to the oral interview.

Financial Criteria – 30%

The following formula will be used to evaluate financial proposal:

* Lowest priced proposal/price of the proposal being evaluated x 30. All financial proposals shall be submitted along with the applications, and no modification shall be made on the proposals unless requested by UNCDF

Cumulative analysis:

The award of the contract shall be made to the individual consultant whose offer has been evaluated and determined as:

a) responsive/compliant/acceptable, and

b) Having received the highest score out of a pre-determined set of weighted technical and financial criteria specific to the solicitation. Example 70%-30%.

Individual consultants and persons employed by a company or institution are invited to apply. Any individual employed by a company or institution who would like to submit an offer in response to a Procurement Notice for individual consultant must do so in their individual capacity by providing a CV so that their qualifications may be judged accordingly.

Women candidates or women-owned businesses are strongly encouraged to apply.

UNCDF is committed to achieving workforce diversity in terms of gender, nationality and culture. Individuals from minority groups, indigenous groups and persons with disabilities are equally encouraged to apply. All applications will be treated with the strictest confidence.

Any request for clarification must be sent in writing, or by standard electronic communication to the address or email uncdf.procurement@uncdf.org UNCDF will respond in writing or by standard electronic mail and will send written copies of the response, including an explanation of the query without identifying the source of inquiry, to all consultants.

References

UNDP’s Individual Consultant’s General Terms and Conditions are provided here:

http://www.undp.org/content/dam/undp/documents/procurement/docum

**Annex 2**

**OFFEROR’S LETTER TO UNDP**

**CONFIRMING INTEREST AND AVAILABILITY**

**FOR THE INDIVIDUAL CONTRACTOR (IC) ASSIGNMENT**

Date

**Elsie G Attafuah**

**Resident Representative,**

**United Nations Development Programme,**

**11 Yusuf Lule Road, Nakasero,**

**Kampala, Uganda**

Dear Sir/Madam:

I hereby declare that:

1. I have read, understood and hereby accept the Terms of Reference describing the duties and responsibilities of [*indicate title of assignment*] under the [*state project title*];
2. I have also read, understood and hereby accept UNDP’s General Conditions of Contract for the Services of the Individual Contractors.
3. I hereby propose my services and I confirm my interest in performing the assignment through the submission of my CV which I have duly signed and attached hereto as Annex I;
4. In compliance with the requirements of the Terms of Reference, I hereby confirm that I am available for the entire duration of the assignment, and I shall perform the services in the manner described in my proposed approach/methodology which I have attached hereto as Annex III
5. I hereby propose to complete the services based on the following payment rate: *[please check the box corresponding to the preferred option]:*
* An all-inclusive daily fee of [*state amount in words and in numbers indicating currency]*
* A total lump sum of [*state amount in words and in numbers, indicating exact currency]*, payable in the manner described in the Terms of Reference.
1. For your evaluation, the breakdown of the abovementioned all-inclusive amount is attached hereto as Annex II.
2. I recognize that the payment of the abovementioned amounts due to me shall be based on my delivery of outputs within the timeframe specified in the TOR, which shall be subject to UNDP's review, acceptance, and payment certification procedures.
3. This offer shall remain valid for a total period of \_\_\_\_\_\_\_\_\_\_\_ days [*minimum of 90 days*] after the submission deadline.
4. I confirm that I have no first degree relative (mother, father, son, daughter, spouse/partner, brother or sister) currently employed with any UN agency or office *[disclose the name of the relative, the UN office employing the relative, and the relationship if, any such relationship exists].*
5. If I am selected for this assignment, I shall *[please check the appropriate box]:*
* Sign an Individual Contract with UNDP.
* Request my employer *[state name of company/organization/institution]* to sign with UNDP a Reimbursable Loan Agreement (RLA), for and on my behalf. The contact person and details of my employer for this purpose are as follows:

1. I hereby confirm that *[check all that applies]*:
* At the time of this submission, I have no active Individual Contract or any form of engagement with any Business Unit of UNDP.
* I am currently engaged with UNDP and/or other entities for the following work:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Assignment** | **Contract Type** | **UNDP Business Unit / Name of Institution/Company** | **Contract Duration** | **Contract Amount** |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |

* I am also anticipating conclusion of the following work from UNDP and/or other entities for which I have submitted a proposal:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Assignment** | **Contract Type**  | **Name of Institution/ Company** | **Contract Duration** | **Contract Amount** |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |

1. I fully understand and recognize that UNDP is not bound to accept this proposal, and I also understand and accept that I shall bear all costs associated with its preparation and submission and that UNDP will in no case be responsible or liable for those costs, regardless of the conduct or outcome of the selection process.
2. ***If you are a former staff member of the United Nations recently separated, please add this section to your letter:*** I hereby confirm that I have complied with the minimum break in service required before I can be eligible for an Individual Contract.
3. I also fully understand that, if I am engaged as an Individual Contractor, I have no expectations nor entitlements whatsoever to be re-instated or re-employed as a staff member.
4. Are any of your relatives employed by UNDP, any other UN organization or any other public international organization?

 YES  NO If the answer is "yes", give the following information:

|  |  |  |
| --- | --- | --- |
| **Name** | **Relationship** | **Name of International Organization** |
|  |  |  |
|  |  |  |
|  |  |  |

1. Do you have any objections to our making enquiries of your present employer?

 YES  NO 

1. Are you now, or have you ever been a permanent civil servant in your government’s employ?

 YES  NO  If answer is "yes", WHEN?

1. REFERENCES: List three persons, not related to you, who are familiar with your character and qualifications.

|  |  |  |
| --- | --- | --- |
| **Full Name** | **Full Address** | **Business or Occupation** |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |

1. Have you been arrested, indicted, or summoned into court as a defendant in a criminal proceeding, or convicted, fined or imprisoned for the violation of any law (excluding minor traffic violations)?

 YES  NO  If "yes", give full particulars of each case in an attached statement.

I certify that the statements made by me in answer to the foregoing questions are true, complete, and correct to the best of my knowledge and belief. I understand that any misrepresentation or material omission made on a Personal History form or other document requested by the Organization may result in the termination of the service contract or special services agreement without notice.

 DATE: SIGNATURE:

NB. You will be requested to supply documentary evidence which support the statements you have made above. Do not, however, send any documentary evidence until you have been asked to do so and, in any event, do not submit the original texts of references or testimonials unless they have been obtained for the sole use of UNDP.

**Annexes** *[please check all that applies]***:**

* CV shall include Education/Qualification, Processional Certification, Employment Records /Experience
* Breakdown of Costs Supporting the Final All-Inclusive Price as per Template
* Brief Description of Approach to Work

**ANNEX II**

**BREAKDOWN OF COSTS**

**SUPPORTING THE ALL-INCLUSIVE FINANCIAL PROPOSAL**

1. **Breakdown of Cost by Components:**

|  |  |  |  |
| --- | --- | --- | --- |
| **Cost Components** | **Unit Cost** | **Quantity** | **Total Rate for the Contract Duration** |
| 1. **Personnel Costs**
 |  |  |  |
| Professional Fees |  |  |  |
| Life Insurance |  |  |  |
| Medical Insurance  |  |  |  |
| Communications |  |  |  |
| Land Transportation |  |  |  |
| Others (pls. specify) |  |  |  |
|   |  |  |  |
| 1. **Travel Expenses to Join duty station**
 |  |  |  |
| Round Trip Airfares to and from duty station |  |  |  |
| Living Allowance |  |  |  |
| Travel Insurance |  |  |  |
| Terminal Expenses |  |  |  |
| Others (pls. specify) |  |  |  |
|  |  |  |  |
| 1. **Duty Travel**
 |  |  |  |
| Round Trip Airfares |  |  |  |
| Living Allowance |  |  |  |
| Travel Insurance |  |  |  |
| Terminal Expenses |  |  |  |
| Others (pls. specify) |  |  |  |
| Overall total |  |  |

1. **Breakdown of Cost by Deliverables\***

|  |  |  |
| --- | --- | --- |
| **Deliverables***[list them as referred to in the TOR]* | **Percentage of Total Price (Weight for payment)** | **Amount** |
| Deliverable 1 |  |  |
| Deliverable 2 |  |  |
| …. |  |  |
| Total  | 100% | UGX…… |

*\*Basis for payment tranches*

**Annex 3**

**GENERAL CONDITIONS OF CONTRACT FOR THE SERVICES OF INDIVIDUAL**

**CONTRACTORS**

1. **LEGAL STATUS:** The Individual Contractor shall have the legal status of an independent contractor vis-à-vis the United Nations Development Programme (UNDP), and shall not be regarded, for any purposes, as being either a “staff member” of UNDP, under the UN Staff Regulations and Rules, or an “official” of UNDP, for purposes of the Convention on the Privileges and Immunities of the United Nations, adopted by the General Assembly of the United Nations on 13 February 1946. Accordingly, nothing within or relating to the Contract shall establish the relationship of employer and employee, or of principal and agent, between UNDP and the Individual Contractor. The officials, representatives, employees or subcontractors of UNDP and of the Individual Contractor, if any, shall not be considered in any respect as being the employees or agents of the other, and UNDP and the Individual Contractor shall be solely responsible for all claims arising out of or relating to their engagement of such persons or entities.

1. **STANDARDS OF CONDUCT:**
2. **General**: The Individual Contractor shall neither seek nor accept instructions from any authority external to UNDP in connection with the performance of his or her obligations under the Contract. Should any authority external to UNDP seek to impose any instructions regarding the Individual Contractor’s performance under the Contract, the Individual Contractor shall promptly notify UNDP and shall provide all reasonable assistance required by UNDP. The Individual Contractor shall not take any action in respect of his or her performance of the Contract or otherwise related to his or her obligations under the Contract that may adversely affect the interests of UNDP. The Individual Contractor shall perform his or her obligations under the Contract with the fullest regard to the interests of UNDP. The Individual Contractor warrants that she or he has not and shall not offer any direct or indirect benefit arising from or related to the performance of the Contract or the award thereof to any representative, official, employee or other agent of UNDP. The Individual Contractor shall comply with all laws, ordinances, rules and regulations bearing upon the performance of his or her obligations under the Contract. In the performance of the Contract the Individual Contractor shall comply with the standards of conduct set in the Secretary General’s Bulletin ST/SGB/2002/9 of 18 June 2002, entitled “Regulations Governing the Status, Basic Rights and Duties of Officials other than Secretariat Officials, and Expert on Mission”. The Individual Contractor must comply with all security directives issued by UNDP.
3. **Prohibition of Sexual Exploitation and Abuse, and Sexual Harassment**: Without limitation to the terms set forth in (a) above, in the performance of the Contract, the Individual Contractor shall comply with the standards of conduct set forth in the Secretary-General’s bulletin ST/SGB/2003/13 of 9 October 2003, concerning “Special measures for protection from sexual exploitation and sexual abuse”. In particular, the Individual Contractor shall not engage in any conduct that would constitute sexual exploitation or sexual abuse (“SEA”), as defined in that bulletin. Moreover, and without limitation to the application of other regulations, rules, policies and procedures, bearing upon the performance of the activities under the Contract, the Individual Contractor shall comply with the standards of conduct stated in UNDP’s policy on “Harassment, Sexual Harassment, Discrimination, and Abuse of Authority” set forth in the Programme and Operations Policies and Procedures.

In the performance of the Contract, should sufficient information of prohibited conduct including but not limited to sexual harassment (“SH”), and/or SEA, against the Individual Contractor be brought to UNDP’s attention, UNDP shall commence an investigation into the Individual Contractor’s conduct in this regard in accordance with UNDP regulations, rules, policies and procedures. Should the allegations (i) be found to have been substantiated and (ii) should they constitute grounds for termination of this Individual Contract, even after the expiry or termination of the Individual Contract, where such prohibited conduct involves SH or SEA, the Individual Contractor’s name will be placed into an internal United Nations’ database which may affect the Individual Contractor’s ability to work with/for the United Nations System in any capacity in the future.

1. The Individual Contractor acknowledges and agrees that any breach of any of the provisions set forth in Article 2 (a) and (b) shall constitute a breach of an essential term of the Contract, and, in addition to any other legal rights or remedies available to any person, shall give rise to grounds for suspension or termination of the Contract. In addition, nothing herein shall limit the right of UNDP to refer any alleged breach of the foregoing standards of conduct or any other terms of the Contract to the relevant national authorities for appropriate legal action.

1. **TITLE RIGHTS, COPYRIGHTS, PATENTS AND OTHER PROPRIETARY RIGHTS:** Title to any equipment and supplies that may be furnished by UNDP to the Individual Contractor for the performance of any obligations under the Contract shall rest with UNDP, and any such equipment and supplies shall be returned to UNDP at the conclusion of the Contract or when no longer needed by the Individual Contractor. Such equipment and supplies, when returned to UNDP, shall be in the same condition as when delivered to the Individual Contractor, subject to normal wear and tear, and the Individual Contractor shall be liable to compensate UNDP for any damage or degradation of the equipment and supplies that is beyond normal wear and tear.

UNDP shall be entitled to all intellectual property and other proprietary rights, including, but not limited to, patents, copyrights and trademarks, with regard to products, processes, inventions, ideas, know-how or documents and other materials which the Individual Contractor has developed for UNDP under the Contract and which bear a direct relation to, or are produced or prepared or collected in consequence of, or during the course of, the performance of the Contract, and the Individual Contractor acknowledges and agrees that such products, documents and other materials constitute works made for hire for UNDP. However, to the extent that any such intellectual property or other proprietary rights consist of any intellectual property or other proprietary rights of the Individual Contractor: (a) that pre-existed the performance by the Individual Contractor of his or her obligations under the Contract, or (b) that the Individual Contractor may develop or acquire, or may have developed or acquired, independently of the performance of his or her obligations under the Contract, UNDP does not and shall not claim any ownership interest thereto, and the Individual Contractor grants to UNDP a perpetual license to use such intellectual property or other proprietary right solely for the purposes of and in accordance with the requirements of the Contract. At the request of UNDP, the Individual Contractor shall take all necessary steps, execute all necessary documents and generally assist in securing such proprietary rights and transferring or licensing them to UNDP in compliance with the requirements of the applicable law and of the Contract. Subject to the foregoing provisions, all maps, drawings, photographs, mosaics, plans, reports, estimates, recommendations, documents and all other data compiled by or received by the Individual Contractor under the Contract shall be the property of UNDP, shall be made available for use or inspection by UNDP at reasonable times and in reasonable places, shall be treated as confidential and shall be delivered only to UNDP authorized officials on completion of services under the Contract

1. **CONFIDENTIAL NATURE OF DOCUMENTS AND INFORMATION:** Information and data that are considered proprietary by either UNDP or the Individual Contractor or that are delivered or disclosed by one of them (“Discloser”) to the other (“Recipient”) during the course of performance of the Contract, and that are designated as confidential (“Information”), shall be held in confidence and shall be handled as follows. The Recipient of such Information shall use the same care and discretion to avoid disclosure, publication or dissemination of the Discloser’s Information as it uses with its own similar information that it does not wish to disclose, publish or disseminate, and the Recipient may otherwise use the Discloser’s Information solely for the purpose for which it was disclosed. The Recipient may disclose confidential Information to any other party with the Discloser’s prior written consent, as well as to the Recipient’s officials, representatives, employees, subcontractors and agents who have a need to know such confidential Information solely for purposes of performing obligations under the Contract. Subject to and without any waiver of the privileges and immunities of UNDP, the Individual Contractor may disclose Information to the extent required by law, *provided that* the Individual Contractor will give UNDP sufficient prior notice of a request for the disclosure of Information in order to allow UNDP to have a reasonable opportunity to take protective measures or such other action as may be appropriate before any such disclosure is made. UNDP may disclose Information to the extent required pursuant to the Charter of the United Nations, resolutions or regulations of the General Assembly or its other governing bodies, or rules promulgated by the Secretary-General. The Recipient shall not be precluded from disclosing Information that is obtained by the Recipient from a third party without restriction, is disclosed by the Discloser to a third party without any obligation of confidentiality, is previously known by the Recipient, or at any time is developed by the Recipient completely independently of any disclosures hereunder. These obligations and restrictions of confidentiality shall be effective during the term of the Contract, including any extension thereof, and, unless otherwise provided in the Contract, shall remain effective following any termination of the Contract. Notwithstanding the foregoing, the Individual Contractor acknowledges that UNDP may, in its sole discretion, disclose the purpose, type, scope, duration and value of the Contract, the name of the Individual Contractor, and any relevant information related to the award of the Contract.

1. **TRAVEL, MEDICAL CLEARANCE AND SERVICE INCURRED DEATH, INJURY OR**

**ILLNESS:** If the Individual Contractor is required by UNDP to travel beyond commuting distance from the Individual Contractor’s usual place of residence, and upon prior written agreement, such travel shall be at the expense of UNDP. Such travel shall be at economy fare when by air.

UNDP may require the Individual Contractor to submit a “statement of good health” from a recognized physician prior to commencement of services in any offices or premises of UNDP, or before engaging in any travel required by UNDP, or connected with the performance of the Contract. The Individual Contractor shall provide such a statement as soon as practicable following such request, and prior to engaging in any such travel, and the Individual Contractor warrants the accuracy of any such statement, including, but not limited to, confirmation that the Individual Contractor has been fully informed regarding the requirements for inoculations for the country or countries to which travel may be authorized.

In the event of death, injury or illness of the Individual Contractor which is attributable to the performance of services on behalf of UNDP under the terms of the Contract while the Individual Contractor is traveling at UNDP expense or is performing any services under the Contract in any offices or premises of UNDP, the Individual Contractor or the Individual Contractor’s dependents, as appropriate, shall be entitled to compensation equivalent to that provided under the UNDP insurance policy, available upon request.

1. **PROHIBITION ON ASSIGNMENT; MODIFICATIONS:** The Individual Contractor may not assign, delegate, transfer, pledge or make any other disposition of the Contract, of any part thereof, or of any of the rights, claims or obligations under the Contract except with the prior written authorization of UNDP, and any attempt to do so shall be null and void. The terms or conditions of any supplemental undertakings, licenses or other forms of Contract concerning any goods or services to be provided under the Contract shall not be valid and enforceable against UNDP nor in any way shall constitute a contract by UNDP thereto, unless any such undertakings, licenses or other forms of contract are the subject of a valid written undertaking by UNDP. No modification or change in the Contract shall be valid and enforceable against UNDP unless provided by means of a valid written amendment to the Contract signed by the Individual Contractor and an authorized official or appropriate contracting authority of UNDP.

1. **SUBCONTRACTORS**: In the event that the Individual Contractor requires the services of subcontractors to perform any obligations under the Contract, the Individual Contractor shall obtain the prior written approval of UNDP for any such subcontractors. UNDP may, in its sole discretion, reject any proposed subcontractor or require such subcontractor’s removal without having to give any justification therefore, and such rejection shall not entitle the Individual Contractor to claim any delays in the performance, or to assert any excuses for the non-performance, of any of his or her obligations under the Contract. The Individual Contractor shall be solely responsible for all services and obligations performed by his or her subcontractors. The terms of any subcontract shall be subject to and shall be construed in a manner that is fully in accordance with, all of the terms and conditions of the Contract.

1. **USE OF NAME, EMBLEM OR OFFICIAL SEAL OF THE UNITED NATIONS:** The Individual

Contractor shall not advertise or otherwise make public for purposes of commercial advantage or goodwill that it has a contractual relationship with UNDP, nor shall the Individual Contractor, in any manner whatsoever, use the name, emblem or official seal of UNDP, or any abbreviation of the name of UNDP, in connection with his or her business or otherwise without the written permission of UNDP.

1. **INDEMNIFICATION:** The Individual Contractor shall indemnify, defend, and hold and save harmless UNDP, and its officials, agents and employees, from and against all suits, proceedings, claims, demands, losses and liability of any kind or nature, including, but not limited to, all litigation costs and expenses, attorney’s fees, settlement payments and damages, based on, arising from, or relating to: (a) allegations or claims that the use by UNDP of any patented device, any copyrighted material or any other goods or services provided to UNDP for its use under the terms of the Contract, in whole or in part, separately or in combination, constitutes an infringement of any patent, copyright, trademark or other intellectual property right of any third party; or (b) any acts or omissions of the Individual Contractor, or of any subcontractor or anyone directly or indirectly employed by them in the performance of the Contract, which give rise to legal liability to anyone not a party to the Contract, including, without limitation, claims and liability in the nature of a claim for workers’ compensation.

1. **INSURANCE:** The Individual Contractor shall pay UNDP promptly for all loss, destruction or damage to the property of UNDP caused by the Individual Contractor, or of any subcontractor, or anyone directly or indirectly employed by them in the performance of the Contract. The Individual Contractor shall be solely responsible for taking out and for maintaining adequate insurance required to meet any of his or her obligations under the Contract, as well as for arranging, at the Individual Contractor’s sole expense, such life, health and other forms of insurance as the Individual Contractor may consider to be appropriate to cover the period during which the Individual Contractor provides services under the Contract. The Individual Contractor acknowledges and agrees that none of the insurance arrangements the Individual Contractor shall, in any way, be construed to limit the Individual Contractor’s liability arising under or relating to the Contract.

1. **ENCUMBRANCES AND LIENS:** The Individual Contractor shall not cause or permit any lien, attachment or other encumbrance by any person to be placed on file or to remain on file in any public office or on file with UNDP against any monies due to the Individual Contractor or to become due for any work donor or against any goods supplied or materials furnished under the Contract, or by reason of any other claim or demand against the Individual Contractor.

1. **FORCE MAJEURE; OTHER CHANGES IN CONDITIONS:** In the event of and as soon as possible after the occurrence of any cause constituting force majeure, the Individual Contractor shall give notice and full particulars in writing to UNDP of such occurrence or cause if the Individual Contractor is thereby rendered unable, wholly or in part, to perform his or her obligations and meet his or her responsibilities under the Contract. The Individual Contractor shall also notify UNDP of any other changes in conditions or the occurrence of any event, which interferes or threatens to interfere with the performance of the Contract. Not more than fifteen (15) days following the provision of such notice of force majeure or other changes in conditions or occurrence, the Individual Contractor shall also submit a statement to UNDP of estimated expenditures that will likely be incurred for the duration of the change in conditions or the event. On receipt of the notice or notices required hereunder, UNDP shall take such action as it considers, in its sole discretion, to be appropriate or necessary in the circumstances, including the granting to the Individual Contractor of a reasonable extension of time in which to perform any obligations under the Contract or suspension thereof.

Force majeure as used herein means any unforeseeable and irresistible act of nature, any act of war (whether declared or not), invasion, revolution, insurrection, or any other acts of a similar nature or force, provided that such acts arise from causes beyond the control and without the fault or negligence of the Individual Contractor. The Individual Contractor acknowledges and agrees that, with respect to any obligations under the Contract that the Individual Contractor must perform in or for any areas in which UNDP is engaged in, preparing to engage in, or disengaging from any peacekeeping, humanitarian or similar operations, any delay or failure to perform such obligations arising from or relating to harsh conditions within such areas or to any incidents of civil unrest occurring in such areas shall not, in and of itself, constitute force majeure under the Contract

1. **TERMINATION:** Either party may terminate the Contract, in whole or in part, upon giving written notice to the other party. The period of notice shall be five (5) days in the case of contracts for a total period of less than two (2) months and fourteen (14) days in the case of contracts for a longer period. The initiation of conciliation or arbitral proceedings, as provided below, shall not be deemed to be a “cause” for or otherwise to be in itself a termination of the Contract. UNDP may, without prejudice to any other right or remedy available to it, terminate the Contract forthwith in the event that: (a) the Individual Contractor is adjudged bankrupt, or is liquidated, or becomes insolvent, applies for moratorium or stay on any payment or repayment obligations, or applies to be declared insolvent; (b) the Individual Contractor is granted a moratorium or a stay or is declared insolvent; (c) the Individual Contractor makes an assignment for the benefit of one or more of his or her creditors; (d) a Receiver is appointed on account of the insolvency of the Individual Contractor; (e) the Individual Contractor offers a settlement in lieu of bankruptcy or receivership; or (f) UNDP reasonably determines that the Individual Contractor has become subject to a materially adverse change in financial condition that threatens to endanger or otherwise substantially affect the ability of the Individual Contractor to perform any of the obligations under the Contract.

In the event of any termination of the Contract, upon receipt of notice of termination by UNDP, the Individual Contractor shall, except as may be directed by UNDP in the notice of termination or otherwise in writing: (a) take immediate steps to bring the performance of any obligations under the Contract to a close in a prompt and orderly manner, and in doing so, reduce expenses to a minimum; (b) refrain from undertaking any further or additional commitments under the Contract as of and following the date of receipt of such notice; (c) deliver all completed or partially completed plans, drawings, information and other property that, if the Contract had been completed, would be required to be furnished to UNDP thereunder; (d) complete performance of the services not terminated; and (e) take any other action that may be necessary, or that UNDP may direct in writing, for the protection and preservation of any property, whether tangible or intangible, related to the Contract that is in the possession of the Individual Contractor and in which UNDP has or may be reasonably expected to acquire an interest.

In the event of any termination of the Contract, UNDP shall only be liable to pay the Individual Contractor compensation on a pro rata basis for no more than the actual amount of work performed to the satisfaction of UNDP in accordance with the requirements of the Contract. Additional costs incurred by UNDP as a result of termination of the Contract by the Individual Contractor may be withheld from any amount otherwise due to the Individual Contractor by UNDP.

1. **NON-EXCLUSIVITY:** UNDP shall have no obligation respecting, and no limitations on, its right to obtain goods of the same kind, quality and quantity, or to obtain any services of the kind described in the Contract, from any other source at any time.

1. **TAXATION:** Article II, section 7, of the Convention on the Privileges and Immunities of the United Nations provides, inter alia, that the United Nations, including its subsidiary organs, is exempt from all direct taxes, except charges for public utility services, and is exempt from customs restrictions, duties and charges of a similar nature in respect of articles imported or exported for its official use. In the event any governmental authority refuses to recognize the exemptions of the United Nations from such taxes, restrictions, duties or charges, the Individual Contractor shall immediately consult with UNDP to determine a mutually acceptable procedure. UNDP shall have no liability for taxes, duties or other similar charges payable by the Individual Contractor in respect of any amounts paid to the Individual Contractor under this Contract, and the Individual Contractor acknowledges that UNDP will not issue any statements of earnings to the Individual Contractor in respect of any such payments

1. **AUDITS AND INVESTIGATIONS**: Each invoice paid by UNDP shall be subject to a post-payment audit by auditors, whether internal or external, of UNDP or by other authorized and qualified agents of UNDP. The Individual Contractor acknowledges and agrees that UNDP may conduct investigations relating to any aspect of the Contract or the award thereof, and the obligations performed thereunder.

The Individual Contractor shall provide full and timely cooperation with any post-payment audits or investigations hereunder. Such cooperation shall include, but shall not be limited to, the Individual Contractor’s obligation to make available any relevant documentation and information for the purposes of a post-payment audit or an investigation at reasonable times and on reasonable conditions. The Individual Contractor shall require his or her employees, subcontractors and agents, if any, including, but not limited to, the Individual Contractor’s attorneys, accountants or other advisers, to reasonably cooperate with any post-payment audits or investigations carried out by UNDP hereunder.

If the findings or circumstances of a post-payment audit or investigation so warrant, UNDP may, in its sole discretion, take any measures that may be appropriate or necessary, including, but not limited to, suspension of the Contract, with no liability whatsoever to UNDP.

The Individual Contractor shall refund to UNDP any amounts shown by a post-payment audit or investigation to have been paid by UNDP other than in accordance with the terms and conditions of the Contract. Such amount may be deducted by UNDP from any payment due to the Individual Contractor under the Contract.

The right of UNDP to conduct a post-payment audit or an investigation and the Individual Contractor’s obligation to comply with such shall not lapse upon expiration or prior termination of the Contract.

1. **SETTLEMENT OF DISPUTES**:

**AMICABLE SETTLEMENT**: UNDP and the Individual Contractor shall use their best efforts to amicably settle any dispute, controversy or claim arising out of the Contract or the breach, termination or invalidity thereof. Where the parties wish to seek such an amicable settlement through conciliation, the conciliation shall take place in accordance with the Conciliation Rules then obtaining of the United Nations Commission on International Trade Law (“UNCITRAL”), or according to such other procedure as may be agreed between the parties in writing.

**ARBITRATION**: Any dispute, controversy or claim between the parties arising out of the Contract, or the breach, termination, or invalidity thereof, unless settled amicably, as provided above, shall be referred by either of the parties to arbitration in accordance with the UNCITRAL Arbitration Rules then obtaining. The decisions of the arbitral tribunal shall be based on general principles of international commercial law. For all evidentiary questions, the arbitral tribunal shall be guided by the Supplementary Rules Governing the Presentation and Reception of Evidence in International Commercial Arbitration of the International Bar Association, 28 May 1983 edition. The arbitral tribunal shall be empowered to order the return or destruction of goods or any property, whether tangible or intangible, or of any confidential information provided under the Co n t r a c t , order the termination of the Contract, or order that any other protective measures be taken with respect to the goods, services or any other property, whether tangible or intangible, or of any confidential information provided under the Contract, as appropriate, all in accordance with the authority of the arbitral tribunal pursuant to Article 26 (“Interim Measures of Protection”) and Article 32 (“Form and Effect of the Award”) of the UNCITRAL Arbitration Rules. The arbitral tribunal shall have no authority to award punitive damages. In addition, unless otherwise expressly provided in the Contract, the arbitral tribunal shall have no authority to award interest in excess of the London Inter-Bank Offered Rate (“LIBOR”) then prevailing, and any such interest shall be simple interest only. The parties shall be bound by any arbitration award rendered as a result of such arbitration as the final adjudication of any such dispute, controversy or claim.

1. **LIMITATION ON ACTIONS**: Except with respect to any indemnification obligations in Article 9, above, or as are otherwise set forth in the Contract, any arbitral proceedings in accordance with Article 17, above, arising out of the Contract must be commenced within three (3) years after the cause of action has accrued.

The Parties further acknowledge and agree that, for these purposes, a cause of action shall accrue when the breach actually occurs, or, in the case of latent defects, when the injured Party knew or should have known all of the essential elements of the cause of action.

1. **PRIVILEGES AND IMMUNITIES**: Nothing in or relating to the Contract shall be deemed a waiver, express or implied, of any of the privileges and immunities of the United Nations, including its subsidiary organs.